Cooperative Research Centre for Landscape Environments and Mineral Exploration

LEME LEGACY PRODUCT

Submitted by:		Colin Pain

Date submitted: 	21/04/07		V2 Lisa Worrall 1.6.07

Project name: 	The CRC LEME Atlas: a Digital Compilation of CRC LEME Regolith Maps

Abbreviated title:	Atlas of Regolith Maps

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		One

Project Leader:  	Colin Pain

Start date and duration:  01/07/06 – 30/06/08 (2 years)

Participants:	 	GA, CSIRO EM, ANU, ANU, CUT, NSW DPI, PIRSA

Brief project description:

In spite of many attempts, LEME has never had a GIS standard for regolith maps, or a policy on archiving spatial data.  This project aims to remedy this situation by employing a GIS contractor to take all the LEME digital regolith maps and standardise them according to Australian spatial data standards.  The maps will then be compiled in an ATLAS form

Deliverables (outputs) and expected impacts of research (outcomes):

- CRC LEME Atlas of Regolith Maps.  The Atlas will be a digital compilation (as GIS coverages) of all the regolith maps produced by LEME.  The outcome will be a set of maps consistent between themselves, and meeting Australian spatial data standards.  This in turn means that LEME regolith maps will continue to be useful long after LEME has ended.

- A report on the status of regolith mapping in Australia

Milestones: (dates of significant events marking scientific progress)

|  | Aug 06 | List of regolith maps produced, and work plan finalised |  |
| --- | --- | --- | --- |
|  | Oct 07 | GIS services | 7 |
|  | Nov 07 | GIS services | 7 |
|  | Dec 07 | GIS services | 7 |
|  | Jan 08 | GIS services | 7 |
|  | Feb 08 | GIS services | 7 |
|  | Mar 08 | Release of Atlas |  |

Confidentiality requirements  None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES 2006-2008

STAFFING-FTEs (eg 0.50) for 2006-2008

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colin Pain | IK |  |  |  |  | 0.20 |  |  | 0.20 |
| TOTAL |  |  |  |  |  | 0.20 |  |  | 0.20 |

PROJECT OPERATING COSTS $K 2006-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 35 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 35 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2008

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GIS Support |  |  |  |  | 30 |  |  | 30 |
| Incidentals |  |  |  |  | 5 |  |  | 5 |
| Total |  |  |  |  | 35 |  |  | 35 |