Cooperative Research Centre for landscape Environments and Mineral Exploration

LEGACY PRODUCT

Submitted by:  Colin Pain

Date submitted:  21/04/07    		V3 - Lisa Worrall 1.6.07

Project name:   CRC LEME Field Guide for Describing and Sampling Regolith Materials

Abbreviated title:  Describing and sampling regolith materials Field Guide

Type of project Centre    (Centre or Industry/Commercial):

Program:    One

Themes:    1. Understanding Regolith Processes

Project Leader:   Colin Pain

Start date and duration:  01/07/06 – 30/12/07 (18 months)

Participants:    GA

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The handbook will be an updated version of the GA RTMAP handbook.  This new handbook will build on CRCLEME field experience, and provide a methodology and set of standards for describing regolith in the field.  It will be of value to anyone dealing with regolith materials in the field.

Deliverables (outputs) and expected impacts of research (outcomes):

A Field Handbook for Describing and Sampling Regolith Materials, produced in a durable form for use in the field.

Milestones: (dates of significant events marking scientific progress)

| f | Mar 07 | First draft |  |
| --- | --- | --- | --- |
|  | Apr – Jun 07 | Revisions |  |
|  | Aug 07 | Submission to Publishers |  |
|  | Dec 07 | Proofs and Publication | 12K |

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs (eg 0.50) for 2007-2008

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colin Pain | IK |  |  |  |  | 0.15 |  |  | 0.15 |
| TOTAL |  |  |  |  |  | 0.15 |  |  | 0.15 |

PROJECT OPERATING COSTS $K 2007-2008

|  | $K | Source external |
| --- | --- | --- |
| CRC Opex funds requested | 12 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 12 |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Printing |  |  |  |  | 12 |  |  | 12 |
| Total |  |  |  |  | 12 |  |  | 12 |