# Cooperative Research Centre for Landscape Environments and Mineral Exploration

LEGACY PROJECT SUMMARY

Project No:  						(Issued by LEME Head Office)

Submitted by:		Charles Butt

Date submitted: 	20 April 2007			V2  31.5.07 RRA

Project name:  	Thematic volume web updates: Regolith expression of Australian ore systems

Abbreviated title: 	Regolith Expression – web updates

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		2

Themes:

Project Leader:  	Charles Butt

# Start date and duration:  1st July 2007;  12 months

Participants:	Charles Butt, Ian Robertson (Keith Scott)

Brief project description:

The aim of the project is to update and expand the existing Thematic Volume Regolith Expressions of Australian Ore Systems by publishing additional case histories on the CRC LEME website.  In particular, case histories from regolith settings, commodities and regions not previously covered or poorly represented will be sought.

The requirement will be to edit new case histories as they are offered and possibly to update and improve existing ones.  The original intent was to have about 150 case histories, but only about 2/3 of these were received and published.  Reaching this original target would be an objective, but unlikely to be achieved – as reflected in the modest time allocation.

At present, only the case histories are published on the web.  It is not intended to place the existing supporting chapters on the website, at least until a substantial proportion of the hard copy volumes have been sold.  Consequently, there is no intention to amend or add to the Models, nor to include other discussion or review material.

Deliverables (outputs) and expected impacts of research (outcomes):

The new case histories will add to the existing compilation of case histories already available on the LEME website as well as in the published monograph.

The additional case histories will expand and develop what is already an important scientific resource.

# Milestones: (dates of significant events marking scientific progress)

31 December 2007	assessment of level of interest from potential authors of new case histories. Publication of 1 case history

1 June 2008 -	completion and web publication of final case histories.

# Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

# RESOURCES 2006-2007

# STAFFING-FTEs

(eg 0.50) for 2007-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CRM Butt |  |  |  |  | 0.05 |  |  |  |  |  |
| IDM Robertson |  |  |  |  | 0.05 |  |  |  |  |  |
| VRU |  |  |  |  | 0.05 |  |  |  |  |  |
| TOTAL |  |  |  |  | 0.15 |  |  |  |  |  |

Possible collaborator:  KM Scott

# All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

# PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| Materials; travel | 4 |  |
| Total Project Opex | 4 |  |

# DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Miscellaneous incl travel |  |  |  | 4 |  |  |  |  |  |
| TOTAL |  |  |  | 4 |  |  |  |  |  |