Cooperative Research Centre for Landscape Environments and Mineral Exploration

LEGACY PRODUCT

Project number……………… (Issued by LEME Head Office)

Submitted by:		Keith Scott

Date: 			April 11 2006

Project name: 	Regolith Textbook

Abbreviated title: 	Regolith Textbook

Type of project 	(Centre or Industry): Centre

Program: Communications - Head Office

Theme:

Project Leader:  Keith Scott

Start date and duration:  July 2006 – end of LEME.

Partners: CSIRO Publishing

Brief project description and what is new:

The book will be a compilation and distillation of work over the past 10 years in LEME 1 and LEME 2 on regolith science.  There are two other textbooks on regolith (Ollier and Pain – Regolith, Soils and Landforms; Taylor and Eggleton – Regolith Geology and Geomorphology). This new book will build on these, and will be aimed at senior university students as well as practitioners in both MINEX and NRM. Details of topics and chapter headings have yet to be finalized. The work will be multi-authored, and edited by Keith Scott and Colin Pain.

Deliverables and expected outcomes:

We have approached CSIRO Publishing with a view to having them publish the book. Details have yet to be finalized.

Milestones:

Invitation to potential authors	May 2006

Deadline for submissions	October 2006

Reviewing	November 2006 – March 2007

Revisions by authors	April 2007 – June 2007

Submission to Publishers	August 2007

Proofs	December 2007

Publication	March 2008

Confidentiality – Nil

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES

Staffing

| Year | Contractor | Core Party | Total |
| --- | --- | --- | --- |
| 2006 | CSIRO (10%) | GA (5%) | 15% |
| 2007 | CSIRO (10%) | GA (5%) | 15 |
| Staff | Name | Name |  |
|  | Keith Scott | Colin Pain |  |

Various LEME staff, and perhaps others, will contribute chapters and sections to the book. This has yet to be finalized.

Funding  (All figures in $K)

| Year | CRC LEME |  |
| --- | --- | --- |
|  | Operating Cash | Salaries | Participant | Totals |
| 2006 | $5000 | $15,000 | CSIRO | $15,000 |
| 2007 | $5000 | $15,000 | CSIRO | $15,000 |
| Totals | $10,000 | $30,000 |  | $40,000 |

External funding: None

Total funding over 2 years:   $40,000