Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY 07-08

Project No: 		 1.23				(Issued by LEME Head Office)

Submitted by:		J Keeling

Date submitted: 	22/04/07		V2  Lisa Worrall  1.6.07

Project name:  	Exploring through Cover in the Central Gawler

Abbreviated title: 	Central Gawler

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		One

Themes:  		1. Understanding of regolith processes

2. Models of regolith landscape evolution

4. Regional mineral exploration studies

5. Making geochemistry more effective

Project Leader:  	J Keeling

Start date and duration:  01/07/03 – 30/06/08 (5 years)

Participants:	 	PIRSA, CSIRO (E&M), AU, GA

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

An arcuate belt of Proterozoic rocks in the central Gawler Craton has been recognised as a potential new gold province of regional significance.  Deposits at Tarcoola, Boomerang, Glenloth and Earea Dam, together with new gold prospects at Tunkillia, Nuckulla Hill, Barns, Baggy Green and Weednanna outline a >500 km long arcuate belt of similar mineralisation and alteration styles.  That such a regional gold system has gone largely unrecognised is due to the presence of extensive cover sediments, a gold-depleted regolith and the lack of an effective exploratory tool, until the widespread use of calcrete geochemistry in the mid-1990s.

Some companies have experienced significant success with Au-in-calcrete sampling while others have been frustrated by the difficulty in discriminating between anomalies closely associated with bedrock mineralisation and spurious anomalies associated with significant thicknesses of transported regolith.  The project addresses the need for additional data on landscape history, metal mobilisation through cover and development of supplementary targeting techniques to plan effective drilling programs, in particular to test calcrete anomalies.

Since mid-2005, the central Gawler Craton has also been targeted by exploration companies for sedimentary uranium with a consequent high demand for project data on the distribution and architecture of palaeodrainage sediments in the area.  An improved map showing palaeochannel sediment distribution on the Gawler Craton is now planned for 06-07 in conjunction with anticipated new data coming from company exploration drilling for uranium.

Zircon dates from the Eucla Margins project indicate that the source of heavy minerals at Jacinth deposit is dominantly from the Musgrave Ranges.  It is proposed that during 2006-08, a GIS of available data including palaeodrainage and sediment cover in the area south of the Musgrave Block to the margin of the Eucla Basin will be compiled.  Heavy mineral suites from Tertiary and Permian sediments will be analysed from selected drill hole samples held in PIRSA’s Core Storage Facility to track heavy mineral dispersion.  These data will aid models of HM distribution in marginal marine sediments of the Eucla Basin.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- GIS including data on

  - regolith thickness

  - regolith type

  - palaeo-drainage

  - geochemistry

- Distribution and description of sedimentary cover in the Central Gawler Craton

- Dating and evolution of the palaeodrainage system

- Dating dune and sand spread cover

- Understanding metal mobilisation through sediment and dune cover

- Prospect scale preliminary models of

  - landscape evolution (includes: regolith stratigraphy dating transported cover and reference site description and maps)

  - weathering of the primary mineral system

  - physical dispersion processes

  - hydro-geochemical dispersion processes

  - role of vegetation in cycling of Au

Outcomes

Anticipated outcomes include uptake of regional data products and use of identified regolith vectors to mineralisation, leading to increased and more efficient mineral exploration in the area with improved exploration success.

Milestones: (dates of significant events marking scientific progress and requests for payments)

| i | Dec 03 | Completion of all current work on the Harris Greenstone Belt on the northern margin of the Central Gawler Gold Province (work completed and final LEME report printed and distributed. All work incorporated in the HGB GIS and data CD issued by PIRSA April 2005). Publication AJES paper on “Evolution of beach placer shorelines and heavy mineral deposition in the eastern Eucla Basin”. |  |
| --- | --- | --- | --- |
| i | Feb 04 | Complete construction of the Central Gawler Gold Province GIS, workshop the production of interim maps (Catalogue of available data compiled as a joint GA, PIRSA, CRCLEME report; initial GIS in completed; workshop of interim maps held 30 March –1 April). |  |
| i | Jun 04 | release GIS and interim maps, report on prospect scale process studies, review and reassess project plan in conjunction with the PIRSA/GA group reviewing the nature and timing of the mineralising systems (commitment from GA and PIRSA to funding Central Gawler projects for a further 2 years release of version 1 GIS and preliminary data issued at Gawler State of Play workshop, Adelaide 4-6 August, 2004). |  |
| i | Oct 04 | Field workshop of LEME participants in Central Gawler Gold projects (combined field trip, PIRSA-AU-CSIRO, held June 04 during excavation of dune at Barns). |  |
| i |  | Release Harris Greenstone GIS on DVD |  |
| i |  | Report by Hou on Kingoonya Palaeochannel |  |
| i | Nov 04 | Announcement by Iluka of discovery of Jacinth HMS deposit, high-grade zircon. Followed in December 04 by discovery of Ambrosia, and in November 2005 by Tripitaka. Over $4 billion in-ground value. |  |
| i | May 05 | Paper by Hou and Warland on “Eucla Basin - world-class palaeo-beach place province” MESA Journal 37. |  |
| i | Jun 05 | Exploration Through Cover Conference, Adelaide University, 24 June. |  |
| i | Aug 05 | LEME report Hydrogeochemistry of the Tunkillia Gold Prospect (Gray and Pirlo). CHIM trials at Challenger Gold Mine. |  |
| i | Nov 05 | LEME Symposium: Papers on plant biogeochemistry of Au at Barns (Lintern) and in the Wudinna area (Mayo and Hill) |  |
| i | Dec 05 | Papers prepared on dating dune cover and significance to landscape evolution and geochemical dispersion (Lintern and Rhodes; Sheard et al.). |  |
| i | Jun 06 | Completion report on regolith mapping and site studies in the Wudinna area. Final copies of regional regolith and geochemical maps output on DVD in GIS. LEME report on Boomerang Au prospect. |  |
| i | July 06 | Papers on CHIM results over Challenger Au Mine, uranium in palaeodrainage sediments and source HMS Eucla Basin presented at AESC, Melbourne. |  |
| i | Aug 06 | Models and methods for HMS accumulation Eucla Basin; CHIM results in China and Australia, IAGOD Conference Moscow. |  |
| i | Sep 06 | Exchange trip to southern China – CHIM development project |  |
| i | Nov 06 | Papers on integrated exploration strategies for gold in the Central Gawler Craton, HMS Eucla Basin, Age of dunes Great Victoria Desert, LEME Symposium Adelaide. Chemical Geology paper on source of pedogenic carbonate in western Gawler Craton. |  |
| i | Dec 06 | Presentation on integrated exploration strategies for mineral exploration in the Central Gawler Craton, SA Explorers Conference, Adelaide. |  |
| i | Mar 07 | Paper in MESA Journal on CHIM results over Challenger Au Mine. |  |
|  | May 07 | Updated 1:2,000,000 map of palaeodrainage and palaeo-coastal sediments in South Australia. |  |
|  | Jun 07 | LEME reports on: Wudinna Regolith Map – exploration implications; Kingoonya Palaeochannel. CHIM field work at Challenger and Tunkillia. |  |
|  | Jul 07 | GIS of palaeodrainage and available data on the area draining south of the Musgrave Ranges to the Eucla Basin. HM analysis of palaeodrainage. |  |
|  | Jul 07 | Chinese CHIM field work and workshops commence | 5 |
|  | Aug 07 | LEME report: Summary of key data for benchmark regolith sites on the Gawler Craton | 3 |
|  | Sept 07 | Exchange trip to China on CHIM development and new mineral exploration technologies. |  |
|  | Nov 07 | Sprigg Symposium, Adelaide – focus on regolith in mineral exploration and the environment. |  |
|  | Apr 08 | Explorers Guide to mineral exploration in the Central Gawler Craton. Synthesis of landscape evolution, cover distribution and metal dispersion. |  |

Detail of planned publications (07-08):

- Hou, B., Frakes, L.A., Sandiford, M., and Worrall, L.  Landscape evolution and significance of Eucla Basin and palaeovalleys, southern Australia: sedimentary, tectonic and economic implications. In Clarke et al., (Eds) Australian Cainozoic Cratonic Basins, special issue, International Association of Sedimentologists.

2. 	Luo, Hou. B., Zhou (to be modified)  Ionic conductivity anomaly in soil cover – exploration of blind mineralisation beneath regolith cover. Geochemistry: Exploration, Environment, Analysis.

3. 	Cooper – The history of sedimentary uranium exploration in South Australia. IMM Transactions.

4. 	Hill, S., et al. Role for biogeochemical methods in mineral exploration in the central Gawler Craton, South Australia. Journal of Geochemical Exploration.

5. 	Hill, S., et al. Biogeochemical and calcrete surveys over the Tunkillia Au Prospect. MESA Journal

6. 	Keeling, J., Sheard, M., Hou, B., Zang, W.  and S. Hill. Explorers Guide to the Gawler Craton. CRC LEME Open File Report.

# Possible papers in addition to above (subject to funding and time commitments):

# Possible papers in addition to above (subject to funding and time commitments):

Confidentiality requirements

None (except where use of company data may have a short time restriction before release)

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs (eg 0.50) for 2007-2008

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| John Keeling | IK |  |  |  |  |  |  | 0.40 | 0.40 |
| Baohong Hou | IK |  |  |  |  |  |  | 0.80 | 0.80 |
| Malcolm Sheard | IK |  |  |  |  |  |  | 0.90 | 0.90 |
| Wenlong Zang | IK |  |  |  |  |  |  | 0.90 | 0.90 |
| George Gouthas | IK |  |  |  |  |  |  | 0.10 | 0.10 |
| Liliana Stoian | IK |  |  |  |  |  |  | 0.20 | 0.20 |
| Barry Cooper | IK |  |  |  |  |  |  | 0.90 | 0.90 |
| Lisa Worrall | IK |  |  |  |  | 0.10 |  |  | 0.10 |
| Steve Hill | IK |  | 0.10 |  |  |  |  |  | 0.10 |
| Total |  |  | 0.10 |  |  | 0.10 |  |  | 4.4 |

All LEME STUDENTS contributing to Projects 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Robert Dart | AU | PhD |
| Jack Lowrey (Non LEME) | AU | Honours |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 8 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 8 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

| Expenditure Item | ANU | AU | CUT | CSIRO EM | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CHIM collaboratoin |  |  |  |  |  |  | 5 | 5 |
| Plan drafting and printing |  |  |  |  |  |  | 3 | 3 |
| TOTAL |  |  |  |  |  |  | 8 | 8 |

Note: Operating funds for PIRSA staff in previous years largely contributed from PIRSA internal budget