Cooperative Research Centre for landscape Environments and Mineral Exploration

PROJECT SUMMARY 07-08

Project No:    1.21   (Issued by LEME Head Office)

Submitted by:  Colin Pain

Date submitted:  21/04/07 		V1

Project name:   Physiographic regions of Australia

Abbreviated title:  Physiographic regions

Type of project Industry  (Centre or Industry/Commercial

Program:    One

Themes:    1. Understanding of regolith processes

2. Models of regolith landscape evolution

Project Leader:   Colin Pain

Start date and duration:  01/07/05 – 30/12/07 (2.5 years)

Participants:   Geoscience Australia, ACLEP

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

In 2005/2006 the Australian Collaborative Land Evaluation Program (ACLEP) provided funding to LEME for the preparation of a national map of physiographic regions.  A first draft was completed by the end of June 2006.  ACLEP was successfully approached for a further $15,000 of funding in order to enhance regolith information. The new objective of the Project is to assess the complexity of each physiographic region in the present coverage and, where necessary, compile new more detailed line work so that each polygon has a similar level of complexity.  Where appropriate we will use data from other LEME projects.

There will also be a report.  The map of physiographic regions of North America (1940) was accompanied by a 520-page book.  The original map of physiographic regions of Australia (1977) appeared in a 15-page chapter in a book on the geography of Australia.  We envisage something in between.

The project contributes to LEME’s strategic intent by providing a basis for the regional description and explanation of the Australian regolith.  It also provides a firm basis on which to extrapolate results obtained from studies of detailed areas to surrounding areas at lower resolution.  In particular the project will work with P4 projects in the Murray-Darling Basin.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

A report describing the Physiographic Regions map – this will be a new report on the landforms of Australia.

Outcomes

- 1. A more comprehensive set of attributes for ASRIS, and therefore better decision making capacity for those who use ASRIS for NRM decisions.

- 2. A better understanding of the landscape context for much of LEME’s work

Milestones: (dates of significant events marking scientific progress)

| f | Sep 06 | Progress report to ACLEP |
| --- | --- | --- |
| f | Dec 06 | Progress report to LEME executive |
|  | Jun 07 | Final line work and attributes for map |
|  | Dec 07 | Draft of report ready for printing |

Detail of planned publication

- 1. Pain, C.F. The Australian Physiographic Regions Map Accompanying Notes.

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs (eg 0.50) for 2007-2008

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colin Pain | IK |  |  |  |  | 0.20 |  |  | 0.20 |
| TOTAL |  |  |  |  |  | 0.20 |  |  | 0.20 |

PROJECT OPERATING COSTS $K  2006-2007

|  | $K | Source external |
| --- | --- | --- |
| CRC Opex funds requested | Nil |  |
| Committed (definite) external funds |  | ACLEP |
| CARRY OVER FROM 06-07 | ~ 8 |  |
| Total Project Opex | ~ 8 |  |

Note: Carryover amount to be confirmed.

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GIS/map preparation |  |  |  |  | 6 |  |  | 6 |
| Travel |  |  |  |  | 2 |  |  | 2 |
| Total |  |  |  |  | 8 |  |  | 8 |

Note: The final budget will be determined once the carryover figure is known at the end of the 06/07 financial year.