Cooperative Research Centre for landscape Environments and Mineral Exploration

PROJECT SUMMARY 07-08

Project No:        (Issued by LEME Head Office)

Submitted by:  Mike Craig

Date submitted:  19/03/07  				V1

Project name:   Queensland Regolith Map

Abbreviated title:  QLD Regolith

Type of project:  Commercial   (Centre or Industry/Commercial)

Program:    One

Themes:

Project Leader:   Mike Craig

Start date and duration: 01/07/06 – 30/06/08 (2 Years)

Participants: GA, Geological Survey of Queensland, Queensland Department of Natural Resources and Water

Brief project description:

- 1. Construct a 1:2 Million scale Regolith Map of Queensland (seamlessly connected to the NT Regolith Map and associated products), and the 1:250 k scale interpretative underpinning product.

- 2. Construct an Atlas of Regolith Materials of Queensland

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- 1. Regolith Map of Queensland - 1:2 Million scale

- 2. Atlas of Regolith Materials of Queensland

- 3. Digital files relating to the Regolith Map of Queensland

- 4. Digital files relating to the Atlas of Regolith Materials of Queensland

- 5. Hardcopies of the 1:2 Million scale Regolith Map and the Atlas

Outcomes:

- 1. First time available state-wide coordinated assessment of regolith materials, regolith distribution and major landform associations.

- 2. First time available Atlas of Regolith Materials of Queensland

- 3. Seamless connection with NT Regolith Project products from Queensland, together forming the basis of a National Regolith Map and Australian Atlas of Regolith Materials as a future GA goal.

Milestones: (dates of significant events marking scientific progress)

|  | Jul 06 – Jun 07 | Compilation of existing data sets, trans-Qld regolith traverse, key areas selected for further work. |
| --- | --- | --- |
|  | Jul 07 – Mar 08 | Field data collection, data analyses completed |
|  | Apr 08 – Jun 08 | Delivery of Regolith Map of Queensland and an Atlas of Regolith Materials of Queensland. Synthesis report, scientific publications in national/ international journals/ conferences. |

Details of planned publications

- 1. Craig, M. et al 1:2 million Regolith Map of Queensland GSQ/GA/CRC LEME

- 2. Thomas, M., et al. Atlas of Regolith Materials of Queensland

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs (eg 0.50) for 2007-2008

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | GSQ | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mike Craig | IK |  |  |  |  | 1.00 |  |  | 1.00 |
| Matilda Thomas | GA |  |  |  |  |  |  |  | 0.50 |
| Mal Jones | GSQ |  |  |  |  |  |  |  | 0.60 |
| TOTAL |  |  |  |  |  | 1.00 |  |  | 2.10 |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested |  |  |
| Committed (definite) external funds | 111 | GSQ contract |
| Total Project Opex | 111 |  |

| Possible additional external funds (for info) | ? | Any 2007 unused |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project lab and deliverables costs |  |  |  |  | 111 |  |  | 111 |
| TOTAL |  |  |  |  | 111 |  |  | 111 |