Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY 07-08

Project No:  		1.33				(Issued by LEME Head Office)

Submitted by:		Lisa Worrall

Date submitted: 	21/04/07			V2 Lisa Worrall 1.6.07

Project name:  	Exploration through Cover in the Tanami

Abbreviated title: 	Tanami

Type of project	Centre/Industry		(Centre or Industry/Commercial):

Program:  		One

Themes:  		1. Understanding of regolith processes

2. Models of regolith landscape evolution

4. Regional mineral exploration studies

5. Making geochemistry more effective

Project Leader:  	Lisa Worrall

Start date and duration:  1/07/05 - 30/06/08 (3 years)

Participants:	ANU, AU, CUT, GA, (NTGS, GSWA, Tanami Gold NL, Newmont Australia, Anglo American)

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The collaborative regolith research project Exploring through the Cover in the Tanami has as its objective the development of a cost-effective means of exploring through cover in the Tanami. The project collaborators are CRC LEME, Geoscience Australia, the Northern Territory Geological Survey, the Geological Survey of Western Australia, Tanami Gold NL, Newmont Australia and Anglo American.

In 2007-2008 work will focus on integrating the results of the multidisciplinary activity in the project to date. A model of regional regolith landscape evolution will be developed, palaeo and contemporary dispersion processes will be identified, and exploration strategies, including recommendations about appropriate sampling media in the Tanami, will be formulated.   An Explorers Guide to the Tanami will be released at AGES in Alice Springs in April 2008.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Reports

-	Fieldwork completion reports

-	Summary of results especially analytical results

- Synthesis report on 4D model of regional regolith landscape evolution including recommendations about appropriate sampling media and pre competitive data acquisition

- Explorers Guide

- Oral and Poster Presentations with published abstracts

- Published Papers

Outcomes

Improved effectiveness of exploration through cover in the Tanami

Milestones: (dates of significant events marking scientific progress and payment)

| i | Mar 05 | Reconnaissance fieldwork at the Coyote Prospect |  |
| --- | --- | --- | --- |
| i | Mar 05 | Fieldwork Program Completion Report |  |
| i | Oct 05 | Review Meeting (Ivy Camp, Granites) |  |
| i | Oct 05 | Reconnaissance fieldwork at the Titania Prospect |  |
| i | Oct 05 | Fieldwork Program Completion Report |  |
| i | Jan/Feb 06 | Follow-up Fieldwork at the Coyote Prospect |  |
| i | Mar 06 | Review Meeting (ARRC, Perth) |  |
| i | Mar 06 | Fieldwork Program Completion Report |  |
| i | Jun 06 | Reports on Analytical Results |  |
| i | Aug 06 | Additional fieldwork testing the predictive capability of hypotheses developed at the Review Meetings |  |
| i | Sep 06 | Fieldwork Program Completion Report |  |
| i | Nov 06 | Review Meeting (Hahndorf, SA) |  |
|  | Feb 07 | Reports on Analytical Results |  |
| i | Mar 07 | Review Meeting (AGES, Alice Springs) |  |
| i | Mar 07 | AGES Presentation |  |
|  | June 07 | IAGS Presentations |  |
|  | Jul/Aug 07 | Additional fieldwork at Callie | 18 |
|  | Aug 07 | Submission of all analyses | 2 |
|  | Sept 07 | Submission of papers to IAGS special issue of GEEA |  |
|  | Nov 07 | ASEG Presentation |  |
|  | Feb 08 | Complete draft of Explorers Guide |  |
|  | Apr 08 | AGES Presentation |  |
|  | Apr 08 | Release of Explorers Guide at AGES, Alice Springs |  |

Details of planned publications

- Kirste, D., Worrall, L., Joseph, J. and N. Reid. A hydrologic and hydrogeochemical study of the regolith signature of gold mineralization in the Tanami Desert Region of Australia. Geochemistry: Exploration, Environment, Analysis IAGS Special Issue

- Kirste, D., Worrall, L., Reid, N. and Hill S. Hydrogeochemical and biogeochemical anomalies related to mineralisation under regolith cover, Tanami region, Australia. Geochemistry: Exploration, Environment, Analysis

- Petts, A.E. and S.M. Hill. Understanding the Spatial Distribution of Termite Mounds in the Regolith: Implications for Landscape Evolution and Mineral Exploration. Journal of Applied Ecology.

- Petts, A., Hill, S. and Worrall, L. Termitaria as a biogeochemical sampling medium for mineral exploration: the significance of species variations towards a representative and robust approach Geochemistry: Exploration, Environment, Analysis IAGS Special Issue

- Pillans, B. 300 million years of weathering in the Tanami Desert, northern Australia. Science.

- Reid, N, Hill, S., and Lewis, D.M. Spinifex Grasses used to detect Buried Gold Mineralisation  in Semi-arid Northern Australia. Australian Journal of Earth Sciences.

- Reid, N, Hill, S., and Lewis, D.M. Snappy Gum (Eucalyptus brevifolia) Biogeochemistry of the Coyote Au-Deposit, Tanami, WA. Geochemistry: Exploration, Environment, Analysis.

- Reid, N., Hill, S. and Lewis, D. Mineral Expression and Plant Species Differences at the Titania Prospect: Biogeochemical Sampling in the Tanami region, Northern Territory, Australia Geochemistry: Exploration, Environment, Analysis IAGS Special Issue

- Reid, N, Hill S. and Lewis D. Phytoexploration signals: Does one sample represent an area, case study using Melaleuca lasiandra. Geochemistry: Exploration, Environment, Analysis IAGS Special Issue

- Worrall, L., Green, M., Kirste, D., and Pillans, B. Au anomalies at surface in the Tanami Desert Region of NW Australia show a strong spatial association with the maximum extent of the late Cretaceous transgression. Geology.

- Worrall, L., Kirste, D.,Joseph, J., Pillans, B., Reid, N.,Petts, A. and Hill, S. Targeting  gold mineralisation through the cover in the Tanami Desert Region in Northern Australia. Geochemistry: Exploration, Environment, Analysis. IAGS Special Issue

- Worrall, L., Kirste, D.,Joseph, J., Pillans, B., Reid, N.,Petts, A. and Hill, S. Explorers Guide to the Tanami. CRC LEME Open File Report.

Confidentiality requirements

A Memorandum of Understanding describes the nature of the collaboration between project partners on this project.  Some datasets will remain confidential to their owners.  All proposed publications and public presentations are to be reviewed prior to publication/presentation by the project partners.

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs (eg 0.50) for 2007-2008 * Until 30/12/07

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lisa Worrall | IK |  |  |  |  | 0.30 |  |  | 0.30 |
| Steve Hill | IK |  | 0.30 |  |  |  |  |  | 0.30 |
| John Joseph |  |  | 0.50* |  |  |  |  |  | 0.25 |
| Brad Pillans |  | 0.10 |  |  |  |  |  |  | 0.10 |
| Matt Lenahan | CRC | 0.20* |  |  |  |  |  |  | 0.10 |
| Tony Eggleton | HON |  |  |  |  |  |  |  |  |
| Dirk Kirste | SFU |  |  |  |  |  |  |  |  |
| Total |  | 0.20 | 0.55 |  |  | 0.30 |  |  | 1.05 |

All LEME STUDENTS contributing to Projects 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Anna Petts | AU | PhD |
| Nathan Reid (Non LEME) | AU | PhD |

PROJECT OPERATING COSTS $K 2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested |  |  |
| Committed (definite) external funds | 20 |  |
| Committed In Kind | 110* | Industry |
| Total Project Opex (LEME only) |  |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

* TGNL and Newmont Australia are providing in kind support; especially with, travel, food, accommodation, vehicles, fuel, field assistance and analytical costs.  The total value of such support is in excess of $60k/a.  GA are also providing XRF, ICP-MS and XRD analyses as in kind support.  The value of this support is in excess of $50k/a.

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

| Expenditure Item | ANU | AU | CUT | CSIRO EM | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel |  |  |  |  | 8 |  |  | 8 |
| Vehicle hire and expenses |  |  |  |  |  |  |  |  |
| Incidentals |  |  |  |  | 2 |  |  | 2 |
| Geophysical equipment hire |  |  |  |  | 6 |  |  | 6 |
| Freight |  |  |  |  | 2 |  |  | 2 |
| Assays |  |  |  |  | 2 |  |  | 2 |
| Thin sections |  |  |  |  |  |  |  |  |
| Drafting and report production |  |  |  |  |  |  |  |  |
| Total |  |  |  |  | 20 |  |  | 20 |