Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY 07-08

Project No:  		1.34				(Issued by LEME Head Office)

Submitted by:		John Greenfield

Date submitted: 	03/04/07		V2 Lisa Worrall 1.6.07

Project name:  	Exploration through cover in the Thomson Orogen

Abbreviated title: 	NSW Thomson Orogen Project

Type of project	Centre/Industry	(Centre or Industry/Commercial):

Program:  		One

Themes:  		1. Understanding regolith processes

2. Models of regolith landscape evolution

4. Regional mineral exploration studies

5. Making geochemistry more effective

Project Leader:  	John Greenfield

Start date and duration:  01/07/05 - 30/06/08 (3 years)

Participants:	 	GA, NSW DPI, ANU, AU

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The Thomson Orogen, which underlies the Channel Country in northwest New South Wales, is one of the last major greenfield terrains in NSW.  The NSW DPI has made this terrain the focus of a new Exploration Initiative.  The Thomson Orogen has potential for arc and ocean-crust related gold and base metal deposits while the area to the south of the Orogen may have potential for Mississippi Valley style zinc deposits.  The prospective units are obscured by Eromanga Basin sediments.  The basin cover presents a significant impediment to exploration.

The primary objective of this project is to lower mineral exploration risk by developing an effective means of exploring through the cover in the Thomson Orogen.  The achievement of this objective will be measured by the increase in exploration investment in the area.

The strategy to achieve these objectives builds on the results of Tibooburra, Curnamona and Cobar-Giralambone Projects (these areas are also under Eromanga Basin cover and Tibooburra is on the western margin of the Thomson Orogen) and has eight elements:

1	Mapping the character and disposition of regolith materials in 3D

2	Developing an understanding of landscape history for the late Mesozoic – Cenozoic, including post-Mesozoic tectonics.

3	Characterising contemporary dispersion processes (physical and chemical; including biogeochemical and electro-chemical processes)

4	Identifying palaeo-dispersion processes

5	Developing an exploration strategy

6	Developing and implementing an effective knowledge transfer and training

7	Tracking results and revising strategies based on experience

This project has close interaction with the generic process projects in Programs 1, 2 and 3, especially Lachlan Fold Belt, Metal Mobility and Geochemical Baselines Projects.

2007-2008 Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Digital Database and GIS

- 4 x 1:100k Regolith Maps

- LEME Reports

- Explorers Guide to the Thomson Orogen

- Publications in national and international journals

- Presentations at national and international conferences

- University theses

Outcomes

- Development of an accurate landscape evolution model and application to mineral exploration beneath cover in the NSW Thomson Orogen

- Increase in exploration investment in the NSW Thomson Orogen

Milestones: (dates of significant events marking scientific progress and payment)

| i | July 06 | Pay for 176 biogeochem Au analyses from March 06 baseline trip (GA) |  |
| --- | --- | --- | --- |
| i | Jul 06 | Tibooburra Fieldwork: Hons and PhD fieldwork, DGPS surveys (Adelaide Uni) |  |
| i | Aug 06 | Preliminary biogeochem report (Hulme, includes contract salary) |  |
| i | Aug 06 | Geophysical Interpretation of Thomson (NSWDPI) |  |
| i | Aug 06 | Submit Warratta Inlier biogeochemistry assays (Adelaide Uni) |  |
| i | Sept 06 | Prelim baseline Geochem Report (de Caritat, Lech, Hulme) |  |
| i | Sept 06 | Finalize Warratta Inlier Regolith Landform map (Adelaide Uni) |  |
| i | Sept 06 | Planning-progress meeting in Canberra |  |
| i | Sept 06 | Submit New Bendigo soil and regolith samples for geochemistry assay (AU) |  |
| i | Sept 06 | BHEI Conference (S. Hill) |  |
| i | Oct 06 | Baseline geochem/biogeochem sampling trip (GA, AU) |  |
| i | Oct 06 | Baseline biogeochem sample preparation |  |
| i | Oct 06 | Baseline geochem sample preparation |  |
| i | Nov 06 | Completion of McAvaney & Tucker Hons |  |
| i | Nov 06 | Regolith Symposium 2006, Hahndorf |  |
| i | Dec 06 | Baseline geochem sample submission |  |
| i | Mar 06 | Tibooburra fieldwork (Adelaide Uni) |  |
|  | Jun 06 | Public release of four 100k Regolith sheets |  |
| i | Jun 06 | Geochronology analysis and results (ANU) |  |
|  | Aug 07 | Draft version of the Explorers Guide to the Thomson Orogen complete (Hill, AU) |  |
|  | Sept 07 | 250k scale regolith maps across Thomson (NSWDPI- cartography contractors) |  |
|  | Sept 07 | Gold nugget and lag report (McQueen, ANU) | 0.5 |
|  | Sept 07 | Clay Mineralogy report (Greene, ANU) | 0.5 |
|  | Nov 07 | Planning Meeting in Canberra | 4 |
|  | Dec 07 | Final baseline report submitted (GA-NSWDPI) | 1 |
|  | May 08 | Rollout of project results including release of the Explorers Guide ?Mines and Wines | 2 |
|  | Jun 08 | Release of Thomson GIS DVD (NSWDPI) |  |

Details of planned publications

- Caritat, P. de, and Lech, M. Final report on the regional baseline geochemical survey across the NSW Thomson Orogen. CRC LEME open file report.

- Colquhoun, G. (Compiler), (in prep). Thomson Orogen Geoscience Database. DVD. Geological Survey of NSW, Maitland.

- Davey, J.E. & Hill, S.M. Regolith Geology and long-term landscape evolution of an intra-cratonic basin margin:  the Mt Browne and Mt Poole Inliers, north-western New South Wales.  Australian Journal of Earth Sciences.

- Greene, R. Final report on the Aeolian contribution to overbank samples from the NSW Thomson Orogen. CRC LEME open file report

- Hill, S.M., Chamberlain, T. & Hill, L.J. Regolith and Landscape Evolution of the Tibooburra Inlier, northwestern NSW:  framework for mineral exploration under cover on intra-continental basin margins.  Australian Journal of Earth Sciences.

- Hill, S.M. et al. Explorers Guide to the Western Thomson Orogen. CRC LEME open file report

- Hulme, K. and Hill, S.M. Time and Space constraints on riparian biogeochemical expressions of mineralisation under cover:  River red gum biogeochemistry along the southern margins of the Tibooburra Inlier, WNSW. Australian Journal of Earth Sciences..

- Hulme, K. Final report on the regional baseline biogeochemical survey across the NSW Thomson Orogen. CRC LEME open file report

- Greenfield, J., Reid, W., Gilmore, P., Caritat P. de., Lech, M., Hill, S., Hulme, K.,Watkins, J., and Worrall, L. The NSW Thomson Orogen Project- an overview. In Colquhoun (comp).

- McQueen, K. Final report on lag sampling and the origin of gold nuggets in the NSW Thomson Orogen. CRC LEME open file report.

- McAvaney, D., Hill, S.M. & Collins, A. Neotectonic evolution of the southern Warratta Inliers and its significance on Au dispersion and residence.  Journal TBA.

- Reid, W.J. Milparinka 1:100 000 Regolith Geology sheet 7238. 1st edition. Geological Survey of NSW, Sydney.

- Reid, W.J. Tibooburra 1:100 000 Regolith Geology sheet 7339. 1st edition. Geological Survey of NSW, Sydney.

- Reid, W.J. Olive Downs 1:100 000 Regolith Geology sheet 7239. 1st edition. Geological Survey of NSW, Sydney.

- Reid, W.J. Yantara 1:100 000 Regolith Geology sheet 7338. 1st edition. Geological Survey of NSW, Sydney.

- Reid, W.J. Thomson Orogen 1:250 000 Regolith Geology. 1st edition. Geological Survey of NSW, Maitland

- Tucker, L & Hill, S.M. Plant biogeochemistry of buried Au mineralisation at the New Bendigo Inlier, WNSW.  Geochemistry: Exploration, Environment, Analysis..

Confidentiality requirements

None at this stage

Date submitted to Executive:

Date approved by CEO/Exec:

Date approved by Board

RESOURCES 2007-2008

STAFFING-FTEs (eg 0.50) for 2007-2008 *up to 31/12/07

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| John Greenfield | IK |  |  |  |  |  | 0.30 |  | 0.30 |
| Lisa Worrall | IK |  |  |  |  | 0.10 |  |  | 0.10 |
| Ken McQueen | CRC | 0.40* |  |  |  |  |  |  | 0.20 |
| Steve Hill | IK |  | 0.10 |  |  |  |  |  | 0.10 |
| Patrice de Caritat | CRC |  |  |  |  | 0.10* |  |  | 0.05 |
| Megan Lech | IK |  |  |  |  | 0.30* |  |  | 0.15 |
| Bob Brown | IK |  |  |  |  |  | 0.25 |  | 0.25 |
| Nancy Vickery | IK |  |  |  |  |  | 0.25 |  | 0.25 |
| John Watkins | IK |  |  |  |  |  | 0.10 |  | 0.10 |
| Ken McDonald | IK |  |  |  |  |  | 0.30 |  | 0.30 |
| Bob Musgrave | IK |  |  |  |  |  | 0.20 |  | 0.20 |
| Steve Dicks | IK |  |  |  |  |  | 0.20 |  | 0.20 |
| Richard Greene | IK | 0.30 |  |  |  |  |  |  | 0.30 |
| Bill Reid | IK |  |  |  |  |  | 0.95 |  | 0.95 |
| Kingsley Mills | IK |  |  |  |  |  | 0.20 |  | 0.20 |
| Dick Glen | IK |  |  |  |  |  | 0.20 |  | 0.20 |
| Steve Trigg | IK |  |  |  |  |  | 0.20 |  | 0.20 |
| Gary Burton | IK |  |  |  |  |  | 0.20 |  | 0.20 |
| Phil Gilmore | IK |  |  |  |  |  | 0.25 |  | 0.25 |
| Karen Hulme | IND |  |  |  |  |  |  |  |  |
| Total |  | 0.50 | 0.10 |  |  | 0.30 | 3.60 |  | 4.50 |

All LEME STUDENTS contributing to Projects 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Robert Dart | AU | PhD |
| Jesse Davey | AU | PhD |

PROJECT OPERATING COSTS ($K) 2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 8 |  |
| Committed (definite) external funds |  |  |
| Committed In Kind | 575* | GA, NSWDPI |
| Total Project Opex | 8 |  |

* NSW DPI is providing $575k as operating to DPI staff.

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

| Expenditure Item | ANU | AU | GA | NSW DPI | Total |
| --- | --- | --- | --- | --- | --- |
| Travel |  | 4 |  |  | 4 |
| Map and Report production | 1 | 2 | 1 |  | 4 |
| Total | 1 | 6 | 1 |  | 8 |