Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  						(Issued by LEME Head Office)

Submitted by:	David J Gray

Date submitted: 23rd April 2007	V6  24.01.08 GK (as directed by David Gray and Steve Rogers)

Project name:  Hydrogeochemistry for Mineral Exploration

Abbreviated title: Hydrominex

Type of project: Industry/Commercial

Program:  2

Themes:

Project Leader:  David J Gray

Start date and duration:  Ongoing until 30th June 2008

Participants: David J Gray, Ryan Noble, Bear McPhail, Patrice de Caritat

Brief project description:

The objective of this project is to further develop hydrogeochemistry as a tool for mineral exploration under cover (areas and commodities).  In the main this will be through targeted Industry-funded projects so as to develop robust exploration methods for specific commodities in particular environments.  Particular technologies developed within this project include use of isotope technology, enhanced chemical modelling, sampling development and Industry partnership.

One “Legacy” product from this project will be a “Practical guide for hydrogeochemistry for mineral exploration” report.  This will be important to transfer the results for the previous 6 years to a general exploration audience, including the practical methodology and examples of successful application of hydrogeochemistry.  This should be a “How To” for explorers.

A additional “Legacy” product is dealing with the significant challenge of integrated analysis and interpretation of complex groundwater data. We will use a geo-statistical approach based on self-organising maps (SOM). A SOM analysis can highlight subtle relationships and assist in the process of knowledge creation from complex and disparate data. This exploratory data analysis tool is unsupervised and data-driven, the resulting patterns, boundaries and relationships are internally-derived, as opposed to concept driven analysis as performed by the geochemist. SOM can be used to assess the spatial coherence or context of samples belonging to a particular grouping. Subtle trends and relationships such as identifying and separating overlapping geological processes, related to mineralization and subsequent weathering may also be identifiable by this method.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs:

- Open File report on “Practical guide for hydrogeochemistry for mineral exploration”

- Critical input into understanding of groundwater geographical variation and impact on exploration strategies (using CSOM and other geostatistical studies), which will also form a component into a P3 project into 4D modelling of Yilgarn groundwaters

- Release final restricted report for Anglo-American on hydrogeochemistry at Calama

- Release final restricted report for Anglo-American on hydrogeochemistry at Kayar

- Release final restricted report for Anglo-American on hydrogeochemistry at Hinta

- Finish and submit a manuscript on hydrogeochemistry at Cannington

- Prepare report about groundwater at Cobar.

- Release of results for Gold exploration from AMF project at Esperance / Salmon Gums

- Release of results for NiS exploration from Echo Project in Yandal Belt

Outcomes:

1.	Broaden spectrum of commodities for which hydrogeochemical exploration has been trialled

2.	Apply hydrogeochemical exploration expertise to new areas in different geology, regolith and landscape settings

3.	Apply geochemical and hydrogeological modelling to gain better understanding of processes affecting dispersion, footprint size, and the development of geochemical and isotopic vectors

Milestones: (dates of significant events marking scientific progress)

SOM Analysis 1 (Northern Yilgarn Groundwaters) completion – Release of $3K

SOM Analysis 2 (Southern Yilgarn Groundwaters) completion – Release of $3K

Report releases from ANU/GA – Release of $1K

Invoicing of miscellaneous costs – Release of $0.5K

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| McPhail |  | 0.2 |  |  |  |  |  |  |  |  |
| De Caritat |  |  |  |  |  |  | .075 |  |  |  |
| Gray |  |  |  |  | 0.35 |  |  |  |  |  |
| Noble |  |  |  |  | 0.35 |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 13 |  |
| Refund from ANU | (12.4) |  |
| Carry Over of external funds from 06/07 | 7.687 |  |
| Total Project Opex | 2.787 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ANU/GA Reports | (12.4K) |  |  | 5..5K |  |  |  |  |  |
| CSOM analysis of database | 1K |  |  | 6..5K |  |  |  |  |  |
| Carry Over of External funds |  |  |  |  |  | 7.687K |  |  |  |
| TOTAL | (11.4K) |  |  | 12K |  | 7.687K |  |  | 8.287K |

Cooperative Research Centre for Landscape Environments and Mineral Exploration

REVISED PROJECT SUMMARY				HO-170105

Project No:  						(Issued by LEME Head Office)

Submitted by:	David J Gray

Date submitted: 3rd September 2007			V2 - Updated RRA 22.10.07

V3 - Updated SR

Project name:  Hydrogeochemical Mapping of the Northeast Yilgarn Craton

Abbreviated title: Hydrogeochemical Mapping

Type of project: Industry/Commercial

Program:  2

Themes:

Project Leader:  David J Gray

Start date and duration:  Ongoing until 30th June 2008

Participants: David J Gray, Ryan Noble

Brief project description:

The objective of this project is to further develop hydrogeochemistry as a tool for mineral exploration under cover (areas and commodities).  In the main this will be through targeted Industry-funded projects so as to develop robust exploration methods for specific commodities in particular environments.  Particular technologies developed within this project include use of isotope technology, enhanced chemical modelling, sampling development and Industry partnership.

One “Legacy” product from this project will be a “Practical guide for hydrogeochemistry for mineral exploration” report.  This will be important to transfer the results for the previous 6 years to a general exploration audience, including the practical methodology and examples of successful application of hydrogeochemistry.  This should be a “How To” for explorers.  Allied to this will be an extensive, industry and other agency funded project, on the utility of groundwater for large scale geochemical mapping, based in the NE Yilgarn Craton.  To data we have organised more than $140K external funding plus additional in-kind analytical support.

Note that this is a revision of the previous hydrogeochemistry proposal, so is a change from a $9K to a $14.5 request, not for additional funds.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs:

- Sampling for “Hydrogeochemistry of the Northeastern Yilgarn Craton”

- Open File report on “Practical guide for hydrogeochemistry for mineral exploration”

- Critical input into understanding of groundwater geographical variation and impact on exploration strategies, which will also form a component into a P3 project into 4D modelling of Yilgarn groundwaters

- Release of results for Gold exploration from AMF project at Esperance / Salmon Gums

- Release of results for NiS exploration from Echo Project in Yandal Belt

-Final Report: September 2008 (presentation to be made in June 2008).

Outcomes:

1.	Broaden spectrum of commodities for which hydrogeochemical exploration has been trialled

2.	Apply hydrogeochemical exploration expertise to new areas in different geology, regolith and landscape settings

3.	Apply geochemical and hydrogeological modelling to gain better understanding of processes affecting dispersion, footprint size, and the development of geochemical and isotopic vectors

Milestones: (dates of significant events marking scientific progress)

Dec 07 - Sampling Leinster area – Release of $3.00

April - 08 Sampling Yeelirrie area – Release of $2.50K

May 08 - Report releases

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| McPhail |  | 0.2 |  |  |  |  |  |  |  |  |
| De Caritat |  |  |  |  |  |  | .075 |  |  |  |
| Gray |  |  |  |  | 0.35 |  |  |  |  |  |
| Noble |  |  |  |  | 0.35 |  |  |  |  |  |
| Hydrogeochemist |  |  |  |  | 0.65 |  |  |  |  |  |
| TOTAL |  |  |  |  | 1.35 |  |  |  |  |  |