# Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  						(Issued by LEME Head Office)

Submitted by:	 Tim Munday

Date submitted:  23rd April 2007			V2 31.5.07 RRA

# Project name:  Objective Logging of Regolith Materials

# Abbreviated title: 	Objective Logging

Type of project  Centre				(Centre or Industry/Commercial):

Program:  	P2

# Themes:

# Project Leader:  Tim Munday

# Start date and duration:

Participants:	 CSIRO, GA, PIRSA, Industry

Brief project description:

The project aims to develop practical automatic interpretation tools for logging regolith materials returned as core, drill chips, or pulps. It also aims to better define the regolith mapping and predictive modelling capabilities of spectral data acquired from imaging spectrometers such as HyMap.  The intent is to provide the exploration geologist, mining engineer, geomorphologist or environmental scientist with meaningful, objective information of regolith materials to aid geological, geophysical, geotechnical and geochemical interpretation.  The goal is not to replace the experienced geological interpretation of materials in their spatial and temporal context, but to complement and refine this knowledge through the rapid analysis and presentation of mineralogical (spectral), geochemical (hand held XRF).  The project technology will aid the definition of 3D and 4D models of regolith and landscape with exploration and environmental applications.

In this, the final year of this project, particular emphasis will be placed on the documentation of spectral logging procedures and protocols relevant to regolith materials/settings, and the implementation of regolith logging methods/algorithms into an operational software framework, specifically TSG Core (An analytical framework for processing and analysing spectra developed by CSIRO). The project will also further explore the application of the HyChips technology in the exploration workflow. Finally we propose to develop and conduct a training workshop with AUSSpec for the  mining and exploration industry and their service providers, to promote understanding and awareness of the developed  technologies.

Specific Objectives for 2007-8 include:

- Conduct of workshop on Spectral indices for use in regolith settings (Nov07) .

- Production of a workshop report on procedures and protocols for using spectra in the exploration workflow, with particular emphasis on regolith materials

- Complete the development of regolith unmixing alogorithms and the implementation of this code in TSG.

# Deliverables (outputs) and expected impacts of research (outcomes):

# Outputs

- Software implementation of algorithms for the rapid, objective interpretation of multi-parameter logs and presentation of interpreted results, including new spectral matching techniques specific to regolith materials. Specifically this will entail an implementation on TSG on automated unmixing algorithms and will involve:

- Incorporation of low frequency” spectral feature matching appropriate to unmixing algorithms

- Implementation of data compression techniques for processing and analysis

- Incorporation of regolith interpretation algorithms in TSG and commercial deployment.

- Technology transfer workshop with industry (including analytical labs) – to raise awareness and broaden industry acceptance and adoption of techniques developed.

- Report on a workshop to define regolith “Spectral indices” which can be incorporated into commercial software (TSG). Development of strategy for the commercial application and communication of this IP collaborative with CEM and other LEME partners eg PIRSA and GA.

Outcomes

- Routine acquisition of mineralogical (spectral) data with geochemical data in exploration through the regolith, resulting in more effective exploration, targeting and priority setting.

- Better value from drillhole data, through the provision of regolith material and mineralogical information.

- Take up of auto-interpretation procedures by the exploration sector (through analytical labs?) to aid geological and geochemical interpretation in regolith settings

- More efficient and effective exploration in areas of cover, through ready identification of significant regolith boundaries, and better discrimination of bedrock/alteration variations in the regolith.

# Milestones: (dates of significant events marking scientific progress)

- Nov 2007: Workshop with industry on spectral interpretation of Regolith Materials

- June 2008 Implementation of new algorithms (Regolith Templates) for the spectral interpretation and objective logging/analyses of regolith materials using TSG software.

- June 2008: Report summarising case studies concerning the application of spectral logging in exploration through cover.

Research progress will be formally reported through Quarterly reports and a final project report. Reports will be prepared in digital format for ready dissemination by electronic means.

# Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

# RESOURCES 2007-2008

# STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tim Munday | IK |  |  |  | 0.35 |  |  |  |  | 0.3 |
| Cajetan Phang | CRCLEME |  |  |  | 0.60 |  |  |  |  | 0.65 |
| TOTAL |  |  |  |  |  |  |  |  |  | 0.95 |

# PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 5 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 25 |  |

| Possible additional external funds (for info) | 20 | Hire of CRCLEME HyChips Logger to Industry Industry |
| --- | --- | --- |

# DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

# Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Unmixing algorithm development (Consulting) |  |  |  | $10K |  |  |  |  | 10 |
| Workshop on spectral indices, sampling protocols |  |  |  | $5K |  |  |  |  | 5 |
| Software coding of regolith unmixing algorithms/library in TSG |  |  |  | $10K |  |  |  |  | 10 |
| Total |  |  |  |  |  |  |  |  | 25 |