Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  						(Issued by LEME Head Office)

Submitted by:		Dr Ravi Anand

Date submitted: 	April 2006			V2 31.5.07 RRA

Project name:  	Predictive Geochemistry in Areas of Transported Overburden: Mechanisms of Anomaly Formation (AMIRA P778 Project)

Abbreviated title: 	Predictive Geochem AMIRA P778

Type of project	Commercial

Program:  		2

Themes:  		Mechanisms of anomaly formation

Project Leader:  	Dr Ravi Anand

Start date and duration:  May 2006-May 2009 (CRC LEME participation expires 30 June 2008)

Participants:	 	CSIRO Exploration & Mining, CSIRO Land & Water, Adelaide University, Curtin University, and AMIRA

Brief project description:

As the discovery rate of world-class mineral deposits continues to decline in Australia and other parts of the world, increased attention is being focused on geochemical exploration methods designed for covered terrains.  If definitive, low cost surface or near-surface sampling surveys can be conducted in areas of shallow cover (say <30m), large areas can be tested and expensive unnecessary drilling can be reduced.  In order to apply geochemical exploration methods confidently in a given area, or to be able to determine that such techniques are inappropriate, it is necessary that we understand the mechanisms by which surface expressions may form.  Explorers will then be better able to decide whether to do further drilling given a specific response at the surface.  Research is required that will determine which mechanisms can cause metal migration through post-mineralization cover.

As mineral exploration moves into regions dominated by shallow transported cover, conventional approaches are simply not applicable and thus increasingly there is a need for new innovative approaches to geochemical exploration.  However to develop such new approaches there is a major need to identify the operating mechanisms capable of transferring metals from buried mineralization upwards through barren cover to the surface.

Understanding the processes of metal transport through transported overburden requires expertise and experimental techniques from a wide range of disciplines.  In the proposed project the researchers will be using a combination of field and analytical techniques derived from soil science, botany, molecular microbiology, geochemistry, plant chemistry, hydrogeochemistry and regolith geology.

The main objective of the proposed project is to determine the mechanism(s) for formation of geochemical anomalies in transported overburden in a variety of Australian environments and, based on these mechanisms, to develop effective and reliable geochemical exploration techniques.  The research focus will be on:

- Studies to develop practical sampling strategies and methodologies in areas of transported cover based on biota, soil and gas investigations.

- Experimental and theoretical work on the mechanisms leading to the formation of surface anomalies.  This will provide the framework and constraints for the practical sampling methods.

The researchers will apply a range of techniques such as vegetation analysis of various plant species, metal uptake in the rhizosphere (plant-root zone), mass balance studies, in-house lab and greenhouse studies; groundwater geochemistry and redox analysis, microbial characterization including their role in gas generation and mineral-trace element biotransformation (solubilisation/precipitation) throughout the profile, isotope analysis to establishing source of metal in plants and soil, using artificial inserted adsorbent collectors to  detect surface geochemical anomalies and utilising other research on soil desorption analysis to test gas migration possibilities.  The researchers will use a combination of in situ and in vivo spectroscopic techniques such as synchrotron-based techniques, nanosims, electron microprobe and laser ablation ICP-MS to determine the nano-scale location of metals in vegetation and regolith materials.

Sponsors of the project: BHP Billiton, Cameco Corporation, Teck Cominco, Independence Gold, SGS Minerals, Barrick Gold, Inco, Newmont, Codelco, Rio Tinto, CVRD, Jabiru Metals, JOGSEG.

Deliverables (outputs) and expected impacts of research (outcomes):

Scientific Deliverables (new scientific advances)

(i) Improved scientific understanding of the mechanisms that are responsible for metal migration through transported cover;

(ii) Guidelines for assessment of which transported regolith environments metal dispersion is possible in and what sample media/techniques are most likely to detect it.

(iii) New cost-effective and practical exploration method(s), with higher reliability and probability of success; (distinction between negative and null result)

(iv) Potential to use new exploration methods in other parts of the world.

Deliverables to Client (Adoption mechanisms)

i. Technical reports describing the work completed at each study site;

ii. Technical report summarizing experimental and theoretical work on sampling strategies, sample preparation and sample analysis;

iii. Final report on mechanistic models to account for observed metal migration or its absence, integrating all aspects of the study including different regolith and palaeo-climatic controls on migration, and variations with respect to different commodity elements.

iv. National and international publications in peer reviewed journals.

Milestones: (dates of significant events marking scientific progress)

July 2007: Progress report on Miitel North Ni prjpect

July 2007: Progress report on microbial processes at Jaguar

August/September 2007: Progress report on Jaguar deposit

October  2007: Interim report on practical sampling strategies

February 2008: Progress report on Moolart Well deposit

April 2008: Progress report on Barns gold prospect

In addition,

(a)Quarterly reports to sponsors of the project.

(b) Six monthly meetings with sponsors where scientific results are presented

© Field trip/workshop for sponsors: this involves visiting study sites and discussion on sampling and analytical protocols: November, 2007

Confidentiality requirements

The outcomes will be confidential to sponsors during and up to one year after completion of the three year project, after which researchers have the right to publish.

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | Uni Chile | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ravi Anand | In Kind |  |  |  | 0.50 |  |  |  |  | 0.5 |
| Rob Hough | In Kind |  |  |  | 0.30 |  |  |  |  | 0.30 |
| Ryan Noble | CRC |  |  |  | 0.40 |  |  |  |  | 0.40 |
| Cajetan Phang | CRC |  |  |  | 0.15 |  |  |  |  | 0.15 |
| Mel Lintern | CRC |  |  |  | 0.75 |  |  |  |  | 0.75 |
| Steve Wakelin | Industry |  |  |  |  | 0.50 |  |  |  | 0.50 |
| Steve Rogers | CRC |  |  |  | 0.05 |  |  |  |  | 0.05 |
| Craig MacFarlane | CRC |  |  |  | 0.50 |  |  |  |  | 0.50 |
| Steve Hill | CRC |  | 0.15 |  |  |  |  |  |  | 0.15 |
| Mehrooz Aspandiar | CRC |  |  | 0.30 |  |  |  |  |  | 0.30 |
| David Gray | CRC |  |  |  | 0.15 |  |  |  |  | 0.15 |
| Brian Townley | University of Chile | 0.70 |  |  |  |  |  |  |  | 0.70 |
| TOTAL |  | 0.70 | 0.15 | 0.30 | 2.80 | 0.50 |  |  |  | 4.45 |

PROJECT OPERATING COSTS $K 2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | $135K |  |
| Total Project Opex | $135K |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vegetation, soil, regolith analyses, SEM, probe, , column and field experiments, isotopes, vegetation productivity measurements, field trips etc |  |  |  | 123,000 |  |  |  |  |  |
| Vegetation analyses, field trip |  | 5,000 |  |  |  |  |  |  |  |
|  |  |  | 7,000 |  |  |  |  |  |  |
| Soil, regolith, vegetation analyses, field trip |  |  |  |  |  |  |  |  |  |
| Geomicrobiological investigations, field trips |  |  |  |  |  |  |  |  |  |
| TOTAL |  | 5,000 | 7,000 | 123,000 |  |  |  |  | 135K |