Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		3.26				(Issued by LEME Head Office)

Submitted by:		Paul Shand

Date submitted: 	20/4/07			V1

Project name:  	Engineering Evaluation Initiative Phase II-Wheat belt Geochemistry Risk Assessment

Abbreviated title: 	AG2 - Acid Drainage

Type of project	Centre-Industry (WA EEI, CALM, Avon Catchment Council) co-investment)				(Centre or Industry/Commercial):

Program:  		3

Themes:  		Acid Sulfate Soils

Project Leader:  	Brad Degens(DoW)/Paul Shand

Start date and duration:  01.01.06-30.12.08

Participants:	 CRC LEME, CSIRO L&W, Agriculture WA, DoE WA, CALM, WA EEI, Avon CC, Yarra Yarra CC, WA  Channel Management Group

Brief project description:

Drainage geochemical risk assessments will be expanded beyond their current focus in the Avon Catchment. Geochemical evaluation of risks will be assessed in regional drainage of saline areas in three WA basins. The Engineering Evaluation Initiative is a program founded, supported and largely funded by WA government agencies (principally WA Ag Dep,  CALM) and relevant Catchment Authorities) to evaluate engineering options for environmental rehabilitations in agricultural areas subject to salinity risk. This project extends beyond the lifetime of LEME (December 2008).

1. Details of focus and outputs

New initiatives for drainage geochemistry risk assessment will focus on:

- Geochemical evaluation of risks associated with regional drainage of saline lands

- Assessment of potential trace-element risk risks in the Yarra Yarra, Blackwood, South Coast catchments

- Development of conceptual models for drain/groundwater interactions and element mobilisation/retardation

- Prediction of acidification risk to receiving environments

- Assessment of potential trace-element risk risks imposed by trace elements

- Active management of acid-trace element rich drainage waters

- Computer simulation(s) of groundwater evolution and regolith weathering during recent (up to 3 million years BP) aridity, with particular interest in the development of acidity.

Outputs

- Review of existing data on acid groundwater trace element geochemistry, soil types, regolith architecture, trace element analysis, flow regimes and, remote sensing data.

- Geochemical reconnaissance (similar to current Avon study) of existing drains, ground and surface waters

- Identification of knowledge gaps and additional data requirements needed to complete regional-scale geochemical risk assessment.

# Additional data collection: data required to fill knowledge gaps identified in Output iv, sampling and detailed geochemical analysis of ground waters and drainage waters, and mineralogical analysis of drainage material (especially Fe precipitates).

- Identification of potential geochemical hazards and risks.

- recommendations for management options during drain installation

- summary report of results, potential impacts, recommendations for management

- PHREEQC modelling in support of regional water balance assessments (part of EEI 2) using methods established for the CSIRO-EEI Avon Drainage Modelling project.

- Forecasting the impacts of engineering drainage on the transport and transformation of trace elements in undrained and drained environments

- Model output - Provide kinetic and/or thermodynamic input for further, more localised modelling. Input into understanding of groundwater geographical variation and impact

- Geochemical risks of receiving environments

This project will complement assessments in receiving environments being undertaken in the Avon Drainage, as part of Stage two of the current Avon EEI/CRC LEME project. The aspect will focus on:

  - playas and other natural wetlands,

  - surface waters (rivers, creeks)

  - engineered wetlands and disposal basins (Morowa, Bodallin)

Our project will provide assistance with site selection, and forge research partnerships with CALM and other partners, focussing on key receiving environments.  Priory will be given to existing or proposed community drainage projects.

Outputs

- Determination of trace-element and heavy-metal loadings to receiving environments from drains

- Prediction of trace-element and heavy-metal behaviour in receiving environments (proportion of material that remains in solution, as distinct from precipitation and incorporation into sediments).

- Geochemical speciation of trace-element and heavy-metals in receiving environment sediments.

- Determination of scenarios where sediment-bound trace elements and heavy metals may be re-solubilised and re-enter the aqueous phase

- Determination of long-term acid buffering capacity of alkaline receiving environments, and estimation of  useful life for acid drainage disposal

- Management options for minimising risks of trace elements in receiving environments

- Project coordination

The implementation of this project will mirror that applied in the EEI - Acid Drainage WA project (AG1) involving:

- Stage 1: Review of existing geochemical and regolith data.

- Stage 2: Additional data collection involving strategic sampling of surface, ground and drain chemistry and mineralogy.

- Stage 3: Integration of geochemical and mineralogical data with regional drainage modelling to evaluate regional scale geochemical risks.

A project of this magnitude requires a WA-based project manager, to coordinate day-to-day activities of scientific and community partners, including fieldwork, sampling, community liaison, data management. The project will be managed by Dr Brad Degens WA Department of Water

Outputs

EEI-2 Reporting

Research Management

Project Communication

Deliverables (outputs) and expected impacts of research (outcomes):

- Review of existing data on acid groundwater trace element geochemistry, soil types, regolith architecture, trace element analysis in existing drains, flow regimes and remote sensed data.

- Broad geochemical reconnaissance survey (similar to current Avon study) of existing drains, ground and surface waters across catchment to address spatial gaps in existing information.

- Identification of knowledge gaps and additional data requirements needed to complete regional-scaled geochemistry risk assessment.

# Strategic collection of additional geochemical and mineralogical data to fill knowledge gaps identified in Stage iii. (involving sampling and detailed geochemical analysis of ground waters and drainage waters, and focussed mineralogical analysis of drainage evaporates and precipitates),

- Geochemical modelling in support of regional water balance assessments using the methods established for the CSIRO - EEI Avon Drainage Modelling project - Geochemical modelling component.

- Identification of geochemical hazards and potential risks.

- Potential to provide new methods for testing regolith models and groundwater eveolution

Impacts include:

Allow hazards and risks from acid drainage to be assessed at local and regional scales and minimise environmental impact

- Science based improvements in management options

- Improved recommendations for management options during drain installation

Outcomes

- Evaluation of drainage through careful assessment of risk, opportunities and the determination of effective management systems.

- Enable NRM regions and stakeholder groups to develop a consistent approach to catchment and regional drainage, with minimal off site environmental impact.

4. Publications and Reports

1. Refereed Journals

Project in early Stages to be defined

2. Reports

Analysis and interpretation of geochemical risk Yarra Yarra catchment

Regional Evaluation of Geochemical Risks for the Blackwood Catchment and a Coast Catchment and management implications based on geochemical modelling outcomes Final Report

3. Conferences-Seminars

ISF 2008 Adelaide.  Provisional paper title: Acid saline drainage risk assessment and management.

Case studies to be included in the planned Thematic Volume ‘Inland Acid Sulfate Soil Systems’ Fitzpatrick, R. (Ed)

Milestones: (dates of significant events marking scientific progress)

| Milestone | Description | Date |
| --- | --- | --- |
| 1 | Project sign-off, contractual arrangements agreed. | 28 Feb 2006 |
| 2 | YY Contract – Sample collection and analysis completed for contract | 31 May 2006 |
| 3 | YY Contract – interpretation of geochemical risk completed (delivery as component of consultant contract report) | 30 June 2006 |
| 4 | Yarra Yarra and Blackwood- Existing geochemical data collated and reviewed. Interim report submitted. | 31 July 2006 |
| 5 | REVIEW MEETING -review existing data and identify additional information needs for Yarra Yarra and Blackwood | 1 Aug 2006 |
| 6 | YaYa Contract - Analysis and interpretation of geochemical risk completed (delivery as component of consultant contract report) | 30 Sept 2006 |
| 7 | TEAM MEETING -review progress of data collection, select sites for mineralogy surveys, identify geochem modeling scenarios | 1 Dec 2006 |
| 8 | Catchment 3 contract - Analysis and interpretation of geochemical risk completed (delivery as component of consultant contract report) | 31 Dec 2006 |
| 9 | Catchment 4 contract - Analysis and interpretation of geochemical risk completed (delivery as component of consultant contract report) | 31 Dec 2006 |
| 10 | Yarra Yarra and Blackwood– Overview of Blackwood and Yarra Yarra geochemistry survey results. Interim report submitted. | 28 Feb 2007 |
| 11 | TEAM MEETING - team meeting to review data, identify remaining information gaps and commence risk assessment for Yarra Yarra; review existing data and identify additional information needs for South Coast. Complete 4-D model. | 30 May 2007 |
| 12 | Blackwood: Regional evaluation of geochemical risks for the Blackwood catchment and drainage management implications based on geochemical modelling outcomes - Final report submitted | 31 Oct 2007 |
| 13 | TEAM MEETING – Drafting of Yarra Yarra report, review South Coast and receiving environment geochemistry data and modelling. | 31 Jan 2008 |
| 14 | Yarra Yarra - Regional evaluation of geochemical risks for the Yarra Yarra catchment and management implications for drainage based on geochemical modelling outcomes - Final Report submitted | 31 March 2008 |
| 15 | South Coast + Receiving Environment (RE) Geochemical Risk Evaluation – Overview of South Coast and combined receiving environment geochemistry survey results. Interim report submitted. | 30 May 2008 |
| 16 | TEAM MEETING –Drafting of receiving environment and South Coast catchments reports. | 30 July 2008 |
| 17 | Receiving Environment (RE) Geochem Risk Evaluation : Geochemical risk assessment of acid waters in receiving environments and management implications based on geochemical modelling outcomes - Final Report submitted | 30 Sept 2008 |
| 18 | South Coast: Regional evaluation of geochemical risks for south coast catchments and implications for drainage management based on geochemical modelling outcomes - Final Report submitted | Dec 2008 |

Confidentiality requirements

Permission to be sought from WA DoE EEI (John Ruprecht) prior to media contact

Date submitted to Executive:

Date approved by CEO/Exec:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P Shand | IK |  |  |  |  | 0.10 |  |  |  |  |
| R. Fitzpatrick | IK |  |  |  |  | 0.10 |  |  |  |  |
| D.Gray | IK |  |  |  | 0.20 |  |  |  |  |  |
| Grant Douglas | IK |  |  |  |  | 0.10 |  |  |  |  |
| Grant Douglas | Industry |  |  |  |  | 0.10 |  |  |  |  |
| A Baker or GIS | Industry |  |  |  |  | 0.2 |  |  |  |  |
| R Noble | IK |  |  |  | 0.10 |  |  |  |  |  |
| TOTAL |  |  |  |  | 0.30 | 0.50 |  |  |  | 0.80 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 50 |  |
| Committed (definite) external funds | 176 | WA EEI |
| Total Project Opex | 226 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties – to be agreed

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Data Management |  |  |  |  |  |  |  |  |  |
| Geochemical Modelling (salary) |  |  |  |  |  |  |  |  |  |
| Analytical Technical Assistant (ICP-MS) |  |  |  |  |  |  |  |  |  |
| Analysis (Anions, mineralogy) |  |  |  |  |  |  |  |  |  |
| Field Sampling consumables |  |  |  |  |  |  |  |  |  |
| Field work (vehicles, accommodation, travel) |  |  |  |  |  |  |  |  |  |
| Review meetings x 2 |  |  |  |  |  |  |  |  |  |
| 4-D Modelling |  |  |  |  |  |  |  |  |  |
| Total |  |  |  | $20K | $106K |  |  |  | 226K |