Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		3.27				(Issued by LEME Head Office)

Submitted by:	Paul Shand

Date submitted: 	20/4/07			V1

Project name:  	Evaluation of Acid Drainage Treatment Technologies AG 3

Abbreviated title: 	AG3

Type of project  Industry					(Centre or Industry/Commercial):

Program:  	3

Themes:  	Acid Sulfate Soils

Project Leader:  	Brad Degens(DoW)/Paul Shand

Start date and duration:  01.07.07-30.06.09

Participants:	 	Consortium of LEME, DoE WA, D0W WA, Agriculture WA – WA EEI and Avon Catchment Council

Brief project description:

This project forms part of the Avon catchment Council (ACC) investment in Salinity Management.  The project will be managed by the WA Department of Water.  The project will build on the outcomes of the two current P3 acid drainage geochemistry risk assessment projects (3.15 and 3.26).  Both these projects have established that acid drainage waters in the WA wheatbelt are widespread and contain highly elevated levels of heavy metals and trace elements.  The two projects have also established appropriate sampling protocols, water and sediment analytical procedures (in the presence of highly elevated salt concentrations) and made some initial management recommendations.  However, if drainage is to be widely adopted as a salinity mitigation management tool in areas of acid groundwater then appropriate technical options for the treatment of acidity and mitigation of trace elements need to be developed.

Treatment technologies for acidity and trace element mitigation will be trialled and demonstrated in three ways:

- Through the construction and study of pilot scale engineered treatment/evaporation basins where a range of treatment options will be trialled;

- Investigating the feasibility of ‘in-drain’ treatments that do not require significant engineering works; and

- Amelioration of acidity and associated trace element precipitation through mixing acid drainage waters with alkaline surface waters

Project aims

- to review and report on available treatment methods for acidic drainage waters

- to identify feasible treatment methodologies and identify sites for method evaluation;

- construct and evaluate practical options for treatment of acidic saline drainage waters, focussing on the discharge point of drains;

- evaluate simple, low cost options for treatment of acidic saline drainage waters in drains;

- identify, evaluate and demonstrate practical options for treatment of acidic saline drainage waters exploiting mixing with alkaline surface waters;

- develop a set of best-management practice guidelines for such drainage treatments in the Avon catchment;

- promote the outcomes of evaluation trials and best management guidelines to the broader community in the Avon River Basin;

- contribute to 2006-2008 investment planning for salinity management in the Avon Region.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Acidity and geochemical changes and the proportion of metals in solution compared to the proportion of metals precipitating out into sediment material will be monitored throughout the study using advanced analytical techniques (Inductively Coupled Plasma-Mass Spectroscopy, X-ray diffraction, isotope analysis).

- Geochemical models will be developed to predict the behaviour of trace elements and heavy metals during treatment feasibility studies.

- Information on the feasibility of treatment and disposal options will be communicated to end-users through pilot scale demonstration trial field days.

- Incorporation of management recommendations into EEI, NAP drainage management guidelines, information meetings with community groups, WA Channel Management Group (WACMG), CMA’s. Technical reports and progress reports as part of EEI program to ACC.

- Information relating to the potential costs of treatment/disposal options will also be communicated to end users.

Outcomes and Impact

- Development of cost effective treatment options for disposal of acid groundwater in the WA wheatbelt

- Enable NRM regions and stakeholder groups to develop a consistent approach to acid drainage disposal, with minimal off site environmental impact.

Milestones: (dates of significant events marking scientific progress)

| ITEM | Date |
| --- | --- |
| 1. Sign-off on contract | 1 December 2006 |
| 2. Analysis of water chemistry for CaCO3 based treatment trials completed and delivered | 31 May 2007 |
| 3. Interim report – effectiveness of neutralisation of acid drainage waters by floodwaters and fate/risk of neutralisation products | 31 October 2007 |
| 4. Analysis of water chemistry for sulfide bioreactors/treatment trenches completed and delivered | 30 December 2007 |
| 5. Analysis of sediment and neutralisation product chemistry completed and delivered | 28 February 2008 |
| 6. Final report - Efficiency of acid drainage treatment options and mitigation of geochemical risks (including fate, form and long-term stability of neutralisation products) | 31 March 2008 |

To be negotiated with Client (ACC) and project partners

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO/Exec:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| W Hicks | Industry |  |  |  |  | 0.05 |  |  |  |  |
| W Hicks | CRC |  |  |  |  | 0.05 |  |  |  |  |
| W Hicks | IK |  |  |  |  | 0.1 |  |  |  |  |
| M Raven | IK |  |  |  |  | 0.1 |  |  |  |  |
| P Shand | IK |  |  |  |  | 0.1 |  |  |  |  |
| G Douglas | IK |  |  |  |  | 0.05 |  |  |  |  |
| TOTAL |  |  |  |  |  | 0.10 |  |  |  | 0.10 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested |  |  |
| Committed (definite) external funds | 220 | Avon Catchment Council |
| Total Project Opex |  |  |

| Possible additional external funds (for info) |  | CouncilCC |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

Currently too early in project Development to determine distribution of operating costs – allocation still to be determined by Project Leader

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  |  |  |  |  |  |