Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		3.20 			(Issued by LEME Head Office)

Submitted by:		Rob Fitzpatrick

Date submitted: 	31 May 07		V2 Paul Shand

V3 with additional opex 11.1.08

Project name:  	Inland acid sulfate soils: distribution and regolith processes

Abbreviated title: 	Inland ASS

Type of project	Centre / Industry

Program:  		3 - Environmental applications of regolith geoscience

Themes:  		Acid Sulfate and Alkali Soils

Project Leader:  	Rob Fitzpatrick

Start date and duration:  July 2004, 3 years (to 2008)

Participants:	 	CSIRO Land and Water, AU, ANU

Brief project description:

Objectives

- To develop innovative approaches and methodologies for constructing mechanistic models of soil-landscape evolution for inland sulfidic environments, including inland acid sulfate soil (ASS) and groundwater systems across Australia.

- To apply this information to derive pedo-regolith transfer functions to help spatially model and predict soil-water landscape properties at 30 pilot regions/catchments across Australia (3-8 pilot studies per State) with implications for infrastructure and NRM planning, water quality management and mineral exploration.

- To apply this information to publish an Atlas of inland ASS in Australia, which includes: (i) a national map of inland ASS with common legend that incorporates risk assessment criteria and correlations between Australian and International Soil Classification Systems, (ii) database of representative soil-regolith case studies from pilot regions around Australia and (iii) web-based product geo-referenced with other ASRIS products.

Scope of Work

- Create a project framework under which integrated outcomes will be delivered to develop a national understanding of the spatial distribution and process of Inland ASS and related hydrology in Australian regolith by undertaking the following three sub-projects:

(i) Spatial distribution and processes of Inland ASS and acidic groundwaters,

(ii) Geochemistry, isotope geochemistry and mineralogy,

(iii) Biomineralisation and microbial biochemistry.

Knowledge to Date

This new project builds on knowledge of existing staff in CRC LEME with skills in pedology, mineralogy, geochemistry, hydrogeochemistry, geophysics and microbiology.  Current staff and students in CRC LEME have developed and are continuing to develop special-purpose mechanistic process models and GIS up-scaling approaches for the broad-scale mapping to characterise, map and remediate inland ASS.  They have also demonstrated that Inland ASS can contain anomalous concentrations of elements such as Cu, Pb, and Zn and introduced a new geochemical sampling medium for mineral exploration (ore bodies). However, most of this research was conducted in SA and thus far these projects have not been combined into a unified national approach to optimise the use of resources and these approaches.

The distribution and mechanisms of ASS, especially for Inland ASS, have not been adequately assessed nationally despite their known significance in relation to land degradation, water quality and mineral exploration.  It is now critical to define the national spatial distribution, impact on water resources, land degradation and significance to mineral exploration in order to provide the scientific underpinning for policy development, management, amelioration and to identify regions where ASS sampling can be used in mineral exploration.

What is New?

This project integrates new and previous Inland ASS and related hydrogeochemistry projects carried out in Australia for mineral exploration, NRM planning, acidity assessment and management into a National strategic initiative.

Interactions with other projects

This project is linked with CRC LEME projects: (i) 3.18: Impact of water level draw downs on the geochemistry of saline River Murray wetlands (Draw Down Geochemistry), the SA Department of Water, Land and Biodiversity Conservation “Loveday Rehabilitation” program and the ANU, (ii) 3.19: Investigating the role of microbial processes in cycling of Fe, S, and metals in acid sulfate soil sites). Close linkages with WA Drainage project (Steve Rogers/ Richard George).  Focus and align Inland ASS research in Australia through NatCASS (steering committee for map component) and other State and Federal NRM committees.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Develop improved geophysical and geochemical field methods to characterise and map various sulfidic environments across Australia. (RWF, MT, GH).

- Develop quantitative mineralogical (XRD) and geochemical (XRF) techniques to improve reliability, accuracy and speed of analysis of ASS. (RWF, MF).

- Develop new and or more accurate soil-landscape process models of Inland ASS. (RWF).

- Provision of new information on the distribution and properties of Inland ASS in 30 pilot regions/ catchments across Australia (series of web-delivered ASS maps). (RWF).

- Develop and promote improved risk assessment and land management systems for Inland ASS. (RWF, WH).

- Develop new geochemical applications for identifying, and sampling ore bodies from inland ASS and related seepage areas (RWF, WH).

- Provide leadership on the development of national (through NatCASS) and international (through International Union of Soil Sciences) interpretation guidelines for describing, characterising, classifying and managing inland sulfidic environments. (RWF)

- Scientific reports and papers (at least one for Science or Geoderma).

- An Atlas of Australian inland ASS (Stage 3), incorporating:

A database of representative soil-regolith case studies from 30 pilot regions/ catchments across Australia,

- A better understanding of inland ASS geochemical processes in different geomorphic, geologic, mineralised zone and land use settings across Australia and publishing this information in a special LEME Monograph/ web site on Inland ASS in Australia.

- A national map of inland ASS with common legend (web-based product geo-referenced with other ASRIS products) that incorporates: (i) risk assessment criteria, (ii) correlations between Australian and International Soil Classification Systems, (iii) policy, (iv) land-use planning and (v) signatures of economic mineralization.

- Presentations at a National Inland ASS workshop and five International Conferences.

Outcomes

- Develop a national understanding of the spatial distribution and biogeochemical process leading to Inland ASS formation and related hydrology in Australian regolith

- Provide scientific basis upon which ASS risk assessment and management strategies can be developed

Milestone Achievements (Progress against milestones, outputs and outcomes)

| Milestones, outputs and outcomes | Mile- stone Date | Progress status to June 2008 (achievements and breakthroughs/ problems experienced) |
| --- | --- | --- |
| Develop improved geophysical and geochemical field methods to characterise and map various sulfidic environments across Australia. | Sept 04 July 06 Sept 06 June 2008 | Significant overall progress has been made to link pedological, geophysical (gamma ray radiometrics, electromagnetics, magnetics and ground penetrating radar) and clay minerals (layer silicates, oxyhydroxides, sulfides, etc) and remote sensing data to deduce sub-surface geochemical processes and understand how specific properties impact on ASS. Organised/ran ClayGEMME 2004 workshop: published 5 papers Organised and presented three talks at the special symposium at the 18th World Congress of Soil Science (July 9-15, 2006 in Philadelphia, USA) on “Soil Mineralogy and Geophysics for Environmental Management and Mineral Exploration (ideas gained from ClayGEMME 2004 workshop). Presented invited keynote paper on “Mineralogy of inland ASS” at symposium on ASS Mt Lofty Ranges (SA) – The following two PhD theses were completed and submitted for external examination: Andrew Baker (Herrmanns and Rodwell catchments) and Mark Thomas (Herrmanns and Spalding catchments), which includes Inland ASS in a Pb-Zn mineralised zone, degraded wetlands and polluted streams. Ground penetrating radar and magnetics illustrated occurrence of paleo-channels and soil morphological features. Publish 5 papers on improved geophysical and geochemical field methods to characterise and map various sulfidic environments across Australia. |
| Develop quantitative mineralogical and geochemical techniques to improve reliability, accuracy and speed of analysis of ASS. Assessing biological potential | July 06 July 07 Aug 07 June 2008 | A draft paper has been written outlining the development of standard XRF laboratory methods for determining major elements (fusion method) and trace elements is nearing completion. The latter method has been refined to determine high concentrations of Se (>1ppm), Br, I, Cl and U. An XRF standard fusion and pressed pellet method has been developed by Mark Fritz – MSc student. Also progress has been made in testing the speciation potential of XRF for the characterisation of pyrite minerals in ASS. Obtained good correlation with chromium reducible method for pyrite determination for several known samples across Australia... Three project proposals (for beam time) have been written with Dr Rosalie Hocking to analyse selected Inland ASS samples containing As, Se, Zn, Cu, Cr using synchrotron techniques via CSIRO Emerging Science – synchrotron: Environmental and extreme chemistry – project. Progress in development of new national and international soil classification definitions with Prof Leigh Sullivan (CRC CARE). Final report, MSc thesis (technical report) and paper with new XRF methods for ASS |
| Develop new and or more accurate soil-landscape process models of Inland ASS Provision of new information on the distribution and properties of Inland ASS in 30 pilot regions/ catchments across Australia (series of web-delivered ASS maps). | July 05 Sept 05 Feb 06 May 06 April 06 April 06 May 06 May 06 Aug 06 Nov 06 Feb 06 April 07 June 08 | Very good progress has been made in the development of several new mechanistic models for regions/catchments using the toposequence approach, which integrates pedological, mineralogical, hydrological, biogeochemical, geological, climatic and land-use information for the following new/in progress case studies in: South east (SA) – Completed CRC LEME report: “An evaluation of the soils of Tilley Swamp and Morella Basin, South Australia by Richard Merry and Robert Fitzpatrick for South Australian Department of Water, Land and Biodiversity Conservation. WA Wheat belt drainage project– Completed paper for CRC LEME Regolith Symposium on ”Geochemistry and Mineralogy of soils, salts, gels, precipitates and sulfidic materials in drains, including publication of models. Stage 2: Sampling and analyses of Receiving Environments (Acid/alkaline lakes) in WA Wheat belt Write-up of stage 2: model development – delay because of delay in sample preparation and chemical analyses. Riverland – Loxton: Completed CRC LEME report: “Evaluation of Floodplain Soils along the Loxton Salt Interception Scheme Pipeline Corridor near Loxton, South Australia by Robert W Fitzpatrick, Warren S Hicks, Andrew Baker and Julianne James–Smith for South Australian Water Corporation. Dundas Tableland (Victoria) – Completion and award of PhD to Jon Fawcett – on development of a mechanistic model to predict ASS soil-water landscape properties with implications for infrastructure and NRM planning, water quality management. Commenced joint investigations with South Para Biodiverstiy project/ Catchment Board at the Puddledock landslide/erosion site where a major inland Acid Sulfate problem exists (land and water degradation) because the site is less 2kms from the South Para reservoir Rob Fitzpatrick. Mid North - Port Pirie: Completed CRC LEME report: Evaluation of Acid Sulfate Soil Conditions at the Solomontown Island Marina Development Site, South Australia: Brett Thomas and Rob Fitzpatrick Mt Lofty Ranges (SA) –Completion of two PhD theses by Andrew Baker (Herrmanns and Rodwell catchments); Mark Thomas Case study in Victoria - Dowds Morass in Gippsland – some additional funding is being negotiated via several agencies in Victoria. This project has been put on hold and replaced by major funded project ($70K) to investigate ASS in Corangamite CMA. Completed field work in October and lab data almost completed and write-up of final report completed by end of February Case studies in NSW – mostly case studies in Dicks creek catchment / others. Some additional funding is being negotiated via several agencies in NSW (Warren Hicks to lead on this). Case studies in Tasmania –Commenced case studies in North East and North western regions in February 07 with Paul Shand, Mark Raven and Steve Marvanek and other NatCASS members. Some additional funding / in-kind has been acquired via several agencies in Tasmania (via Rob Morton) Publish 4 papers and 2 reports covering completed case studies (Tilley Swamp, Tasmania, Dowds Morass, Port Pirie, Dundas Tableland and Loxton). |
| Develop and promote improved risk assessment and land management systems for Inland ASS Develop new geochemical applications for identifying, and sampling ore bodies from inland ASS and related seepage areas | Jul 07 Sept 05 June 08 | Development and promotion of improved risk assessment and land management systems for ASS - See case study reports above. Presented oral paper at the 22nd International Geochemical Exploration Symposium, Perth on “Inland Acid Sulfate Soils – a new geochemical sampling medium: A regional orientation study from the Mount Lofty Ranges, South Australia” by Marian Skwarnecki and Rob Fitzpatrick. Organise and present papers at International Salinity Forum in Adelaide, 31 March – 3 April 2008. Organise and present community and consultant forums in NT and SA. Brochure on Inland Acid Sulfate Soils: Identifying and assessing Inland ASS |
| Provide leadership on the development of national and international interpretation guidelines for describing, characterising, classifying and managing inland ASS Publish scientific papers | July 05 Aug 05 Aug 05 Feb 06 Feb 06 March 6 April 06 Aug 06 Sept 05 Sept 06 Aug 07 April 06 May 06 June 06 June 08 | Provided on-going technical and policy advice on Inland ASS by presenting/writing: (i) several invited papers/keynote addresses at workshops/conferences in Australia (Adelaide, Perth, Melbourne, Brisbane and Cairns) and overseas (USA, Europe); (ii) information at national (NatCASS/ NRM Standing/Ministerial Committees) and international (IUSS) committees; (iii) information to mineral exploration companies and at both public and government arenas, (iv) lecturing at international / Australian Universities agencies/conferences to successfully insure that Inland ASS is recognised as a “Geohazard to environments of the world”. Visiting Professor at the “Summer University of the University of Lleida” Spain, Rob Fitzpatrick gave lectures on “Inland ASS and granite weathering processes” and assist students field studies of soils in the La Cerdanya (Pyrenees, Catalonia, northeast Spain) 11th course; 18th to 21st July, 05. Visiting scientist at Institut de Recherche pour le Developpement (IRD) and Institut de Mineralogie et de Physique des Milieux Condenses (IMPMC) in Paris where Rob Fitzpatrick gave a seminar on ASS and developed linkages with researches to undertake future collaborative research on metals and metalloides in sulfides and iron oxides in Australian ASS via Synchrotron experiments in France with Drs Emmanuel Fritsch, Etienne Balan, Guillaume Morin and Farid Juillot. Visiting scientist to International Soil Reference and Information Centre (ISRIC) and ICSU World Data Centre for Soils, where Rob Fitzpatrick gave a seminar on ASS and develop linkages with Dr David Dent (Director) to progress proposed publication: “Inland ASS: a global overview” Provided information (agenda papers)/presentations to several national committees such NatCASS, Marine And Coastal Committee (MACC), NRM Standing Committee (NRMSC), NRM Ministerial Committee (NRMMC) and LGPMC on the recent outcomes/future work of the “Atlas of Australian Acid Sulfate Soils (ASS) Project (Stage 1 to 3): NatCASS – Melbourne and Gippsland MACC – Adelaide NRMSC – Adelaide NRMMC – Sydney Local Government and Planning Ministers Council - Adelaide Gave lecture and field trip: “ASS origin, distribution, development and management” and ran one day Field trip for the “Surficial Geology III at the University of Adelaide (Rob Fitzpatrick). Paul Shand also participated. Provide lectures in 06 and 07 as for Sept 05: Uncompleted Initiated/organised/presented three papers at the International Workshop on Criminal and Environmental Soil Forensics (part sponsored by LEME) 8th and 9th April 2006, Perth (WA Chemistry Centre) A Post Symposium Workshop following the 18th International Symposium on the Forensic Sciences. Present keynote address and publish paper on “Coastal Acid Sulfate Soils: National Atlas and Future Scenarios” at the Coast to Coast Conference in Melbourne in May, 2006. Publish journal paper on: “Inland Acid Sulfate Soils – a new geochemical sampling medium: A regional orientation study from the Mount Lofty Ranges, South Australia” by Marian Skwarnecki and Rob Fitzpatrick. Draft paper submitted – to finalise by July 07 Publish two journal overview papers on: New minerals and models in inland ASS (possibly Science / Geoderma). Organise and present papers at International Salinity Forum in Adelaide, 31 March – 3 April 2008. Brochure on Inland Acid Sulfate Soils: Identifying and assessing Inland ASS |
| Develop an Atlas of Australian inland ASS, (Stage 2 and 3) incorporating a database of representative soil-regolith case studies from 30 pilot regions/ catchments across Australia | Feb 05 March 06 Feb 06 Aug 07 June 08 | Progress in the development of a framework for national database for 30 sites, including incorporation of process models, with Andrew Baker using FrontPage web based software. Completed paper for CRC LEME Regolith Symposium on the development of online database using toposequence approaches incorporating, pedological, geochemical and mineralogical data with Andrew Baker (PhD student). Publication of article in Focus on Salt in Issue 36, March 06. Ahead of schedule – have developed a draft legend for the National Inland ASS map (Stage 3) to reside on ASRIS web site via NatCASS. To trail and present to NatCASS in Tasmania in Feb 07 Final National Atlas of Inland ASS (Stage 3) – Incomplete but good progress is made. Publish national map of inland ASS (with accompanying report and meta-data) |

Confidentiality requirements

NONE

Date submitted to Executive: 		11 April 2007

Date approved by CEO/Exec:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

All LEME Students contributing to Project - 2005 - 2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Andrew Baker (LEME) | AU | PhD |
| Mark Thomas (LEME) | AU | PhD |
| Mark Fritz (LEME) | AU | MSc |
| Luke Wallace (LEME) | ANU | PhD |
| Jon Fawcett (non LEME) | Melbourne | PhD |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 15 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex |  |  |

1Carry-over from 2005-2006 to ensure: (i) final completion / presentation of reports and payment of contracted consultants (Merry, Thomas and Baker); and (ii) Travel costs to International Soil Conference in USA in July 2006

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rob Fitzpatrick | IK |  |  |  |  | 0.20 |  |  |  | 0.20 |
| Warren Hicks | IK |  |  |  |  | 0.05 |  |  |  | 0.05 |
| Paul Shand | IK |  |  |  |  | 0.05 |  |  |  | 0.05 |
| Steve Wakelin | Free |  |  |  |  |  |  |  |  | 0.10 |
| Mark Thomas (WA drainage) | Free |  |  |  |  |  |  |  |  | 0.1 |
| Richard Merry (Tilley swamp) | Free |  |  |  |  |  |  |  |  | 0.05 |
| Brett Thomas (Solomontown Loxton | Free |  |  |  |  |  |  |  |  | 0.1 |
| Andrew Baker Loxton/National ASS database) | Free |  |  |  |  |  |  |  |  | 0.1 |
| TOTAL |  |  |  |  |  | 0.3 |  |  |  | 0.75 |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008 Show major expenditure items and allocation to core parties

See outputs above in bold

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Organise and present community and consultant forum in NT and SA. Travel costs and accommodation. |  |  |  |  | $5K |  |  |  |  |
| Brochure on Inland Acid Sulfate Soils: Identifying and assessing Inland ASS |  |  |  |  | $4K |  |  |  |  |
| Artwork for minimum 12 papers, reports and flyers |  |  |  |  | $2K |  |  |  |  |
| GIS & Web-site processing and specialized graphics. GIS personnel support (S Marvenick and ASRIS) |  |  |  |  | $3K |  |  |  |  |
| Total |  |  |  |  | $14K |  |  |  |  |

DELIVERY MILESTONES FOR OPERATING

| Activity | Milestone | Indicator of milestone | Date planned | OP budget requested | Date for operating to be requested |
| --- | --- | --- | --- | --- | --- |
| Organise and present community and consultant forum in NT. Travel costs and accommodation. | Forum | Delivery of Forum | August 2007 | $4K | August/September 2007 |
| Organise and present forum to MDB Commission in Canberra. Travel costs and accommodation | Forum | Delivery of Forum | October 2007 | 1K | October/ November 2007 |
| Brochure on Inland Acid Sulfate Soils: Identifying and assessing Inland ASS | Brochure | Delivery of brochure to LEME | March 2008 | $5K | March/April 2008 |
| Artwork for minimum 12 papers, reports and flyers | New figures | Publications of brochure and reports | Throughout FY | $1K | May 2008 |
| GIS & Web-site processing and specialized graphics. GIS personnel support (S Marvenick and ASRIS) | Maps into ASRIS | Incorporation into ASRIS on Web | Throughout FY | $3K | May 2008 |
| Total |  |  |  | $14K |  |

Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-81205

Project No:  						(Issued by LEME Head Office)

Submitted by:		Rob Fitzpatrick

Date submitted: 	October 2007

Project name:  	Booklet to assess, monitor and manage Acid Sulfate Soils in 
                                       wetlands below Lock 1, Blanchetown, South Australia

Abbreviated title: 	Acid sulfate soil booklet

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		P3

Themes:  		Acid Sulfate and Alkali Soils

Environmental geochemistry and the regolith

Project Leader:  	Rob Fitzpatrick

Start date and duration:  October 2007 – June 2008

Participants:	 Rob Fitzpatrick (CSIRO Land and Water), Paul Shand (CSIRO Land and Water), Warren Hicks (CSIRO Land and Water) and Richard Merry (Research Fellow in CSIRO Land and Water), Russell Seaman (wetland vegetation expert, DEH SA)..

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

- The aim of the project is to publish an easy-to-follow pictorial booklet incorporating a “pictorial soil identification key” for local advisers and farmers to easily identify the various ASS types in wetlands below Lock 1 (Blanchetown).  The pictorial manual will assist in the identification of ASS types at local and regional scales and allocate a suitability assessment.

- The pictorial manual will include a suite of robust ASS indicators, which can reliably predict the direction and extent of changes that are occurring in the wetlands (based on Fitzpatrick et al 2003a;b).

- The indicators will have meaning to local and regional community/committee groups and to policy developers.  The ASS indicators will be based on intermediate quality (easily collected/inexpensive) but dense (extensive) data and will be particularly useful as an early warning of wetland system decline or improvement.

- Linking the soil and vegetation indicators to a pictorial soil-landscape and vegetation key and thereby matching to locally practised on-farm management options.

Deliverables (outputs) and expected impacts of research (outcomes):

- The ASS indicators will become central for benchmarking and monitoring of ASS in wetlands for the whole Murray Darling Basin.  As such, the approach seeks to assist communities assess their local wetlands using the best techniques developed to date.  The adoption and regular use of these ASS indicators will also:

- Identify site-specific constraints to productivity.

- Identify risks for future degradation of regional soil and water resources.

- Aid future property planning.

- Generate spatial information for reporting on the state of local wetland environments.

- This project links directly with the CRC LEME National Inland ASS project led by Dr Rob Fitzpatrick and interacts with similar project interests in drained areas of Western Australia.

Impacts

- The approach will seek to develop and encourage a community-based ethos for monitoring ASS in local wetland environments and for assessing the sustainability of current farming practices.  To make this technology bring about change in practice at the local scale and improve sustainability at regional and local scale and will involve working closely with decision makers and opinion leaders (e.g. local community groups and state planning committees) at different levels of responsibility.  People from these groups will consult with staff from CSIRO and CRC LEME during all stages of the project and provide key bridging to accomplish the final project aims.

- Contribute to changes in government agency and industry practice to assess inland ASS (i.e. describe, sample, characerise, analyse and map) for improved environmental risk assessment and management strategies.

- This six month LEME / CSIRO funded project is an opportunity to showcase LEME’s ability to effectively integrate and summarise research expertise in soil science, regolith, geology, mineralogy, biogeochemistry, policy and to investigate a potential natural hazard in the soil-regolith-water environment.  The project is likely to lead to further client-funded research and publications in post LEME, especially 2009-2010.

Background

Due to falling river levels in the Murray, 51 wetlands below lock 1 have become disconnected at 0.1m AHD from the main channel. A further 23 wetlands are at various levels of drying at 0.1m AHD. CSIRO have completed surveys on around 20 of these wetlands between Lock 1 and Wellington. CSIRO have also completed surveys of Lakes Alexandrina and Albert. Initial results between Lock 1 and Wellington indicate that:

- Most of the subaqueous soil materials sampled in the Murray River contained high contents of pyrite with an ASS hazard risk ranging from moderate to severe. It is estimated that large quantities of sulfuric acid will be produced in the subaqueous ASS to a depth of > 50 cm if the river levels lowered significantly and the adjacent wet soils were allowed to dry.  In addition, salinity, wind erosion (e.g. aerial transport of fine granular surface flakes containing sulfuric material and salt efflorescences), mobilisation by rainfall events and malodorous problems may become serious issues.

- It is expected that the greatest potential for acid generation will be where no calcrete deposits exist, that is, with increasing distance from the soft limestones that occur along the margins of the incised river valley.

- The sulfidic material has the potential to produce sulfuric acid in amounts that are beyond the capacity of the soil materials to neutralise.

- Around 75% of samples investigated have a net acid generation potential.  Hence, the sulfidic material has an ASS hazard ranging from moderate to severe).

Milestones: (dates of significant events marking scientific progress)

November 2007:   Collate >20 ASS published case history studies conducted by
                              CSIRO and construct two to five toposequence / cross sections

December 2007:   Construct draft booklet with photographs of key ASS indicators 
                               / ASS profiles and colour cross sections/ toposequence models, 
                               ASS Maps of key areas.

June 2008:	    Edit and preparation for publication and printing direct
                     from LEME Web.

Confidentiality and IP requirements:

Soil and regolith analyses and metadata developed from several ASS studies conducted by CSIRO from Lock 1 to Lower Lakes;  and ‘regional seepage geochemistry’ studies and Stages 1 to 4 from the National Atlas of ASS project (NatCASS steering committee)  currently jointly owned by CSIRO Land & Water, Land & Water Australia (NDSP II; NAP; ASRIS) and LEME 1 and 2.  Prior ownership of this IP will need to be recognised in any future IP generated from this specific project.

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rob Fitzpatrick | in kind |  |  |  |  | 0.10 |  |  |  | 0.10 |
| Warren Hicks | In kind |  |  |  |  | 0.05 |  |  |  | 0.05 |
| Paul Shand | in kind |  |  |  |  | 0.05 |  |  |  | 0.05 |
| Phil Slade (editorial) | Industry as required |  |  |  |  |  |  |  |  |  |
| Richard Merry (Editorial) | Industry as required |  |  |  |  |  |  |  |  |  |
| Doug Reuter (editorial) | Industry as required |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  | 0.20 |

All LEME Students contributing to Project - 2007 - 2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 14 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 14 |  |

| Possible additional external funds (for info) | 10 |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Specialized graphics to produce soil/ water / regolith toposequences |  |  |  |  | 4 |  |  |  | 4 |
| Specialized graphics and typing to produce booklet – in colour |  |  |  |  | 4 |  |  |  | 4 |
| Publish booklet |  |  |  |  | 6 |  |  |  | 6 |
| Total |  |  |  |  | 14 |  |  |  | 14 |

LEME funds sought (a single $ figure only):	$ 14K

Funding will be required to:

(i) Undertake drafting of diagrams, tables to help produce uniform/standard format.

(i) Undertake production of soil/ water / regolith toposequences.

(iii)  Publishing of booklet in colour: run training program.

External funding provided/sought:				$ 10K (in-kind contributions from several community groups and state agencies.

Appendix

Stage 1: Interpretation of field and laboratory data

Construct soil-water process models:

We will construct cross-section diagrams and mechanistic models of paired sites (subaqueous ASS, drained ASS and re-flooded ASS) at each case study wetland site (approx 20 wetlands previously studied by CSIRO).  The mechanistic model is a schematic cross sectional diagram illustrating the soil-water change processes occurring in each soil layer (i.e. losses and gains of salts, solutes, colloids, water and other constituents).  This necessitates recognizing specific soil features, interpreting pH, EC, geochemical and mineralogical data and then grouping the similar soil characteristics into a fewer number of layers using the structural analysis approach (Fitzpatrick et al. 2003a).  The toposequence (soil landscape cross-sections) is suitable for constructing such mechanistic models of spatial and temporal soil-regolith changes in drained and reflooded marshland soils, because each of the vertical and lateral changes can be linked to hydrological and biogeochemical processes.  These soil-regolith models will be used to generate rough soil maps and help to produce practical soil-landscape and vegetation field keys for land mangers in this region.

To integrate field and laboratory experimental data (described above) we will use the pedogeomorphic models to describe and interpret pedogenic processes continuing across different soil layers in the paired sites (“structural approach” outlined in Fitzpatrick et al 2003a).

Stage 2: Publication of ASS booklet with maps

Procedures (based on Fitzpatrick et al 2003a) for identifying the best set of soil-landscape and vegetation field indicators for marshland soils will include:

- Using an idealised soil toposequence to encompass a compilation of the main features present within most of the major toposequences of a specific region.

- Linking the soil and vegetation indicators to a pictorial soil-landscape and vegetation key and thereby matching to locally practised on-farm management options.

- Publishing a practical soil classification system in a user-friendly pictorial booklet  to help land managers assess, monitor, and manage ASS in wetlands.

References:

McVicar, T.R., Rui, L., Walker, J., Fitzpatrick, R.W. and Liu Changming (Editors) (2002) Regional Water and Soil Assessment for Managing Sustainable Agriculture in China and Australia. ACIAR Monograph 84. CSIRO Publishing, Melbourne, Australia. 384 pp.

Fitzpatrick R.W., J.W Cox, B. Munday, and J. Bourne, (2003a).  Development of soil- landscape and vegetation indicators for managing waterlogged and saline catchments.  Australian Journal of Experimental Agriculture: Special Issue on “Application of Sustainability Indicators” 43 245-252.

Fitzpatrick, R.W., Merry R.H, Cox J.W., Rengasamy P and P.J. Davies (2003b).  Assessment of physico-chemical changes in dryland saline soils when drained or disturbed for developing management options. CSIRO Land and Water Technical Report 02/03. CSIRO, 56pp. http://www.clw.csiro.au/publications/technical2003/tr2-03.pdf

Fitzpatrick, R.W., Merry R.H, Shand, P. & Raven, M. 2007 Information paper on environmental and management issues associated with subaqueous and wetland soil drying between Wellington and Lock 1: acidification, contaminant mobilisation and degree of odour production.

Fitzpatrick R.W., J.W. Cox, and J. Bourne (1997).  Managing waterlogged and saline catchments in the Mt. Lofty Ranges, South Australia: A soil-landscape and vegetation key with on-farm management options.  Catchment Management Series.  CRC for Soil and Land Management.  CSIRO Publishing, Melbourne, Australia, 36 pp.