Cooperative Research Centre for Landscape Environments and Mineral Exploration

Ongoing ……YES (Amalgamation of two existing projects)

PROJECT SUMMARY				HO-170105

Project No:  		4.10

Submitted by:		Colin Pain

Date submitted: 	19th April 2007		V2 Ken Lawrie 17 June 07

Project name:  	Landscape analysis – explanations of landscape variation in upland landscapes in the MDB

Abbreviated title: 	Landscape Analysis

Type of project:	Centre

Program:  		P4

Themes:  		Salinity and regolith mapping

Project Leader:  	Colin Pain

Start date and duration:  1 July 2007 – 1 year

Participants:	 	GA, ANU

Brief project description:

Knowledge to date

The focus of this project in the final year of LEME is to synthesise results from various projects to maximize the learnings on landscape characterization and evolution, particularly in the Murray-Darling Basin. This work will:

- Provide a basis for extrapolation from small to large catchments in eastern Australia

- Develop regolith and bedrock models, including ages, to understand catchment and salinity processes at different scales.

- Continue analyses of samples collected during the 06-07 year. This will continue cosmogenic isotope work to assess rates of erosion on different landscape positions. This in turn will be used to support earlier work by John Wilford that relates radiometric signatures to the degree of weathering I different landscape types in the upland areas of the Murray Darling Basin. There is also a student honours project being carried out on a similar topic in the same area.

- Following a review carried out to assess the translation of P4 project results to the national/international peer-reviewed literature, this project allows for minor targeted geochronology and geochemical work to bring results to an appropriate standard for publication in peer-reviewed journals, and to provide a firm scientific basis for knowledge and technology transfer.

- The Physiographic Regions project in P1 developed the criteria for upper level mapping related to soils and regolith in the Australian Soil Resources Information System (ASRIS). The Landscape Analysis project will use the ASRIS mapping hierarchy together with an understanding of regolith and landforms and how they have evolved to develop an understanding of the landscapes that will allow us to more confidently predict regolith distribution.

- Following from point 5, Catchment Management Authorities in NSW work on a three-tiered system of land subdivisions, from large to small: Groundwater Flow Systems (GFS), Hydrogeomorphic Units (HGU), and Land Management Units (LMU). Our studies in Victoria, as part of the MDBC project, in the Bet Bet and Loden Catchments in Victoria will feed into the Landscape Analysis project described here to provide a firm descriptive and evolutionary framework for CMAs.

Outputs

- A legacy report (with database and GIS) that compiles all available K/Ar and Ar/Ar age dates and OSL age dates for the Cenozoic in Eastern Australia (Preliminary work has identified over 1400 previously unpublished data points).

- A legacy report that sets out the methodologies, the scientific background, and example maps for landscape analysis in Eastern Australia.

- Demonstration products in support of salinity management interventions at sub-catchment or whole-of-catchment scales

- A workshop on results will be presented to the Australia New Zealand Geomorphology Group meeting in February 2008 to release products and test the science against a leading peer group of geomorphologists.

- Note – this project links to the DEM Volume legacy product- A special issue of the International Journal of Remote Sensing is being prepared; many of the papers are outcomes from, and will provide peer-reviewed background to, the results obtained from this project.

Outcomes

Demonstration of the value to salinity management of advances in understanding of:

- Controls on regolith distribution and variability within catchments in eastern Australia.

- Sources of signals received by gamma ray instruments and presented on radiometric images (key to moving towards production of 3D soil and recharge maps).

- The 3D variability of materials in small and large catchments and its influence on salt storage and mobility.

- Significantly improved regional natural resource management tools;

- Demonstration of methods of extrapolation using a hierarchical mapping system.

Impacts

- Better understanding by CMAs of the importance and scale of landform and regolith for NRM, initially the management of salinity

- Ability to consider whole-of-catchment management options.

- Increased confidence in modelling results.

Milestones: (dates of significant events marking scientific progress)

December 2007 	preliminary report on dating of landscape evolution in the upland areas of the MDB.

March 2008 	preliminary report presenting information on approaches to dealing with different landscape scales.

February 2008	Workshop at ANZGG

Note: Payment of all monies will be at end March 2008, upon completion of the above milestones

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO/ Exec:

Date approved by Board:

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| John Wilford | IK |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Dave Gibson | IK |  |  |  |  |  | 0.30 |  |  | 0.30 |
| Colin Pain | IK |  |  |  |  |  | 0.30 |  |  | 0.30 |
| Jeremy James | GA |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Janine Luckman | GA |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Larysa Halas | GA |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Brad Pillans | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| TOTAL |  |  |  |  |  |  | 1.40 |  |  | 1.60 |

PROJECT OPERATING COSTS $K 2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 5 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 5 |  |
| Possible additional external funds (for info) |  |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties. This table will be revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel to run and present workshop at ANZGG |  |  |  |  |  | 5 |  |  | 5 |
| TOTAL |  |  |  |  |  | 5 |  |  | 5 |