Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Ongoing ……YES			New……

Project No:  		4.20				(Issued by LEME Head Office)

Submitted by:	Ken Lawrie

Date submitted: 	April 2007			V3 11.01.08 GK

Project name:  	MDBC-funded projects

Abbreviated title: 	MDBC

Type of project	Industry (operating):

Program:  		4

Themes:  		Salinity and Groundwater Management

Project Leader:  	Overall management Ken Lawrie, with sub-project leader John Wilford

Start date and duration:  March 04- end June 08

Participants:	 	Geoscience Australia, CSIRO, ANU, AU

Brief project description:

This is a co-investment project between MDBC, DPIVic, and CRC LEME, and liked to activities in CRC Salinity. Over the past 3 years, strategic research projects covering 4 key areas of project activity have been carried out. These are:

- Catchment characterisation and management. This activity has focussed on evaluating the value-adding potential of regolith geoscience for salinity management in dryland landscapes. The focus has been on developing value-added GFS approaches, and is linked to evaluation in salinity modelling and investment decision making tools in CRC Salinty.

- Floodplain salinisation processes. Activities include the assessment of the cost-effectiveness of airborne geophysics and regolith-landscape modelling for salinity studies on the Murray Floodplain, and assessment of climate impacts on extent of salinisation.

- In-stream processes. This activity is focussed on demonstrating how geomorphology/sedimentology and sub-surface architecture studies of floodplain environments can assist with understanding salinity processes, as well as contributing to better estimates of surface-groundwater interaction and sub-surface flow paths;

- Salt Interception Investigations. This sub-project was established to assess the value of in-river nanoTEM conductivity mapping to optimise salt interception schemes.

Scientific Deliverables (new scientific advances)

- New methods for mapping and predicting salinity in upland landscapes, and relating these to management actions.

- New products for understanding salinisation processes in floodplain landscapes.

- New insights into floodplain landscapes, surface-groundwater connectivity, and salinity dynamics in floodplain landscapes.

Deliverables to Client (Adoption mechanisms)

- Publication of MDBC ‘Knowledge Series’ publications (listed below) for distribution jointly by MDBC and CRC LEME to clients across the Murray-Darling Basin (relevant more broadly).

- Organise and run regional workshops on the value-adding potential of the new GFS methodologies. Target audience is CMAs (and Irrigation cooperatives for AEM products)

- Publication of maps and digital data through web-interface on LEME website.

- Stand-alone products (digital) of value-added GFS constructs (for sub-catchment scale use)

- Incorporation of LEME products as data layers or 3D constructs into hydrogeological and NRM planning models and tools.

- Reports, knowledge transfer workshops and on-line materials.

- Joint workshops with CRC Salinity to assess the uptake of P4 research into CRCFFI.

Impacts

- Improved salinity predictions in upland landscapes.

- Improved salinity, groundwater and surface water management in floodplain landscapes

- Input into salinity interception scheme and disposal basin design.

- Uptake of LEME products will be greatly aided by partnering with MDBC to disseminate products tailored for a specific audience (eg CMAs and NRM managers more generally).

- Participation in MDBC-facilitated workshop on GFS methodologies should also be of great benefit in science adoption with key peer and clients groups.

Milestones: (dates of significant events marking scientific progress)

- Key publications will include 3 ‘Knowledge Series’ publications to be produced as MDBC badged reports (co-badged with LEME). Drafts of the specific products, listed below, are all to be completed by end December 2007. Reports will be reviewed and edited by MDBC, and finalised for release by MDBC at ISF08. The 3 reports are:

- A report on new GFS value-adding methodologies for the MDB (JW, KL, CP, JJ, LH)

- A report summarising in-river nanoTEM geophysics; and comparing and contrasting AEM and in-river technologies (by TJM, KPT, & AF)

- A report summarising the use of AEM geophysics for salinity management in floodplains (by KL, TJM & AF)

- Participate in workshops with CRC Salinity/CRCFFI and regional CMAs by December 2007.

- Finalise all LEME technical reports by end October 2007.

- Prepare workshop on AEM for salinity in floodplains to be held at ISF and regionally by end February 2008.

Note: payment to the core parties for milestones 1-3 will be upon completion by end December 2007.  A sum of $5k each will be held back for payment to CSIRO and GA upon delivery of milestone 4 at ISF in April 2008.

Confidentiality requirements

Reports to be reviewed by clients prior to release.

Date Endorsed by Executive and Approved by CEO

Date Endorsed by the Board:

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Ind | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| John Wilford | IK |  |  |  |  | 0.30 |  |  | 0.30 |
| Ken Lawrie | IK |  |  |  |  | 0.20 |  |  | 0.20 |
| Jeremy James | GA |  |  |  |  | 0.20 |  |  | 0.20 |
| Larysa Halas | GA |  |  |  |  | 0.20 |  |  | 0.20 |
| K P Tan | GA |  |  |  |  | 0.10 |  |  | 0.10 |
| Colin Pain | IK |  |  |  |  | 0.10 |  |  | 0.10 |
| Tim Munday | IK |  |  |  | 0.15 |  |  |  | 0.15 |
| Andrew Fitzpatrick | Ind (DEM) |  |  |  | 0.3 |  |  |  | 0.30 |
| TOTAL |  |  |  |  | 0.45 | 1.1 |  |  | 1.55 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Camilla Sorenson | Joint student with Monash | PhD |
| Mike Hatch | Adelaide University | PhD |
| Tania Dhu | Adelaide University | PhD |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | Nil |  |
| 06/07 Carry Over | 54.624 |  |
| Committed (definite) external funds | 20.0 | MDBC |
| Total Project Opex | 74.624 |  |
| Possible additional external funds (for info) |  |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CEM | CLW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Technical and Contract Services |  |  |  | 30 |  | 44.624 |  |  |  |
| Total |  |  |  | 30 |  | 44.624 |  |  | 74.624 |