Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		5.03				(Issued by LEME Head Office)

Submitted by:		Ian Roach

Date submitted: 	April 23, 2007			V2 29 May 07 I Roach

Project name:  	Regolith Teaching and Training Materials (version 2)

Abbreviated title: 	Regolith TTM

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		5

Themes:  		Education & Training

Project Leader:  	Ian Roach

Start date and duration:  July 2007

Participants:

AU: Steve Hill, Graham Heinson, John Joseph, David Chittleborough

ANU: Ian Roach, Brad Pillans, John Field, Sue Welch, Bear McPhail

CUT: Mehrooz Aspandiar

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The main emphasis on this project is for the provision of regolith teaching and training materials, used in the delivery of undergraduate, Honours and external client courses, and the provision of the National undergraduate Regolith Geology School.  This includes the writing and presentation of lecture, practical and field-teaching materials; remote sensing and basemap imagery and presentation; undergraduate student mapping and sampling programs; and, logistical support for the above.  The quality of these teaching materials ensures that CRC LEME science is an integral part of teaching courses, particularly within university undergraduate courses and the MTEC shortcourse program.  This project enables for the provision of high-quality teaching materials (i.e. the content) for 2 of the 3 of the major objectives of CRC LEME’s E&T program:

- “Provide workshops, seminars and training courses on regolith geoscience and related disciplines, directed at students, industry, government and institutional professionals”; and,

- “Contribute regolith content to university” courses.

Presently there is a major deficit in the provision of quality teaching materials for regolith geoscience.  This is necessary for the delivery of courses via the core party universities but also for providing materials for other teaching requirements in regolith geoscience.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs:

- Quality teaching content and logistical support for the delivery of under-graduate courses in regolith geoscience at ANU, Adelaide and Curtin, including the NURGS at Fowlers Gap;

- Regolith geoscience and remote sensing digital data package for Fowlers Gap Arid Zone Research Station (first edition).  This will include a compilation of remote sensing, maps and analytical results derived from previous CRC LEME courses at this much utilised regolith teaching site;

- Production of teaching materials to contribute to regolith geoscience text-book.

Publications:

- Roach, I.C. & Hill, S.M. Fowlers Gap Regolith Geoscience Research and Teaching Data Compilation.  Preliminary CD compilation, CRC LEME

- Hill, S.M. & Roach, I.C. Regolith geoscience research and teaching at Fowlers Gap, western NSW.  BHEI conference poster and abstract.

- Roach, I.C. & Hill, S.M. South Sandstone Paddock 1:25k regolith-landform map.  CRC LEME

- Hill, S.M. & Roach, I.C. Connors Paddock 1:25k regolith-landform map. CRC LEME

- Hill, S.M. & Roach, I.C. Regolith geoscience research and teaching at Fowlers Gap, western NSW.  2006 Regolith Symposium refereed abstract.

- Hill, S.M., Roach, I.C. Greenwood, D & Greenwood, D.  Long-term regolith and landscape evolution of the Sandy Creek catchment, WNSW. Geomorphology

Outcomes:

- The legacy of this work includes the increased skill and knowledge in regolith geoscience of graduates in Earth Sciences; continued recruitment of Honours and PhD students; and greater industry skill and knowledge.

- Impressive content for contributions of regolith geoscience to teaching and training courses.

- Production of “industry-ready” graduates with regolith geoscience skills and knowledge.

Milestones: (dates of significant events marking scientific progress)

- July 9-13, 2007: Joint AU/ANU undergraduate regolith geology fieldtrip to Fowlers Gap (SH, IR, GH, JF)

- July – November, 2006: Delivery of teaching materials in undergraduate courses at AU, ANU and CUT (All listed staff)

- September, 2007: publish Sth Sandstone regolith-landform map (IR & SH)

- September, 2007: publish Connors regolith-landform map (SH & IR)

- September 16-22, 2007: AU 3rd year regolith fieldtrip to Murray Basin (SH)

- November final compilation of Fowlers Gap Regolith Geoscience teaching materials CD (IR & SH)

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hill, Steve |  |  | 0.25 |  |  |  |  |  |  | 0.25 |
| Roach, Ian |  | 0.25 |  |  |  |  |  |  |  | 0.25 |
| Heinson, Graham |  |  | 0.25 |  |  |  |  |  |  | 0.25 |
| Chittleborough, David |  |  | 0.2 |  |  |  |  |  |  | 0.2 |
| Field, John |  | 0.1 |  |  |  |  |  |  |  | 0.1 |
| Pillans, Brad |  | 0.2 |  |  |  |  |  |  |  | 0.2 |
| Joseph, John |  | 0.1 |  |  |  |  |  |  |  | 0.1 |
| McPhail, Bear |  | 0.1 |  |  |  |  |  |  |  | 0.1 |
| Welch, Sue |  | 0.1 |  |  |  |  |  |  |  | 0.1 |
| Aspandiar. M |  |  |  | 0.25 |  |  |  |  |  | 0.25 |
| TOTAL |  | 0.65 | 0.9 | 0.25 |  |  |  |  |  | 1.8 |

All LEME STUDENTS contributing to Project 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| all | all | all |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 10 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 10 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Map production | 1 |  |  |  |  |  |  |  | 1 |
| Field courses (travel & accomm) | 1 | 2.5 |  |  |  |  |  |  | 3.5 |
| UG student chemical analyses |  | 3.5 |  |  |  |  |  |  | 3.5 |
| Course notes production | 0.5 | 1.5 |  |  |  |  |  |  | 2 |
| Total | 2.5 | 7.5 |  |  |  |  |  |  | 10 |