Cooperative Research Centre for Landscape Environments and Mineral Exploration

LEME LEGACY PRODUCT

PROJECT SUMMARY				HO-170105

Ongoing ………….			New……YES

Project No:  						(Issued by LEME Head Office)

Submitted by:		Ken Lawrie, Colin Pain

Date submitted: 	April 2006

Project name:  	Placing the use of digital elevation models (DEMs) in a proper geomorphic context- principles and case studies.

Abbreviated title: 	DEMs in their geomorphic context

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		4

Themes:  		Regolith, salinity

Project Leader:  	Colin Pain

Start date and duration:  July 2006- March 2008.

Participants:	 GA. This work will be undertaken in conjunction with convenors of the MODSIM conference series, and will include authors from a number of science agencies.

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

In December 2005 Colin Pain received an invitation to edit a special journal volume of scientific papers based on the use of DEMs for NRM application in Australia. This offer came after he presented a conference paper on this subject at the MODSIM 2005 conference in Melbourne. Planning is progressing, and a special volume of case studies of the use of DEMs in environmental mapping and management is being constructed. This is an opportunity to showcase some important work by LEME in this area (particularly in P4), and it is hoped that by taking leadership in this area LEME can assist with developing awareness of the limitations and benefits of the use of DEMs for environmental mapping and management. Contributions from several LEME staff have been identified. This special volume of peer reviewed papers will be timed for release to coincide with ISF 08.

Specific papers to be written by LEME staff will include:

- Landscape Analysis for Environmental Issues – the Question of Scale (Colin Pain;

- The use of LIDAR DEMs and radiometrics to map regolith landscapes in relatively flat basalt plains (Dave Gibson);

- A new approach to mapping and predicting salinity in upland landscapes (John Wilford and Jeremy James).

Deliverables (outputs) and expected impacts of research (outcomes):

- A special issue of an international geomorphology/remote sensing journal still to be negotiated).

- Workshop materials for incorporation in a workshop on catchment characterisation at ISF08.

Milestones: (dates of significant events marking scientific progress)

- Publication of a special issue of an International Journal by March 2008.

- Incorporation of results in a workshop at ISF 08, March 2008.

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2006-2007

Note this deliverable will involve editing papers from up to a dozen scientists in other agencies, in addition to 3 papers from LEME staff.

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colin Pain |  |  |  |  |  |  | 0.05 |  |  | 0.05 |
| Dave Gibson |  |  |  |  |  |  | 0.05 |  |  | 0.05 |
| John Wilford |  |  |  |  |  |  | 0.05 |  |  | 0.05 |
| TOTAL |  |  |  |  |  |  | 0.15 |  |  | 0.15 |

All LEME STUDENTS contributing to Project 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 2K |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 2K |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Miscellaneous expenses |  |  |  |  |  |  |  |  | 2K |
| Total |  |  |  |  |  |  |  |  | 2K |

Complete indicative resource table for following year if appropriate

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colin Pain |  |  |  |  |  |  | 0.05 |  |  | 0.05 |
| Dave Gibson |  |  |  |  |  |  | 0.05 |  |  | 0.05 |
| TOTAL |  |  |  |  |  |  | 0.1 |  |  | 0.1 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 9K |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 9K |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Preparation of special issue- payment for colour images in journal. |  |  |  |  |  | 4K |  |  | 4K |
| Miscellaneous expenses associated with |  |  |  |  |  | 1K |  |  | 1K |
| Preparation of workshop materials |  |  |  |  |  | 1K |  |  | 1K |
| T/A associated with workshops |  |  |  |  |  | 3K |  |  | 3K |
| TOTAL |  |  |  |  |  |  |  |  | 9K |