Cooperative Research Centre for Landscape Environments and Mineral Exploration

LEME LEGACY PRODUCT

PROJECT SCHEDULE SUMMARY

Ongoing ………		New…… YES….

Project number……………… 			(Issued by LEME Head Office)

Submitted by:		Ken Lawrie & Jon Clarke

Date: 			April 2006

Project name: 	International Association of Sedimentologists Special Publication on Australian Cainozoic Cratonic Basins

Abbreviated title: 	IAS publication

Type of project (Centre or Industry): 	Centre

Program: 		P4

Theme: 		Theme 1, 2

Project Leader:  	Jonathan Clarke

Start date and duration:  January 2006, will run for 2 years (release date March 2008)

Partners: International Association of Sedimentologists (IAS). There are also contributions from scientists within LEME and from many Universities and agencies nationally (and a couple of international contributions).

Brief project description and what is new:

This project aims to compile research into the sedimentology, stratigraphy and regolith geology of Australia’s Cainozoic cratonic basins that has been carried out over the last 10 years.  It has been more than a decade since aspects of this topic formed part of other thematic collections  (GSA Special Publication 18 and IAS Special Publication 27).

Australian Cainozoic Cratonic, Basins include the Murray, Darling, Eyre and Eucla Basins.  These cover a significant fraction of Australia and, in the case of the Murray and Darling Basins, include a significant fraction of Australia’s agricultural regions.  The Murray, Eucla, and Eyre Basins also include a range of sediment –hosted mineral deposits.

The last 1- years have seen a significant number of LEME projects in these basins in programs 1, 2, and 4.  In parallel, there have been many independent studies of the sediments in these basins.  The data obtained in these studies illuminates the Cainozoic history of Australia and is critical in developing robust models for mineral exploration and land management.

The volume aims to this synthesise research to provide a bench mark for further research and application.  This is directly relevant to LEME Research in regolith science, which is directed toward two principle priorities - mineral exploration under cover and environment and land use.

It is planned to release this volume at ISF 08, and to run a workshop to coincide with this event. IAS will produce the hard copy volume, at no cost to CRC LEME, except where the printing of colour pages is required. The provisional list of papers is detailed below:

Publications promised to date include:

| Author | Title |
| --- | --- |
| J Clarke and C Pain | Introduction |
| QUATERNARY LANDSCAPES AND THEIR BASINS |
| D Gibson et al. | The Lachlan river system of western NSW |
| G Nanson | The Channel country and Coopers Creek |
| K Page | Depositional landscapes of the modern Murray river and its tributaries |
| S Lang | Rivers of the eastern edge of Lake Eyre |
| M Bourke | McDonell Ranges rivers and their floodouts |
| P Hesse | Ferminal fluvial deposits of the Macquarie Marshes |
| G Nanson & J Magee | Dune fields of central Australia |
| R Greene et al. | Distribution of parna in Australia from source to deposition |
| A Chivas et al. | A review of Australian salt lakes |
| S Lang et al. | Sedimentology of Lake Eyre |
| TBA | Cool water carbonates of the South Australian Guls |
| A Chivas et al. | Sediments of the Gulf of Carpentaria and its margins |
| David Ryan et al. | Australian Estuaries – characteristics and facies models |
| P Macumber | Groundwater discharge landscapes of the eastern Murray Basin |
| REGOLITH, LANDSCAPE, AND SEDIMENTS OF THE OLDER CAINOZOIC |
| TBA | Regolith landscapes of Australian Cainozoic basins |
| R Langford | The architecture of Australian Cainozoic basins |
| TBA | Depositional landscapes of the Yigarn Craton |
| TBA | Upland depositional landscapes of eastern Australia |
| Hill | Indurated depositional landscapes of the Curnomona region |
| R Chan & D Gibson | Gilmore palaeodrainages |
| TBA | Cainozoic marine sediments of the Murray Basin – a review |
| R Chan | Evolution of the Giliambone depositional landscape |
| T Payenberg & J Clarke | Cainozoic sediments of the upper Darling basin |
| N Alley | The Cainozoic evolution of the Lake Eyre Basin |
| Worral, Hou et al. | The Eocene shoreline of the Eucla Basin |
| A Chivas et al | Cainozoic evolution of the Karumba Basin |
| TP Tan | Characterisation of deeply weathered sediments of central-western NSW |
| J Kellett et al | The architecture of the Murumbidgee Fan |
| AUSTRALIAN CAINZOIC BASINS IN A GLOBAL CONTEXT |
| J-J Tiercelin | Cainozoic basins of Africa |
| F Guilloceau | The Paris Basin, similarities and differences to Australian Cainozoic basins |
| TBA | North American Cainozoic basins from an Australian perspective |
| TBA | The depositional architecture of the Amazon Basin |

Deliverables and expected outcomes:

- IAS special publication volume.  This volume, expected to be at least 300-400 pages will be a bench mark publication of the 2006 understanding of Australian Cainozoic cratonic basins. There is a proposal to call this the ‘Campbell Brown Memorial Volume’ in memory of the ex-BMR geologist who (with Tony Stephenson) made a significant contribution to the geology of the Murray Basin (benchmark publication BMR Bulletin 235– Geology of the Murray Basin, 1991), and who died tragically during fieldwork. To be released at ISF 08.

- Workshop of Australia’s Cainozoic Basins, and the significance of this for environmental applications (eg aquifer systems etc). To coincide with ISF 08.

Milestones

Task	Period

- Enquires with IAS	Jan 05-July 05

- Expressions of interest	July 05

- Approval from IAS	December 05

- Call for papers	Jan 06

- Deadline for draft submission	February 07

- Deadline for completion of reviews	June 07

- Final submission to publishers	September 07

- Release of publication (at ISF) 2008 	March 2008

- Workshop (Cainozoic basins and GFS) at ISF 08	March 08

Confidentiality requirements   Nil

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Ind | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Jon Clarke | Ind |  |  |  |  |  | 0.05 |  |  | 0.05 |
| Colin Pain | IK |  |  |  |  |  | 0.05 |  |  | 0.05 |
| Dave Gibson | IK |  |  |  |  |  | 0.05 |  |  | 0.05 |
| Richard Greene | IK | 0.05 |  |  |  |  |  |  |  | 0.05 |
| Lisa Worrall | IK |  |  |  |  |  | 0.05 |  |  | 0.05 |
| Steve Hill | CRC |  | 0.05 |  |  |  |  |  |  | 0.05 |
| TOTAL |  | 0.05 | 0.05 |  |  |  | 0.2 |  |  | 0.3 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 2 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 2 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Miscellaneous expenditure- postage, printing charges etc |  |  |  |  |  |  |  |  | 2 |
| TOTAL |  |  |  |  |  |  |  |  | 2 |

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Ind | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Jon Clarke |  |  |  |  |  |  | 0.05 |  |  | 0.05 |
| Colin Pain |  |  |  |  |  |  | 0.05 |  |  | 0.05 |
| TOTAL |  |  |  |  |  |  | 0.1 |  |  | 0.1 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 10k |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 10k |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T/A for workshop at ISF08 |  |  |  |  |  | 4 |  |  | 4 |
| Preparation of workshop materials |  |  |  |  |  | 1 |  |  | 1 |
| Colour printing of key diagrams in IAS volume |  |  |  |  |  | 5 |  |  | 5 |
| TOTAL |  |  |  |  |  | 10 |  |  | 10 |