Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SCHEDULE SUMMARY

Project number……………… (Issued by LEME Head Office)

Submitted by:		Keith Scott

Date: 			April 11

Project name: 	Regolith Textbook

Abbreviated title: 	Regolith Textbook

Type of project 	(Centre or Industry): Centre

Program: Communications - Head Office

Theme:

Project Leader:  Keith Scott

Start date and duration:  July 2006 – end of LEME.

Partners: CSIRO Publishing

Brief project description and what is new:

The book will be a compilation and distillation of work over the past 10 years in LEME 1 and LEME 2 on regolith science.  There are two other textbooks on regolith (Ollier and Pain – Regolith, Soils and Landforms; Taylor and Eggleton – Regolith Geology and Geomorphology). This new book will build on these, and will be aimed at senior university students as well as practitioners in both MINEX and NRM. Details of topics and chapter headings have yet to be finalized. The work will be multi-authored, and edited by Keith Scott and Colin Pain.

Deliverables and expected outcomes:

We have approached CSIRO Publishing with a view to having them publish the book. Details have yet to be finalized.

Milestones:

Invitation to potential authors	May 2006

Deadline for submissions	October 2006

Reviewing	November 2006 – March 2007

Revisions by authors	April 2007 – June 2007

Submission to Publishers	August 2007

Proofs	December 2007

Publication	March 2008

Date submitted to Executive:

Date approved by CEO:

Date approved by Board:

RESOURCES

Staffing

| Year | Contractor | Core Party | Total |
| --- | --- | --- | --- |
| 2006 | CSIRO (10%) | GA (5%) | 15% |
| 2007 | CSIRO (10%) | GA (5%) | 15 |
| Staff | Name | Name |  |
|  | Keith Scott | Colin Pain |  |

Various LEME staff, and perhaps others, will contribute chapters and sections to the book. This has yet to be finalized.

Funding  (All figures in $K)

| Year | CRC LEME |  |
| --- | --- | --- |
|  | Operating Cash | Salaries | Participant | Totals |
| 2006 | $5000 | $15,000 | CSIRO | $15,000 |
| 2007 | $5000 | $15,000 | CSIRO | $15,000 |
| Totals | $10,000 | $30,000 |  | $40,000 |

External funding: None

Total funding over 2 years:   $40,000

Confidentiality requirements: None

Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SCHEDULE

1.	INTRODUCTION

The book will be a compilation and distillation of work over the past 10 years in LEME 1 and LEME 2 on regolith science.  There are two other textbooks on regolith (Ollier and Pain – Regolith, Soils and Landforms; Taylor and Eggleton – Regolith Geology and Geomorphology). This new book will build on these, and will be aimed at senior university students as well as practitioners in both MINEX and NRM. Details of topics and chapter headings have yet to be finalized. The work will be multi-authored, and edited by Keith Scott and Colin Pain.

2.	OBJECTIVES

### 2.1	Principal objective

Publication of the volume

  - Specific Objectives

Submission of completed papers in time for publication by the end of LEME

- PARTICIPANTS

GA, CSIRO

4.	SCOPE

Summary of regolith science as at 2007.

5.	STRATEGY, APPROACH

Approach authors to submit chapters or part chapters.  These will undergo peer review to international standard.

- POTENTIAL OUTCOMES, DELIVERABLES

Text book on regolith science

6.2	Links to other Programs or Sub-Programs in terms of outputs / outcomes

Relevant to all of LEME.

- STAFFING  (add or delete rows or columns  as required)

| Name | Participant Location | Expertise | % Time Year 1 | % Time Year 2 | % Time Year 3 |
| --- | --- | --- | --- | --- | --- |
| Keith Scott | CSIRO | Geochemistry | 20 | 20 | N/A |
| Colin Pain | GA | Geomorphology | 5 | 5 | N/A |
| Others as required | Various |  |  |  |

8.	BUDGET

8.1	Project Costs (shown in budget spreadsheet)

8.2	Capital Items (shown in budget spreadsheet)

8.3	Centre resources (add or delete rows as required)

| Year | Salaries | Operating | Total |
| --- | --- | --- | --- |
| 1 | $15,000 | $5000 | $20,000 |
| 2 | $15,000 | $5000 | $20,000 |

8.4	Contributions from each of the Project Participants (other than staffing):

Nil

8.5	Other funding sources: Nil

8.6	Project fee to be paid to each of the Project Participants by the Centre:

(add or delete rows as required)

| Participant | Year 1 | Year 2 |
| --- | --- | --- |
| CSIRO | $17,500 | $17,500 |
| GA | $2500 | $2500 |

8.7	Research fee to be paid by Industry Participants: Nil

9.	STUDENT INVOLVEMENT

Nil

10.	WORK PLAN

10.1	General

Approach authors, who will submit papers.  These will undergo peer review to international standards.

10.2	Specific  (add or delete rows as required)

| Task | Period | Staff |
| --- | --- | --- |
| Invitation to potential authors | June 2006 | Scott, Pain |
| Deadline for submissions | October 2006 | Scott, Pain |
| Reviewing | November 2006 – March 2007 | Scott, Pain |
| Revisions by authors | April 2007 – June 2007 | Scott, Pain |
| Submission to Publishers | August 2007 | Scott, Pain |
| Proofs | December 2007 | Scott, Pain |
| Publication | March 2008 | Scott, Pain |

11.	MILESTONES AND REVIEW DATES

See 10.2

12.	CONFIDENTIALITY REQUIREMENTS

Nil