Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		1.21			(Issued by LEME Head Office)

Submitted by:		Colin Pain

Date submitted: 	21/04/06		V2  Updated SG/JM 20.9.06

Project name:  	Physiographic regions of Australia

Abbreviated title: 	Physiographic regions

Type of project	Industry		(Centre or Industry/Commercial

Program:  		One

Themes:  		1. Understanding of regolith processes

2. Models of regolith landscape evolution

Project Leader:  	Colin Pain

Start date and duration:  01/07/05 – 30/06/07

Participants:	 	Geoscience Australia, ACLEP

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

In 2005/2006 the Australian Collaborative Land Evaluation Program (ACLEP) provided funding to LEME for the preparation of a national map of physiographic regions. A first draft of this map will be completed by the end of June 2006. We have now approached ACLEP for further funding to enhance regolith information, and have been successful in getting $15,000. The new objective is to assess the complexity of each physiographic region in the present coverage, and where necessary compile new more detailed line work so that each polygon has a similar level of complexity. Where appropriate we will use data from other LEME projects.

There will also be a report. The map of physiographic regions of North America (1940) was accompanied by a 520-page book. The original map of physiographic regions of Australia (1977) appeared in a 15-page chapter in a book on the geography of Australia. We envisage something in between.

The project contributes to LEME’s strategic intent by providing a basis for the regional description and explanation of the Australian regolith. It also provides a firm basis on which to extrapolate results obtained from studies of detailed areas to surrounding areas at lower resolution. In particular the project will work with P4 projects in the Murray-Darling Basin.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Revised map of physiographic regions (produced in 05/06) with new more detailed line work so that each polygon has a similar level of complexity.

- Attribute descriptions (landform, relief, and substrate materials) for the new polygons in revised map.

- Report to accompany the new map of physiographic regions of Australia.

Outcomes

National framework which will support extrapolation between more regional (detailed) studies.

Milestones: (dates of significant events marking scientific progress)

Sep 06 	Progress report to ACLEP

Dec 06 	Progress report to LEME executive

Jun 07 		Final line work and attributes for map

Jun 07 		Draft of report ready for printing

Confidentiality requirements

None

Date Endorsed by Executive and Approved by CEO;	23.6.06

Date Endorsed by the Board:					29.6.06

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colin Pain | In-kind |  |  |  |  |  | 0.20 |  |  | 0.20 |
| TOTAL |  |  |  |  |  |  |  |  |  | 0.20 |

All LEME STUDENTS contributing to Project 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested |  |  |
| Committed (definite) external funds | 15 | ACLEP |
| CARRY OVER FROM 05-06 | 6,719 |  |
| Total Project Opex | 21,719 |  |

Note: Carryover amount to be confirmed.

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GIS/map preparation |  |  |  |  |  |  |  |  |  |
| Travel |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  | 21,719 |  |  | 21,719 |

Note: The final budget will be determined once the carryover figure is known at the end of the 05/06 financial year.

# Comments

No CRC opex funds are requested – the carry over is unspent external funds from ACLEP.