Cooperative Research Centre for Landscape Environments and Mineral Exploration

COMMERCIAL PROJECTS

PROJECT SUMMARY				HO-170105

Project No:  		1.36				(Issued by LEME Head Office)

Submitted by:		Mike Craig

Date submitted: 	21/04/ 06			V2  Updated SG/JM 20.9.06

Project name:  	Queensland Regolith Map

Abbreviated title: 	Queensland Regolith Map

Type of project:	Commercial 			(Centre or Industry/Commercial)

Program:  		One

Themes:  		1. Understanding of regolith processes

2. Models of regolith landscape evolution

Project Leader:  	Mike Craig

Start date and duration:  01/07/06 – 30/06/08

Participants:	 	GA, Geological Survey of Queensland (GSQ)

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

This project provides a regional regolith-landform framework of Queensland for mineral exploration and land management and extends work carried out in conjunction with the NTGS during the period 2003-2006.

The Australian regolith is a product of weathering, erosion, deposition and chemical transformation.  In tropical and arid environments of Queensland, these processes are reflected in the landforms, desert sands and loams, internal and external drainage systems, and ancient weathering surfaces that we see today through various forms of remotely sensed imagery.

A Regolith Landform Map of Australia (1:5Million) was produced in 1984.  This map showed some major alluvial-colluvial systems, and some major areas of ferruginous duricrust but did not adequately address the question of the evolution of land surfaces and regolith materials.  Since, there has been considerable advances in understanding regolith processes in the Cratonic regions of Australia.  In addition there is now a wealth of new data provided by Second Edition geological mapping, Landsat 7, DTM and radiometric data from high-resolution airborne surveys, and drill data from mineral exploration.

A regional regolith study of Cape York Peninsula was conducted under the auspices of the Cape York Land Use Study (CYPLUS) by AGSO/CRC LEME in 1995.  The study was based on detailed surface observations and regolith information including extracted from remotely sensed imagery. Local scale regolith assessments formed part of detailed studies conducted by CRC LEME as part of AMIRA project activities in the Mt Isa Region of Queensland. The Geological Survey of Queensland has also conducted some detailed local regolith-related studies that are of significance and are available to the project and will help reach the goals of this proposed project.

In 2006, CRC LEME in collaboration with the Northern Territory Geological Survey addressed the need for a wider regional regolith framework by completing the first whole of State (Northern Territory) Regolith Map and Atlas of regolith materials. This excellent regional dataset and QLD’s existing detailed datasets coupled with supplementary detailed studies across Queensland could now provide an extended basis for constructing a regional regolith-landform framework for the entire “Top End” of Australia.

An understanding of the regolith is now acknowledged by industry as necessary for effective mineral exploration. The Queensland Regolith Map is the second step necessary to developing a national regional map which is in itself is fundamental to understanding landscape evolution, extractive and placer mineral occurrences, groundwater potential, rangeland management, and environmental geoscience across Australia.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Regolith-landform map (1:2.5 Million scale) of Queensland, as a companion to the recently completed Northern Territory Regolith Map.

- An Atlas of Regolith Materials of Queensland.

Outcomes

- Significant progress towards a national regolith map.

Milestones: (dates of significant events marking scientific progress)

Aug 06		Scoping document, budget and agreed work-plan.

Dec 06		Compilation of existing relevant datasets

Mar 07		Trans Qld Regolith Traverse and Selection of key areas for supplementary

work

Jul  07		Major field data collection

Nov 08		Preliminary data assemblages for Map

Nov 08		Preliminary data analyses for  Atlas of QLD Regolith Materials, progress

presentations.

Feb 08		Draft Regional regolith-landform map

Feb 08		Draft Atlas of QLD Regolith Materials,

Apr 08		Final Drafts of outputs, Synthesis report and scientific publications in

national/international journals/conference presentations.

Jun 08		Product delivery

Confidentiality requirements: None

Date submitted to Executive:

Date approved by CEO/Exec:		23.6.06

Date approved by Board:		29.6.06

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | GSQ | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M Craig | In Kind |  |  |  |  | 1.00 |  |  |  | 1.00 |

Malcolm Jones - IK GSQ 1.00,   GIS Support Officer GA 0.60

All LEME STUDENTS contributing to Project 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 0 |  |
| Committed (definite) external funds | $103,396 | GA/GSQ |
| Total Project Opex | $103,396 |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties – Estimates only

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIR SA | GSQ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Palaeomagnetic dating |  |  |  |  |  |  |  |  |  |  |
| Atlas |  |  |  |  |  |  |  |  |  |  |
| Map production/GIS |  |  |  |  |  |  |  |  |  |  |
| Petrographics/ geochem/probe/sem |  |  |  |  |  |  |  |  |  |  |
| Reproduction costs-docs photos |  |  |  |  |  |  |  |  |  |  |
| Travel |  |  |  |  |  |  |  |  |  |  |
| GIS Support |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  | 103,396 |  |  |  | 103,396 |