Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		1.34				(Issued by LEME Head Office)

Submitted by:		John Greenfield

Date submitted: 	April 21st 2006		V2 Updated LW/SG/JM 20.9.06

Project name:  	Exploration through cover in the Thomson Orogen

Abbreviated title: 	NSW Thomson Orogen Project

Type of project	Centre/Industry	(Centre or Industry/Commercial):

Program:  		One

Themes:  		1. Understanding regolith processes

2. Models of regolith landscape evolution

4. Regional mineral exploration studies

5. Making geochemistry more effective

Project Leader:  	John Greenfield

Start date and duration:  01/07/05 - 30/06/08

Participants:	 	GA, NSW DPI, ANU, AU

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The Thomson Orogen, which underlies the Channel Country in northwest New South Wales, is one of the last major greenfield terrains in NSW.  The NSW DPI plans to make this terrain the focus of a new Exploration Initiative.  The Thomson Orogen has potential for arc and ocean-crust related gold and base metal deposits while the area to the south of the Orogen may have potential for Mississippi Valley style zinc deposits.  The prospective units are obscured by Eromanga Basin sediments.  The basin cover presents a significant impediment to exploration.

The primary objective of this project is to lower mineral exploration risk by developing an effective means of exploring through the cover in the Thomson Orogen.  The achievement of this objective will be measured by the increase in exploration investment in the area.

The strategy to achieve these objectives builds on the results of Tibooburra, Curnamona and Cobar-Giralambone Projects (these areas are also under Eromanga Basin cover and Tibooburra is on the western margin of the Thomson Orogen) and has eight elements:

1	Mapping the character and disposition of regolith materials in 3D

2	Developing an understanding of landscape history for the late Mesozoic – Cenozoic, including post-Mesozoic tectonics.

3	Characterising contemporary dispersion processes (physical and chemical; including biogeochemical and electro-chemical processes)

4	Identifying palaeo-dispersion processes

5	Developing an exploration strategy

6	Developing and implementing an effective knowledge transfer and training

7	Tracking results and revising strategies based on experience

This project will have close interaction with the generic process projects in Programs 1, 2 and 3, especially Lachlan Fold Belt, Metal Mobility and Geochemical Baselines Projects respectively.

2006-2007 Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Digital Database and GIS

Initial release in September 2005, updated in January 2006. Version 3 release due February 2007.

- 4 x 1:100k Regolith Maps

Submitted to GSNSW Cartography section in March 2006, and due for publication June 2007.

- LEME Reports

- Publications in national and international journals

- Presentations at national and international conferences

- University theses

Outcomes

- Development of an accurate landscape evolution model and application to mineral exploration beneath cover in the NSW Thomson Orogen

- Increase in exploration investment in the NSW Thomson Orogen

Milestones: (dates of significant events marking scientific progress)

| July | Pay for 176 biogeochem Au analyses from March 06 baseline trip (GA) |
| --- | --- |
| Jul 06 | Tibooburra Fieldwork: Hons and PhD fieldwork, DGPS surveys (Adelaide Uni) |
| Aug 06 | Preliminary biogeochem report (Hulme, includes contract salary) |
| Aug 06 | Geophysical Interpretation of Thomson (NSWDPI) |
| Aug 06 | Submit Warratta Inlier biogeochemistry assays (Adelaide Uni) |
| Sep 06 | Prelim baseline Geochem Report (de Caritat, Lech, Hulme) |
| Sep 06 | Finalize Warratta Inlier Regolith Landform map (Adelaide Uni) |
| Sep 06 | Planning-progress meeting in Canberra |
| Sep 06 | Submit New Bendigo soil and regolith samples for geochemistry assay (AU) |
| Sep 06 | BHEI Conference (S. Hill) |
| Oct 06 | Baseline geochem/biogeochem sampling trip (GA, AU) |
| Oct 06 | Baseline biogeochem sample preparation |
| Oct 06 | Baseline geochem sample preparation |
| Nov 06 | Completion of McAvaney & Tucker Hons |
| Nov 06 | Regolith Symposium 2006, Hahndorf |
| Dec 06 | Baseline geochem sample submission |
| Mar 06 | Tibooburra fieldwork (Adelaide Uni) |
| Jun 06 | Public release of four 100k Regolith sheets |
| Jun 06 | Geochronology analysis and results (ANU) |

Confidentiality requirements

None at this stage

Date submitted to Executive:

Date approved by CEO/Exec:		23.6.06

Date approved by Board		29.6.06

RESOURCES 2006-2007

STAFFING-FTEs

| Staff Name | In-kind, CRC or Industry | ANU | AU | GA | NSW DPI | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Ken McQueen | CRC | 0.55 |  |  |  | 0.55 |
| Ian Roach | CRC | 0.15 |  |  |  | 0.15 |
| Steve Hill | CRC |  | 0.15 |  |  | 0.15 |
| Karen Hulme | IK |  | - |  |  |  |
| Lisa Worrall | IK |  |  | 0.10 |  | 0.10 |
| Patrice de Caritat | CRC |  |  | 0.25 |  | 0.25 |
| Amy Kernich |  |  |  | - |  |  |
| Megan Lech |  |  |  | - |  |  |
| GA tech (TBC) |  |  |  | - |  |  |
| Bob Brown | IK |  |  |  | 0.25 | 0.25 |
| Nancy Vickery | IK |  |  |  | 0.25 | 0.25 |
| John Watkins | IK |  |  |  | 0.10 | 0.10 |
| Mike Healy | IK |  |  |  | 0.30 | 0.30 |
| Bob Musgrave | IK |  |  |  | 0.20 | 0.20 |
| Cobar Geo (TBC) | IK |  |  |  | 0.20 | 0.20 |
| John Greenfield | IK |  |  |  | 0.30 | 0.30 |
| Bill Reid | IK |  |  |  | 0.95 | 0.95 |
| Kingsley Mills | IK |  |  |  | 0.20 | 0.20 |
| Dick Glen | IK |  |  |  | 0.20 | 0.20 |
| SteveTrigg | IK |  |  |  | 0.20 | 0.20 |
| Gary Burton | IK |  |  |  | 0.20 | 0.20 |
| Mark Dawson | IK |  |  |  | 0.30 | 0.30 |
| Phil Gilmore | IK |  |  |  | 0.25 | 0.25 |
| TOTAL |  | 0.70 | 0.15 | 0.35 | 3.9 | 5.10 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Jesse Davey | Adelaide | PhD |
| Robert Dart | Adelaide | PhD |
| Layla Tucker | Adelaide | BSc (Hons) |
| Dave McAveny | Adelaide | BSc (Hons) |
| TBC | ANU | BSc (Hons) |

PROJECT OPERATING COSTS ($K) 2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 107 |  |
| Committed (definite) external funds |  |  |
| Committed In Kind | 616* | GA, NSWDPI, MMI |
| Total Project Opex | 107 |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

| Expenditure Item | ANU | AU | GA | NSW DPI | Total |
| --- | --- | --- | --- | --- | --- |
| Field costs incl travel |  |  |  |  |  |
| Vehicle hire and expenses |  |  |  |  |  |
| Incidentals |  |  |  |  |  |
| Equipment hire |  |  |  |  |  |
| Freight |  |  |  |  |  |
| Geochem/geochron analyses |  |  |  |  |  |
| Sample prep |  |  |  |  |  |
| Drafting and report production |  |  |  |  |  |
| Total | 41 | 30 | 36 |  | 107 |

*GA is providing XRF, ICP-MS and XRD analyses as in-kind support.  The value of this support is approx $25K. NSW DPI is providing $475k as operating to DPI staff.  A further estimated $22k will be provided by NSWDPI as in-kind logistical support via travel ($5k), field vehicles/fuel ($5k), freight ($2k) and publishing ($10k).  MMI Technologies is providing free sample preparation and analyses (performed by ALS Chemex) for approximately 100 samples valued at $5k.