Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		2.29				(Issued by LEME Head Office)

Submitted by:		Matthias Cornelius

Date submitted: 	24 March 2006		V2 Updated SG/JM 20.9.06

Project name:  	The Development of a Laterite Geochemical Map of the Western   Yilgarn Craton

Abbreviated title: 	Laterite Atlas

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		Two

Themes:  		Themes 4 & 5

Project Leader:  	Matthias Cornelius (and Paul Morris, GSWA)

Start date and duration:  July 2003; 4 years

Participants:	 	Matthias Cornelius, Ian Robertson, Charles Butt, Amanda Cornelius, Andrew Hacket

Brief project description: The project is aimed at establishing a geochemical atlas for the Western Yilgarn Craton, using lateritic residuum, lag derived from lateritic residuum and lateritic detritus from colluvium. The overall objective of a geochemical atlas is to identify major new geochemical trends and provinces, both in residual and in depositional terrains, that could assist exploration and lead to the discovery of new mineral deposits.  The project is in collaboration with the Geological Survey of Western Australia and MERIWA.

To date, approximately 2000 samples from the southwest quadrant of the Yilgarn Craton have been analysed and results have been published as CRC LEME OFR201 in March 2006.

In 2006, sampling will continue in the NW quadrant and a number of laterite samples from previous CSIRO and CRC LEME studies, representing different styles of mineralization and different commodities, and different bedrock types, e.g., from Golden Grove, Boddington, Mt Gibson, Lawlers, Ora Banda, Beasley Creek, will also be included for analysis to provide target data sets for statistical evaluation using multivariate analysis.  Representative samples from various parts of the western Yilgarn and samples both with an unusual and a typical geochemical composition will undergo mineralogical investigation.

Deliverables (outputs) and expected impacts of research (outcomes):

- Collect approximately 700 samples in the northwestern Yilgarn and analyse using ICP-MS and XRF.

- Produce imaged concentration maps for 53 elements.

- Correlate geochemistry with major lithological bedrock units and structural features.

- Identify major new geochemical trends and provinces.

- Calculate exploration indices, e.g., CHI and PEG (after Smith and Perdrix).

- Calculate summary statistics.

- Provide quality control.

- Characterize the mineralogy and fabric of representative samples.

- Link data to company data sets (e.g., Dominion Mining) and establish projects with industry partners to follow-up specific trends or anomalies

Milestones: (dates of significant events marking scientific progress)

October 2006 – Complete all sampling including helicopter work (subject to sufficient field support staff)

April/May 2007 – Final project report (GSWA Record/MERIWA Final Report) and release of all data into the public domain

September 2007 – Present results at the IGES in Spain

December 2007 – Submit draft paper to an international journal (GEEA?)

Confidentiality requirements

There is no confidentiality requirement post release of the final report.

Date submitted to Executive:

Date approved by CEO/Exec:		23.6.06

Date approved by Board:		29.7.06

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Matthias Cornelius | In-kind |  |  |  | 0.50 |  |  |  |  |  |
| Ian Robertson | In-kind |  |  |  | 0.50 |  |  |  |  |  |
| Amanda Cornelius | CRC |  |  |  | 0.20 |  |  |  |  |  |
| Charles Butt | In-kind |  |  |  | 0.05 |  |  |  |  |  |
| TOTAL |  |  |  |  | 1.25 |  |  |  |  | 1.25 |

All LEME STUDENTS contributing to Project

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 8,000 |  |
| Committed (definite) external funds | 47,309 | MERIWA - Carry Over |
| Total Project Opex | 55,309 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Final report |  |  |  |  |  |  |  |  |  |
| Microprobe and TS |  |  |  |  |  |  |  |  |  |
| Analyses |  |  |  |  |  |  |  |  |  |
| Total |  |  |  | 55,309 |  |  |  |  | 55,309 |

NOTE:

Due to delays in the completion of sampling in the NW Yilgarn, a significant part of the sampling and analytical work will have to be undertaken during the second half of 2006.  Consequently, project funds in the order of $90k will have to be carried over into FY 06/07.  A more accurate estimate of the carry over will be provided in May/June.