Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		2.43				(Issued by LEME Head Office)

Submitted by:		Dr A.J Mauger

Date submitted: 	10 April 2006			V2  Updated SG/JM 20.9.06

Project name:  	Minerals, lithologies and structural mapping using integrated techniques, incorporating hyperspectral, airborne EM, radiometrics, magnetics and gravity of regolith covered basement terrains (Olary District, Gawler Craton, Musgrave Block and Adelaide Geosyncline, South Australia)

Abbreviated title: 	Mineral Mapping South Australia

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		2

Themes:  		Regional exploration studies, Geophysical mapping and modelling, Making geochemistry work in areas of cover, Regolith processes

Project Leader:  	Dr AJ Mauger

Start date and duration:  2001-2008

Participants:	 PIRSA, CRC LEME, University of Adelaide

Brief project description: (in no more than 400 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects, contribution to strategic intent.)

Relating mineralogy to the development, identification, characterisation and measurement of the regolith with the aim of establishing successful mineral exploration vectors using spectrally active minerals in covered terrain constitutes the core of this project.  Utilising spectral geology at all scales of observation (hand specimen, drill core, airborne and space-borne) integrated with other geoscientific datasets, including regolith, geomorphological and geological mapping (“ground truthing”), the distribution and characteristics of different regolith units and their processes of formation from the various basement lithotypes will be identified. New aspects of the project include demonstration of new equipment (CSIRO HyLogger) and new techniques for the analysis of new datasets (in particular hyperspectral and multispectral remote sensing data such as HyMap, Hyperion and ASTER), integration and analysis of multiple datasets.

Particular project areas to come under the umbrella of this project include:

- Gibraltar, north-west of Tarcoola. Proterozoic acid volcanics with a superimposed Jurassic palaeodrainage system.

- Tarcoola Ridge. Examining in situ development of regolith over a known gold deposit and its associated alteration system. Use of CSIRO Automated Core Logger to map 3D distribution of spectrally active minerals.

- Beltana/Aroona/Reliance carbonate hosted willemite deposits. Examining mineral alteration vectors to a known deposit concealed by transported regolith

- White Dam, Olary Domain. Characterising regolith mineral expression of a known deposit to enable predictive exploration using hyperspectral data

- Central Gawler Gold, ASTER image analysis. Use of CSIRO HyLogger to characterise the alteration system associated with Proterozoic gold-only mineralisation.

- Pine Creek kimberlite province. Documenting the spectrally visible mineral expression of regolith covering known kimberlites.

Deliverables (outputs) and expected impacts of research (outcomes):

- Synthesis of case studies conducted over SA

- New models for “seeing” bedrock through cover in SA basement areas

- New models establishing mineral relationships from bedrock to surface
-    Accurate mapping of previously unrecognised saprolite at the surface
-    Prediction tools for mineral exploration
-    Training of students in regolith studies, geophysics, mapping

Milestones: (dates of significant events marking scientific progress)

2001:	Project commenced

March 2002:	HyMap Surveys: Beltana, Pine Creek.

May 2002:	5th International Airborne Remote Sensing Conference, Miami

July 2002:	16th AGC, Adelaide

September 2002:	11th ARSPC, Brisbane

September 2002:	2nd Geological Hyperspectral Focus Grp, North Flinders Ranges

November 2002:	Honours Thesis on use of Hyperion over Tarcoola

January 2003:	Project review

September 2003:	ASTER Mini-Conference

November 2003:	Honours Thesis on Beltana

January 2004:	Complete acquisition HyLogger Phase one

July 2004:	PhD Thesis on White Dam

May-Dec 2004:	Supporting XRD & SEM analytical work for HyLogger Phase one

October 2004:	12th Australasian Remote Sensing Conference

January 2005:	Complete acquisition HyLogger Phase two

Feb-Dec 2005:	Supporting XRD & SEM analytical work for HyLogger Phase two

May 2006	Paper in IMMTrans

July 2006	Australian Earth Sciences Convention 2006

July-Sept 2006:	Supporting XRD & SEM analytical work

June 2008:	Compendium on use of Spectral Geology in Mineral Exploration through the Regolith: South Australian case studies.

Progress will be reviewed quarterly with sponsor reports on demand.  Papers will be prepared for periodic conferences as appropriate.

Confidentiality requirements:  Nil

Date submitted to Executive:

Date approved by CEO/Exec:			23.6.06

Date approved by Board:	 		29.6.06

RESOURCES

Staffing  FTEs   (eg 0.50)  for 2006-2007

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| J Keeling | In Kind |  |  |  |  |  |  | 0.20 | 0.20 |
| A Mauger | In Kind |  |  |  |  |  |  | 0.55 | 0.55 |
| V. Stamoulis | In Kind |  |  |  |  |  |  | 0.30 | 0.30 |
| Totals |  |  |  |  |  |  |  | 1.05 | 1.05 |

All LEME Students contributing to Project - 2006 - 2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 20 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 20 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

Ongoing support					$20 ( in-kind)  Funding Source:

PIRSA Operating Budget for Mineral Mapping Group in PIRSA

CRC Operating Expenses - $K - 2006-2007   (show allocation per core party)

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Analytical XRD & SEM |  |  |  |  |  |  | 5 | 5 |
| HyLogger Data Analysis |  |  |  |  |  |  | 5 | 5 |
| Report preparation & poster preparation |  |  |  |  |  |  | 10 | 10 |
|  |  |  |  |  |  |  |  | 20 |

Please complete tables following for ongoing years if project more than 1 year duration, or delete

RESOURCES

Staffing  FTEs   (eg 0.50)  for 2007-2008

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| J Keeling | In Kind |  |  |  |  |  |  | 0.20 | 0.20 |
| A Mauger | In Kind |  |  |  |  |  |  | 0.65 | 0.65 |
| V Stamoulis | In Kind |  |  |  |  |  |  | 0.30 | 0.30 |
| Totals |  |  |  |  |  |  |  | 1.15 | 1.15 |

All LEME Students contributing to Project 2007 - 2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

CRC Operating Expenses - $K - 2007-2008   (show allocation per core party)

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Analytical XRD & SEM |  |  |  |  |  |  | 5 | 5 |
| HyLogger Data Analysis |  |  |  |  |  |  | 5 | 5 |
| Report preparation |  |  |  |  |  |  | 10 | 10 |
|  |  |  |  |  |  |  |  | 20 |

External funding 2007-2008:  			$K

Ongoing support				20

Funding Source:

PIRSA