Cooperative Research Centre for Landscape Environments and Mineral Exploration

Ongoing ……YES (Amalgamation of two existing projects)

PROJECT SUMMARY				HO-170105

Project No:  		4.10

Submitted by:		John Wilford, Colin Pain

Date submitted: 	April 2006			V2  Updated SG/JM 20.9.06

Project name:  	Landscape analysis – explanations of landscape variation in upland landscapes in the MDB

Abbreviated title: 	Landscape Analysis

Type of project:	Centre

Program:  		P4

Themes:  		Salinity and regolith mapping

Project Leader:  	Colin Pain, John Wilford

Start date and duration:  1 July 2006 – 2 years

Participants:	 	GA

Brief project description: (in no more than 500 words address

Knowledge to date

Projects under way in 05/06 have made it clear that different landscapes require different scales of study to provide meaningful results relating to salt movement. This project will take the understanding gained from the externally funded projects (MDBC and Central West CMA), and extend it by developing a framework for extrapolation of results from detailed studies to broad areas. This framework for the study area will be based on:

- A description of the variation of landscapes.

- A collation of work to date on landscape evolution

- An explanation of landscape evolution

The Physiographic Regions project in P1 is concerned with developing the criteria for upper level mapping related to soils and regolith in the Australian Soil Resources Information System (ASRIS). In 06/07 we have obtained more funding from ACLEP to provide more regolith information for selected physiographic regions – this will involve subdivision of physiographic regions and an assessment of the landscape scale to determine appropriate scales for detailed work. The Landscape Analysis project will use the ASRIS mapping hierarchy together with an understanding of regolith and landforms and how they have evolved to develop an understanding of the landscapes that will allow us to more confidently predict regolith distribution.

Catchment Management Authorities in NSW work on a three-tiered system of land subdivisions, from large to small: Groundwater Flow Systems (GFS), Hydrogeomorphic Units (HGU), and Land Management Units (LMU). So far we have worked at GFS and HGU scales using data of relatively coarse resolution. Only one study (Bet Bet in the MDBC project) has been carried out at a LMU scale. Results to date show that at the GFS scale, descriptions may be adequate, but that explanations, and especially predictions, are not easily made. The Landscape Analysis project described here seeks to remedy this situation by providing a firm descriptive and evolutionary framework.

Outputs

- Maps of hierarchical land units for selected parts of the Murray-Darling Basin.

- A report describing geological and regolith features that indicate how landform and regolith has evolved for selected parts of the Murray-Darling Basin.

- Reports that link the mapping hierarchies to groundwater flow systems, regolith, geomorphic history, geology, salt stores etc.

- Paper, “A review of groundwater flow and regolith architecture in upland landscapes in eastern Australia”, to be published in Hydrological Processes, submitted by March 2008.

- A report detailing the following will be presented to CMAs, MDBC, etc. during the second quarter of 2008.

Outcomes

- Significantly improved regional natural resource management tools;

- Demonstration of methods of extrapolation using a hierarchical mapping system.

Impacts

- Better understanding by CMAs of the importance and scale of landform and regolith for NRM, initially the management of salinity.

- Ability to consider whole-of-catchment management options.

Milestones: (dates of significant events marking scientific progress)

December 2006 	preliminary report on landscape evolution in the upland areas of the MDB.

June 2007 	preliminary report that assesses different approaches to modelling at different landscape scales.

December 2007	Report on regolith and bedrock models that consider catchment and salinity processes at sub-catchment scales.

March 2008	Paper submitted to international journal, and report submitted for peer review.

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO/ Exec:		23.6.06

Date approved by Board:		29.6.06

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| John Wilford | IK |  |  |  |  |  | 0.25 |  |  | 0.25 |
| Dave Gibson | IK |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Colin Pain | IK |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Jeremy James | Ind |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Heike Apps | IK |  |  |  |  |  | 0.25 |  |  | 0.25 |
| TOTAL |  |  |  |  |  |  | 1.10 |  |  | 1.10 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 30 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 30 |  |
| Possible additional external funds (for info) |  |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel |  |  |  |  |  | 10 |  |  | 10 |
| Analyses (age dating of regolith materials) |  |  |  |  |  | 20 |  |  | 20 |
| TOTAL |  |  |  |  |  | 30 |  |  | 30 |

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| John Wilford | IK |  |  |  |  |  | 0.1 |  |  |  |
| Dave Gibson | IK |  |  |  |  |  | 0.05 |  |  |  |
| Colin Pain | IK |  |  |  |  |  | 0.1 |  |  |  |
| Jeremy James | CRC |  |  |  |  |  | 0.25 |  |  |  |
| Heike Apps | IK |  |  |  |  |  | 0.25 |  |  |  |
| TOTAL |  |  |  |  |  |  | 0.75 |  |  |  |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested |  |  |
| Committed (definite) external funds |  |  |
| Total Project Opex |  |  |
| Possible additional external funds (for info) |  |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel |  |  |  |  |  | 10 |  |  |  |
| Analyses |  |  |  |  |  |  |  |  |  |
| Data acquisition |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  | 10 |  |  |  |