# Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  						(Issued by LEME Head Office)

Submitted by:		Tim Munday

Date submitted: 	8/8/2006			V4 Updated TM/SG/JM 20.9.06

Project name:  	Hydrogeological studies of River Murray Floodplains, Riverland, South Australia using airborne and ground geophysical techniques

Abbreviated title: 	SA Murray Floodplains

Type of project	Centre/Industry/commercial				(Centre or Industry/Commercial):

Program:  		4

Themes:  		Theme 7: Salinity systems in regolith and groundwater

Project Leader:  	Tim Munday

# Start date and duration:  August 2005 to June 2007

Participants:	 	CSIRO EM, CSIRO LW, Geoscience Australia, SA Water, DWLBC

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

This project focuses on analysis and interpretation of ground and airborne (AEM) geophysical data across the Chowilla SEA and Bookpurnong floodplains, informing the Chowilla Integrated Natural Resource Management Project and the Bookpurnong Floodplain Pilot Project which are funded by the NAP, MDBC, DWLBC and NHT. Floodplains of the River Murray are a potential source of salt and other contaminants to the river, due to their role in intercepting saline groundwater discharge. The roles of surface water–groundwater interactions in wetland soil and water chemistry, and the resultant biotic responses are poorly known. The connectivity of the surface and groundwater depends on regional hydrogeology and wetland geomorphology, and will also be affected by operations such as wetland wetting-and-drying cycles and groundwater interception.  Regional groundwater is highly saline, anoxic and reduced, impacting wetland water quality and habitat.  The knowledge gap in water interactions in wetlands, and impact of water quality on ecology and biodiversity, is a shortcoming in our ability to determine the most appropriate way of managing wetlands of the lower River Murray.

We propose to apply new geophysical techniques to derive soil-regolith and salt store maps that would help identify local recharge and discharge areas, and likely effects on river salinity. We will examine the role of electrical geophysical methods to map spatial and temporal variations of salinity linked to environmental flow management in particular test sites in the Riverland area. We believe the geophysical data, when linked to detailed ground investigations, will provide an understanding of causal links between in-river salinity, floodplain and upland aquifer characteristics, and discharge processes. This will have environmental benefits to the River and its wetlands, and salinity benefits to ecologically important floodplain areas.

The project will also re-examine existing HEM data for Pike River, Murtho and Chowill SIS areas. Combining these data with local ground information will deliver information on the Loxton-Parilla Sands aquifer which will help plan these schemes. This work will build on knowledge from the SA-SMMSP in the Bookpurnong area, which demonstrated that geophysical methods do provide detailed spatial information to assist in the prediction of irrigation impacts, the design of salt interception schemes, and protection of floodplain values in the Riverland region. These issues are central to the regional and state strategies for the River Murray and are identified as key targets in the SA MDB INRM Plan (2003).

# Project Objectives

Principal objectives are:

- To better define the hydrogeological characteristics of the principal aquifer systems in order to inform planning of floodplain and highland components of the Chowilla, Pike River and Murtho Salt Interception Schemes.

- To determine the value of airborne geophysics in helping define and protect groundwater dependent ecosystems on the Chowilla floodplains.

- To relate run-of-river salinity to variations in floodplain aquifer and soil characteristics

- To map salt stores and soil variability in the Chowilla Floodplain and over Bookpurnong Floodplain Pilot Project site using new helicopter electromagnetic data processed using local constraints.

- To develop spatial-temporal ground geophysical monitoring techniques and apply them to floodplain studies at Bookpurnong and Chowilla (through links to SA CNRM Projects 16 and 17).

- Relate structures in soils and aquifers, as determined by geophysics and drilling, to the siting of irrigation developments, in order to better assess the time delays between changed land use and impact on river.

# Deliverables (outputs) and expected impacts of research (outcomes):

- A CRCLEME technical report on the inversion procedures used in reprocessing existing HEM data for Pike River, Murtho and Chowilla SIS areas. This report will detail characteristics of the Loxton-Parilla aquifer interpreted from airborne EM data and geological information collected from bores. This will assist planning and development of salt interception schemes. GIS compatible grids from the inversion will be supplied to DWLBC. Results from this work will be workshopped with DWLBC.

- CRCLEME Technical report on value of AEM for management of groundwater dependent ecosystems on salinising floodplain

- GIS compatible maps/grids of salt stores and aquifer water quality (salinity) covering Chowilla SEA and Bookpurnong floodplain test areas as derived from the constrained inversion of HEM data. A CRCLEME Technical report will describe procedures used in the constraint and validation of HEM data.  The technical report will include laboratory determination of floodplain sediment characteristics, salinity, moisture content and particle size. It will define the principal factors in determining the observed conductivity. The relationship between observed conductivities (salinity) on the floodplain and in the river will be documented. A merged AEM data set linking the southern upland area and the Chowilla floodplain will be produced in a GIS compatible form.

- A CRCLEME Technical report with the University of Adelaide describing the ground geophysical techniques developed to understand spatio-temporal patterns and processes associated with Environmental flow management on the floodplains and the consequence of SIS implementation. This work will also be presented as a conference paper.

- A CRCLEME/CSIRO LW Technical report on modelling the effects of spatially variable recharge to the Loxton Parilla aquifer at Bookpurnong, and the role of variable transmissivity linked to facies variations in the aquifer. This work will link upland processes with floodplain transmissivity, to determine the effect of aquifer heterogeneity on groundwater flow patters across the floodplain. It will also determine whether additional modelling is necessary.  Interim field results and progress in modelling will be reported in Progress and Annual Reports and Presentations.

# Outcomes

The project addresses key strategies and actions defined as “Essential” in the River Murray Salinity Strategy, the Dryland Salinity Strategy, and the River Murray Catchment Water Management Plans. Additional airborne geophysics in the River Murray floodplain will be a critical bridging link between land characteristics and groundwater processes in upland and floodplain regions. These data will promote an understanding of causal links between in-river salinity and floodplain and upland aquifer characteristics and discharge processes. The outcomes will influence the location and effectiveness of SIS and affect policy irrigation development and salinity credits.

Key outcomes for the project are:

- The provision of baseline data on the spatial distribution of near surface salt stores and materials in the floodplain and their relationship with in-river salinity. Project outputs will assist in the maintenance and development of enhanced environmental values for the Chowilla floodplain and river through a mix of management strategies

- Determining the value of airborne geophysics for informing the management of other floodplains areas in the Murray Basin

- Cost effective and efficient SIS design and development

- Better informed policy on irrigation development and water use efficiency

- The development of an internal (SA Govt Department) capacity to use airborne geophysical data linked to on-ground investigations in hydrogeological applications.

Milestones: (dates of significant events marking scientific progress)

| Milestone No. | Milestone | Responsibility | Objectives Addressed | Deliverables (outputs) Addressed | Milestone Date |
| --- | --- | --- | --- | --- | --- |
| 2006/07 |  |  |  |  |  |
| 1 | Ground calibration site measurements for Chowilla HEM validation and calibration | CRCLEME/DWLBC | 3 | 3 | July 06 |
| 2 | Report to the Project Steering committee and CNRM and MDB INRMG Boards (Jun 06) | CRCLEME/CSIRO LW | 1,2,3,4,& 5 | 1,2,3,4 & 5 | July 06 |
| 3 | Report on Revised interpretation of Pike River and Murtho HEM data | CRCLEME | 1 | 1 | August 06 |
| 4 | Field visit and water sampling for drainage study at Bookpurnong Irrigation area. | CRCLEME/CSIRO LW | 6 | 5 | Dec 06 |
| 5 | Field visits looking at Bookpurnong study sites and effect of SIS and flooding on geophysical responses | CRCLEME/Univ Adelaide/CSIRO LW/DWLBC | 3 & 4 | 2, 3, 4 & 5 | Mar-07 |
| 6 | Field investigations at Chowilla – drilling and sampling for validation of HEM data and link with in river salinity | CRCLEME/DWLBC | 2,3 & 4 | 2, 3 & 4 | Mar-07 |
| 7 | Report on value of AEM for management of groundwater dependent ecosystems in floodplain settings | CRCLEME/CSIRO LW | 2 | 2 | June 07 |
| 8 | Report/workshop/presentation of final project outcomes to CNRM and MDB INRMG Boards (excluding drainage study) | CRCLEME/Univ Adelaide/CSIRO LW | 1,2,3,4,& 5 | 1,2,3 & 4 | Jun-07 |
| 9 | Report on drainage study at Bookpurnong, and HEM interpretation at Chowilla. Paper on Bookpurnong floodplain study. | CRCLEME/Univ Adelaide/CSIRO LW | 6 | 5 | Aug-07 |

Titles of proposed publications and journals where the papers will be submitted

- Combining Air, Ground and ‘In River’ Electromagnetics in the Definition of Spatial Patterns of Groundwater Induced Salt Accumulation (Journal of Environmental and Engineering Geophysics)

- The application of airborne geophysics as an aid to better understanding River Murray - groundwater interactions – examples from the Chowilla Floodplains, South Australia (J Hydrology)

Titles of reports

- Constrained inversion of HEM data for informing the development of the Pike River and Murtho SIS (August 2006)

- AEM for management of groundwater dependent ecosystems on salinising floodplain (June 2007)

- The application of ground geophysical techniques for understanding spatio-temporal patterns and processes associated with environmental flow management on the Murray floodplains, SA (June 2007)

- Modelling the effects of spatially variable recharge to the Loxton Parilla aquifer at Bookpurnong, and the role of variable transmissivity linked to facies variations in the aquifer. (August 2007)

# Confidentiality requirements

Reports will be delivered to the SA CNRM and MDB INRMG Boards whereon their publication will be unrestricted.

Date Endorsed by Executive and Approved by CEO;	23.6.06

Date Endorsed by the Board:					29.6.06

# RESOURCES 2006-2007

# STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tim Munday | In kind |  |  |  | 0.25 |  |  |  |  | 0.25 |
| Andrew Fitzpatrick | In kind |  |  |  | 0.25 |  |  |  |  | 0.25 |
| Amanda Cornelius | CRC |  |  |  | 0.10 |  |  |  |  | 0.10 |
| KP Tan | Ind (CRC funded) |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Graham Heinson | In kind |  | 0.10 |  |  |  |  |  |  | 0.10 |
| Geophysicist | In Kind |  |  |  | 0.10 |  |  |  |  | 0.10 |
| TOTAL |  |  | 0.10 |  | 0.70 |  | 0.20 |  |  | 1.00 |

# PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | $45 |  |
| Committed external funds | $305 | CNRM, SA |
| Total | $350 |  |

# All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Mike Hatch | AU | PhD |

# DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

# Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total ($K) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Consulting –hydrogeological modelling/soil analysis (WUE study) |  |  |  | $85K |  |  |  |  | $85K |
| Field geophysics, sampling materials, lab analyses |  | $10K |  | $55K |  | $4.5K |  |  | $69.5K |
| Drilling |  |  |  | $15K |  |  |  |  | $15K |
| Airborne EM Data Acquisition |  |  |  | $51K |  |  |  |  | $51K |
| Travel |  | $2K |  | $28K |  | $5.5K |  |  | $35.5K |
| Misc computing/modelling |  |  |  | $7.5K |  |  |  |  | $7.5K |
| Misc Operating |  |  |  | $86.5K |  |  |  |  | $86.5K |
| Sub-Total |  | $12k |  | $328,000 |  | $10K |  |  | $350K |
| Less Carry Over from 05/06 |  | -$7k |  | -$162,061 |  | -$7,325 |  |  | -$176,386 |
| Total distribution for 06/07 |  | $5K |  | $165,939 |  | $2,675 |  |  | $173,614 |

# Expenditures incurred in 2005/06 by GA, AU and CEM are as follows:

# GA: $37,325 ($30K of CRC funds allocated to GA in 2005/06)

# AU: $7,000

# CEM: $162,061

# TOTAL: $206,386.

# It should be noted that industry fund did not come good in 2005/06.  Taking into account $30K of CRC funds distributed to GA in 2005/06, the project has a balance of minus $176,386 on 30 June 2006.