Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Ongoing ……YES			New……

Project No:  	4.9					(Issued by LEME Head Office)

Submitted by:	Richard Cresswell, Dirk Kirste, KP Tan, Jim Cox

Date submitted: 	24.5.05		V2. Changes made Steve Rogers 31.7.06

Updated SG / JM  20.9.06

Project name: 	The dynamics of salinity in Australia: Origins, mobilisation and transport of salt in the Australian regolith and response times relating to salinity.

Abbreviated title: 	Salinity Dynamics

Type of project	Centre				(Centre or Industry/Commercial):

## Program:  		4. Salinity mapping and hazard assessment

## Themes:  		1. Understanding regolith processes

3. Acid and alkaline soils

5. Making geochemistry more effective

7. Salinity systems in regolith and groundwater

9. Environmental geochemistry and the regolith

Project Leader:  	Richard Cresswell

## Start date and duration:  1 July 2005 to end December 2007

Participants:	 	CSIRO Land & Water, Geoscience Australia, ANU

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

- This project investigates the physical, chemical and environmental factors influencing salt mobilisation in an Australian regolith context.

- Integration of salt mobilisation understanding into a broad landscape and climatic context.

This project aims to determine quantitative parameters that address system response times in salinity-prone environments. The following specific questions will be addressed by the project:

- What is the origin of the salt?

This question will be addressed on 3 fronts: isotopic studies (Lenahan, Cresswell); rainfall chemistry studies (Cresswell, Dighton) and through chemical modelling in the unsaturated zone (Rassam, Cresswell).

- How does saline water and salt interact with regolith materials?

This will be addressed through geochemical modelling (Rassam); lysimeter experiments (Rassam, Cresswell) and chemical equilibrium, determined through CEC and XRD analysis (Tan, Rassam)

- How and how fast is it mobilized?

Basic hydraulic properties of regolith materials will be determined through field pump tests and laboratory analysis (porosimetry, x-ray tomography, permeability test, etc) on samples collected from drill cores (Tan, Turner, Cresswell, Gilfedder, Dighton). Isotopic studies will help elucidate timeframes for mobilisation and components of the mass balance equations (Cresswell).

- Where and at what rate is it transported?

Landscape analysis, hydrology and hydrogeology models will be used to characterise different terrains and model the 3D spatial variability in salinity mobilisation using the parameters determined in 3)(Cox, Davies, Gilfedder, Stenson, Cresswell, Gibson, Tan). Climate as a driver will be examined in well-characterised catchments and the effects of land-use change evaluated (Cresswell, Davies, Stenson).

To date, salinity parameters have been largely semi-quantitative. Working constructs, such as groundwater flow systems provide a targeting approach for more detailed studies, but generally involve poor integration of sub-surface regolith constraints. The continuing MDBC-funded project is attempting to redress this issue, but requires quantification of parameters such as hydraulic conductivity, transmissivity, permeability, specific yield and porosity that are specific to regolith materials, particularly where these materials act as groundwater hosts. This information is required at micro- macro- and regional scales.

Water transport properties for the regolith are vital components of transport models, and require detailed quantification. The interaction and ionic exchange of salts, particularly at high salinities, is also critical when deducing potential end-of-valley salt loads and correlating standard electrical conductivity measurements to actual salt impact. Hydrochemical studies aimed at elucidating the transport of salts within, and through, the regolith, are also fundamental to this project. This also links to projects under Programs 1, 2 and 3.

Climate trend analysis will be integral to the development of salinity risk maps (e.g. through 2Csalt) and will, therefore, come under the scope of this project.

Deliverables (outputs) and expected impacts of research (outcomes):

# Scientific Deliverables (new scientific advances)

- Rainfall chemistry evaluated and assessed for salt accession (Oct-06)

- Geochemical modelling incorporated into a groundwater flow systems framework (Dec-06).

- Integrated look-up tables of hydrogeological parameters pertinent to groundwater modelling in regolith dominated environments (Jun-07).

- Salinisation response times determined through a combination of geochemical and isotopic tracers and modelling (Jun-07).

- Report documenting salinity mitigation products in Qld catchments (eg Hodgsons Creek) (June 07)

- An assessment of salinity dynamics and processes in MDBC project areas (June 07)

# Deliverables to Client (Adoption mechanisms)

- 3D hydrogeological and hydrogeochemical frameworks for modelling of key NRM areas (Jun-07).

- Rainfall/hydrograph analysis tool (Jun-07).

- Integrated look-up tables of hydrogeological parameters pertinent to groundwater modelling in regolith dominated environments (Dec-07).

Deliverables (Outputs):

- Journal papers, Technical Reports and Open File Reports (see list below)

- Papers presented at National and International Conferences (see table below)

- Communication of results through conferences, workshops and literature

Expected impacts (Outcomes):

- Improved understanding and assessment of salinity risks and response.

- Consolidation of research on the age, origins, distribution and mobilisation of salts in the Australian regolith.

- Integration of chemical processes into salinity delivery mechanisms.

- Adoption of outputs from airborne geophysics and regolith characterisation projects into salinity management procedures and modelling exercises

- Establishment of hydrogeological dynamics (response times of a system) to changes in land-use and/or climate change

- Demonstration of the relevance of regolith and geophysical information to decision support systems for land management of salinity

Milestones: (dates of significant events marking scientific progress)

Quarterly reports from Project Leader to Program 4 Leader and Board

Annual Report of Activities

See attached sheet for milestone details, principal investigator responsibilities and timeline.

Major milestones are:

Review of salinity in Australia – Dec 2006 (Open File Report)

Chemistry of salinity – Jun 2007 (OFR)

Rainfall: hydrograph analysis tool developed – Jun 2007 (OFR)

Integrated look-up tables for salinity modelling - Jun 2008 (OFR)

## Projected Publications and Legacy Products

Legacy:

- Salt in the Australian Landscape: Sources, Stores and Mobilisation

(Cresswell with Glen Walker, Ray Evans, Andrew Herczeg) – paper to AESC Salinity volume 2006

- The Chemistry of Salinity

(Cresswell, Kirste and others) – paper to ISF 2008 Legacy Volume

- Hydraulic Parameters of the Regolith

(Cresswell, Tan, Cox, Kirste and others) – paper to ISF 2008 Legacy Volume

- Salinity Dynamics: Response times in the Australian context

(Cresswell, Gilfedder, Stenson, Rassam, Dighton, Cox, Barton with others) – paper to ISF 2008 Legacy Volume

Proposed publications (plus more to follow, particularly from Graduate students):

N.B. Also, a series of publications from the SA-SMMSP, currently under review to AJES

- Groundwater and Salinity in the Goondoola Basin, Queensland

(Cresswell and Dighton with Andrew Biggs, Mark Silburn, Ralph DeVoil) – in prep AJSR

- Chloride and 36Cl across Australia

(Cresswell with Keith Fifield, Allan Chivas) – in prep GCA

- Matching Deep Drainage to Rainfall and Groundwater Hydrographs

(Cresswell and Rassam with Mark Silburn, Jo Owens, Peter Barker) - in prep

- Base flow for the Fitzroy Basin

(Cresswell with Mark Silburn, Vivienne McNeill)

- Catchment-scale Modelling of Salt Mobility in Hodgson Creek, Queensland

(Gilfedder, Stenson, Cresswell and Dighton with Mark Silburn, Jo Owens, Ralph DeVoil) – in prep

- Modelling salinity: a review of models incorporating salt mobilisation and re-distribution

(Gilfedder, Rassam, Cresswell)

- Deep drainage processes and salt mobility

(Rassam with Jenny Foley, Mark Silburn)

- Salt mobility in the Fitzroy Basin, Queensland

(Cresswell and Gilfedder with Bruce Pearce, Lucy Reading, Mark Silburn)

- Hydrogeology of a weathered basalt terrain: Corangamite, Victoria

(Cox, Davies and Dighton with Chris Smitt, Peter Dahlhaus)

- Salt store and mobilisation in the Regolith: Controls from the Physical Attributes of the Regolith

(Tan and Cresswell) – to ISF 2008

- Dryland Salinity in Australia: A World Comparison

(Cresswell and others) – to ISF 2008

Confidentiality requirements

Some proprietary requirements for CMAs and State Agencies. Short term Commercial-in-Confidence issues with CMAs and INRM groups.

Date submitted to Executive:

Date approved by CEO/Exec:		23.6.06

Date approved by Board:		29.6.06

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KP Tan | CRC |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Richard Cresswell | CRC |  |  |  |  | 0.75 |  |  |  | 0.75 |
| Jim Cox | CRC |  |  |  |  | 0.20 |  |  |  | 0.20 |
| David Rassam | CRC/IK |  |  |  |  | 0.40 |  |  |  | 0.40 |
| Phil Davies | CRC/IK |  |  |  |  | 0.20 |  |  |  | 0.20 |
| Mat Gilfedder | CRC |  |  |  |  | 0.20 |  |  |  | 0.20 |
| John Dighton | CRC/IK |  |  |  |  | 0.20 |  |  |  | 0.20 |
| Matt Stenson | IK |  |  |  |  | 0.10 |  |  |  | 0.10 |
| Annette Barton | CRC/IK |  |  |  |  | 0.40 |  |  |  | 0.40 |
| Richard Greene |  | 0.30 |  |  |  |  |  |  |  | 0.30 |
| Sue Welsh | IK | 0.10 |  |  |  |  |  |  |  | 0.10 |
| Sara Beavis | IK | 0.15 |  |  |  |  |  |  |  | 0.15 |
| R Arculus | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| B Croke | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| P de Deckker | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| B Harrold | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| T Jakeman | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| J Magee | IK | 0.25 |  |  |  |  |  |  |  | 0.25 |
| L McMorrow | IK | 0.25 |  |  |  |  |  |  |  | 0.25 |
| B Opdyke | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| U Troilzscho | IK | 0.25 |  |  |  |  |  |  |  | 0.25 |
| I White | IK | 0.20 |  |  |  |  |  |  |  | 0.20 |
| TOTAL |  | 2.70 |  |  |  | 2.45 | 0.20 |  |  | 5.35 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Matt Lenahan | ANU | PhD |
| Michael Turner | ANU | PhD |
| Peter Somerville | ANU | PhD |
| Michael Smith | ANU | PhD |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 85 |  |
| Total Project Opex | 85 |  |

| Possible additional external funds (for info) | 145 | Qld projects* |
| --- | --- | --- |

* Expected share in QDRNRM projects in: Western catchments ($40k), Border Rivers ($25k), L Balonne/Maranoa ($40k); Condamine ($40k).

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field program | 2 |  |  |  | 10 | 0 |  |  | 12 |
| Physical properties analysis | 0 |  |  |  | 5 | 5 |  |  | 10 |
| Chemical properties analysis | 3 |  |  |  | 10 | 8 |  |  | 21 |
| Consumables | 2 |  |  |  | 3 | 5 |  |  | 10 |
| Travel | 1 |  |  |  | 10 | 15 |  |  | 26 |
| Analytical services | 2 |  |  |  | 5 | 2 |  |  | 9 |
| Publications | 0 |  |  |  | 2 | 0 |  |  | 2 |
| Total | 10 | 0 | 0 | 0 | 45 | 30 |  |  | 85 |

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Richard Cresswell | CRC |  |  |  |  | X |  |  |  | 0.75? |
| Jim Cox | CRC/IK |  |  |  |  | X |  |  |  | 0.20 |
| David Rassam | CRC/IK |  |  |  |  | X |  |  |  | 0.40 |
| Phil Davies | CRC/IK |  |  |  |  | X |  |  |  | 0.30 |
| Mat Gilfedder | CRC/IK |  |  |  |  | X |  |  |  | 0.20 |
| John Dighton | CRC/IK |  |  |  |  | X |  |  |  | 0.20 |
| Matt Stenson | IK |  |  |  |  | X |  |  |  | 0.10 |
| Richard Greene |  | X |  |  |  |  |  |  |  | 0.10 |
| Annette Barton | CRC/IK |  |  |  |  | X |  |  |  | 0.40 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Michael Turner | ANU | PhD |
| Peter Somerville | ANU | PhD |
| Michael Smith | ANU | PhD |
| Matt Lenahan | ANU | PhD |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 28 | 150 |
| Committed (definite) external funds |  | Negotiating1 |
| Total Project Opex | >28 |  |

| Possible additional external funds (for info) | 105 |  |
| --- | --- | --- |

* Expected share in QDRNRM projects in: Western Catchments ($40k), Belyando/Suttor ($25k), Condamine ($40k).

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field program |  |  |  |  |  |  |  |  |  |
| Physical properties analysis |  |  |  |  | 2 |  |  |  | 2 |
| Chemical properties analysis |  |  |  |  | 5 |  |  |  | 5 |
| Consumables |  |  |  |  | 2 |  |  |  | 2 |
| Travel |  |  |  |  | 6 | 3 |  |  | 9 |
| Analytical services |  |  |  |  | 2 |  |  |  | 2 |
| Publications | 2 |  |  |  | 4 | 2 |  |  | 8 |
| Total | 2 | 0 | 0 | 0 | 21 | 5 |  |  | 28 |

Milestone details

| Deliverable | details | milestone date | PI | comments |
| --- | --- | --- | --- | --- |
| Journal papers, Technical Reports and | NAP projects | Jun-06 | RC | Special issues, multiple authors |
| Open File Reports | Project results | on-going | ALL | Papers generated from ALL milestones below. |
| Papers presented at conferences | IAH 2005 | Nov-05 | RC |  |
|  | AIG-6 | Sep-05 | RC | Additional funds from CLW |
|  | AESC/ASEG | Jul-06 | RC, KT | Special session on Salinity Mapping, etc |
|  | Goldschmidt | Aug-06 | RC | Student presentations |
|  | MDB Workshop | Sep-06 | RC, KT |  |
|  | LEME Regolith | Nov-06 | ALL |  |
|  | AEIC/ AHR | Dec-06 | RC, KT |  |
|  | Hydrol. Water Res. Symp. | Dec-06 | DR |  |
|  | SAGEEP | Apr-07 | KT |  |
|  | ISF | Jul-08 | RC |  |
|  | others as required | on-going | ALL |  |
| Groundwater models developed in | Corangamite, VIC | Jun-06 | JC |  |
| key NRM regions | Bland Basin, NSW | Jun-06 | RC |  |
|  | Hodgson Creek, QLD | Jun-06 | MG | input from MS, DR, QDNRM; MDBC case-study site |
|  | others as required | on-going | ALL | linked to QDNRM and MDBC case-studies |
| Geochemical/solute models developed | effect of salinity on solute models | Jun-06 | DR | input from RC, DK |
|  | Bland Basin, NSW | Jun-06 | DK | input from RC, DR |
|  | Hodgson Creek, QLD | Jun-06 | DR | input from MG, MS, RC, QDNRM; MDBC case study site |
|  | Goondoola Basin, Moonie, QLD | Jun-06 | DR | input from MG, MS, RC, QDNRM; linked to L. Balonne work |
|  | others as required | on-going |  | linked to MDBC case-studies |
| Rainwater chemistry database | National collector network | on-going | RC | $5k/a support from MDBC |
| Rainfall:hydrograph analysis tools developed | in house models | Jun-07 | RC | comparison to HARTT |
| Look-up tables developed for physical parameters | gap analysis | Jul-05 | KT | continuation from 4.9 |
|  | colluvial & alluvial deposits | Jun-06 | KT | sand/silt dominated |
|  | "granite" saprolite | Jun-07 | KT | kaolinite dominant |
|  | "basalt" saprolite | Jun-07 | KT | montmorillonite Dom. |
|  | "shale" saprolite | Jun-08 | KT | illite/smectite dom. |
| Look-up tables developed for chemical parameters | gap analysis | Dec-05 | RC | with DR |
|  | compilation of SAR | Jun-06 | RC | with DR |
|  | compilation of CEC | Jun-06 | RC | with DR |
|  | mineralogy effects | Jun-07 | RC | with DR |
|  | salinity effects | Jun-08 | RC | with DR |
| Look-up tables developed for | gap analysis | Dec-05 | RC | input from all |
| hydrogeological parameters | existing data compilation | Jun-06 | RC | input from all |
|  | additional data accumulated | Jun-07 | RC | linked to drilling program |
| Look-up tables for physico-chemical parameters | effect of salinity on EC | Jun-06 | RC | input from all |
|  | effect of mineralogy on EC | Jun-07 | RC | input from all |
|  | effect of water on EC | Jun-07 | RC | input from all |
| 3D hydrogeological frameworks | Corangamite, VIC | Jun-07 | JC | external funding |
|  | Hodgson Creek, QLD | Jun-06 | MG | linked to QDNRM; MDBC case-study site |
|  | others as required | on-going | ALL | linked to QDNRM and MDBC case-studies |
| Integrated look-up tables for salinity modelling | synthesis of previous work | Jun-08 | ALL |  |

Timelines for activities

| 2005-06 | Jul-05 | Aug-05 | Sep-05 | Oct-05 | Nov-05 | Dec-05 | Jan-06 | Feb-06 | Mar-06 | Apr-06 | May-06 | Jun-06 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Journal papers, Technical Reports and Open File Reports | NAP projects |  | On-going |  |  |  |
| Papers presented at conferences |  |  | AIG-6 |  | IAH-NZ |  |  |  |  |  |  |  |
| Drilling of focus catchments | Hodgson Creek | SW slopes |
| Groundwater models developed in key NRM regions | Corangamite, Bland, Hodgson Creek, Warrego/Paroo, Border Rivers, Fitzroy Basin |
| Geochemical/solute models developed | Effects of salinity, Bland, Hodgson Creek, Goondoola Basin |
| Rainwater chemistry database | Monthly collection and analysis of rainfall from 20 sites across Australia |  |  |  |
| Rainfall:hydrograph analysis tools developed | Development of "in house" models and comparison to existing methods (e.g. HARTT) |
| Look-up tables developed for physical parameters | Gap | Colluvial and alluvial deposits |
| Look-up tables developed for chemical parameters | Gap analysis | SAR, CEC constraints |
| Look-up tables developed for hydrogeological parameters | Gap analysis | Existing data compilation |
| Look-up tables for physico-chemical parameters | effect of salinity & water on EC |
| 3D hydrogeological frameworks | Hodgson Creek | Corangamite |
| Integrated look-up tables for salinity modelling |  |  |  |  |  |  |  |  |  |  |  |  |
| 2006-07 | Jul-06 | Aug-06 | Sep-06 | Oct-06 | Nov-06 | Dec-06 | Jan-07 | Feb-07 | Mar-07 | Apr-07 | May-07 | Jun-07 |
| Journal papers, Technical Reports and Open File Reports |  |  |  | On-going |  |  |  |  |  |  |  |  |
| Papers presented at conferences | AESC | Goldschmidt | MDB Wkshp |  | LEME | AEIC |  |  |  | SAGEEP |  |  |
| Drilling of focus catchments |  |  |
| Groundwater models developed in key NRM regions | Fitzroy Basin, SEQ Western Catchments, L. Balonne/Maranoa |
| Geochemical/solute models developed | linked to QDNRM priorities |
| Rainwater chemistry database | Monthly collection and analysis of rainfall from 20 sites across Australia |  |  |  |
| Rainfall:hydrograph analysis tools developed | Development of "in house" models and comparison to existing methods (e.g. HARTT) |
| Look-up tables developed for physical parameters | Granite and basalt saprolite |
| Look-up tables developed for chemical parameters | mineralogical constraints |
| Look-up tables developed for hydrogeological parameters | data accumulation, drilling program complete |
| Look-up tables for physico-chemical parameters | effect of mineralogy on EC |
| 3D hydrogeological frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrated look-up tables for salinity modelling |  |  |  |  |  |  |  |  |  |  |  |  |
| 2007-08 | Jul-07 | Aug-07 | Sep-07 | Oct-07 | Nov-07 | Dec-07 | Jan-08 | Feb-08 | Mar-08 | Apr-08 | May-08 | Jun-08 |
| Journal papers, Technical Reports and Open File Reports |  |  |  | On-going |  |  |  |  |  |  |  |  |
| Papers presented at conferences |  |  |  |  |  |  |  |  |  |  |  |  |
| Groundwater models developed in key NRM regions | Condamine, Belyando/Suttor |
| Geochemical/solute models developed |  |  |  |  |  |  |  |  |  |  |  |  |
| Rainwater chemistry database | Monthly collection and analysis of rainfall from 20 sites across Australia |  |  |  |
| Rainfall:hydrograph analysis tools developed | Development of "in house" models and comparison to existing methods (e.g. HARTT) |
| Look-up tables developed for physical parameters | "shale" saprolite |  |
| Look-up tables developed for chemical parameters | salinity effects |  |
| Look-up tables developed for hydrogeological parameters | data validation (on-going) |  |
| Look-up tables for physico-chemical parameters |  |  |
| 3D hydrogeological frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrated look-up tables for salinity modelling | synthesis of previous work |