## Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  	4.44					(Issued by LEME Head Office)

Submitted by:	Tim Munday

Date submitted:  	7/8/06				V2 - Updated TM/JM/Sg 20.9.06

Project name:  	Development and implementation of salinity management initiatives in the Sunraysia region by informing our understanding of the regional hydrogeology using airborne geophysical data

Abbreviated title: 	Sunraysia AEM Surveys

Type of project		Industry		(Centre or Industry/Commercial):

Program:  		4. Salinity mapping and hazard assessment

Themes:  		6. Geophysical mapping and modelling in regolith terrains

7. Salinity systems in regolith and groundwater

Project Leader:  	Tim Munday

Start date and duration:  July 2006 (12 months)

Participants:	 CSIRO EM, Golburn-Murray Water, GA	(Project is independent of BRS AG initiative)

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The Mallee Murray irrigation region supports a nationally significant citrus, vegetable production and horticulture industry.  This industry is dependent upon the Murray River supplying water for irrigation, household use, livestock consumption, and industrial water use - accounting for nearly half the total water use across the Mallee. Salinisation of the Murray River is a significant threat to the sustainability of the irrigation resource for this region.   Natural inflows of highly saline groundwater to the River Murray have been exacerbated by irrigation development and adjacent clearing of dryland within the vicinity of the river.  Future irrigation development and the delayed impacts of land clearing in the dryland farming area will continue to increase these inflows into the future. The principle asset at risk is the Murray River, that supplies potable and irrigation water to the immediate region and downstream.  Salt-interception schemes are an important feature to protect water quality. However, key to their development and effectiveness is information on the:

- The spatial and temporal distribution of sub-surface saline inflows into the Murray River and their relationship with land use change

- Salt build up in the Mallee floodplain which presents a significant risk to River Murray salinity

- The recognition of high and low irrigation impact zones

- The appropriate location for salt interception high yielding production bores.

It is expected that significant ‘green-field’ developments will continue to occur into at least the medium–term adding further pressure to the supply of water and the protection of river and floodplain values.

Geophysical methods have the capacity to provide detailed spatial information to assist in the prediction of the impact of current and future irrigation developments, the design of salt interception schemes and protection of floodplain values. These issues are central to the regional and state strategies for the River Murray. The project has been initiated by the Sunraysia Salt Interception Integration and Optimisation Steering Committee and Project Board (MDB Ministerial Council Endorsed with MDBC approved work plan) in support of two of their high priority projects - A Sunraysia Regional Disposal Strategy (MDBC Funded) and the Refurbishment Planning for the ageing and underperforming Mildura-Merbein Salt Interception scheme (G-MW/MDBC co-funded). Project outputs will assist in the maintenance and development of enhanced environmental values for the floodplain and river through a mix of management strategies.

# Specific project objectives

We propose that, through the acquisition of appropriate airborne electromagnetic data linked to suitable ground investigations, this project would:

For Mildura-Merbein SIS:

- Reduce number of investigation wells required in order to inform design of groundwater management option(s), and provide for more targeted drilling reducing costs and environmental impacts, by providing an understanding of the distribution of near surface salt stores and materials in the floodplain and their relationship with in-river salinity

- Identify recharge areas postulated as attributing to post flood salt inflows, and

- Identify boundary of “flushed zone” induced by river regulation.

- Map variations in groundwater conductivity

- Map variations in aquifer porosity

For Kings Billabong:

- Identify salt stores and lithological variation in the Quaternary alluvium (Qa).

- Identify the main saline fluxes to the billabong system

- Identify flush zones and recharge areas in the floodplain sediments (Qa).

- Map the water table surface.

- Map the distribution of the single, composite Channel Sands-Parilla Sand aquifer and if possible variations associated with other sedimentary units (the Blanchetown Clay/upper Parilla Sand aquitard)

- identify the preferred groundwater flow paths emanating from the regulated storages

For Red Cliffs

- Provide baseline data on salt storage in floodplain sediments

- Determine recharge/discharge areas, and provide insights into floodplain processes

- Define the extent of the “flushed zone” adjacent to the river

- Map variations in groundwater salinity

“In River” Salinity

- Trial HEM data as a source of data for river bed salinty

- Compare results against NanoTEM run of river EM survey

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Definition of appropriate airborne geophysical system and survey parameters for an AEM survey,

- Technical specifications for incorporation in survey contract

- Management of geophysical survey contract, and quality assessment of the derived geophysical data

- Calibrated airborne geophysical data as conductivity depth images in a GIS compatible form.

- Report on survey outcomes and products delivered.

- GIS compatible map/grids and groundwater model compatible data layers detailing:

  - variations in groundwater salinity,

  - sediment salt loads,

  - variations in sediment porosity,

  - variations in recharge,

  - the extent of the flushed zone,

  - river bed salinities/salt loads

based on the constrained inversion of AEM data

- A report on the constrained inversion of HEM data, the procedure used, limitations of derived products (supplied in a GIS compatible format).

- Technology transfer workshop at GW-W to communicate the outcomes of the work to relevant stakeholders.

The project will build on previous and current studies being undertaken by CRCLEME in the Murray Darling Basin, particularly that associated with the Chowilla Floodplains Living Murray Icon site study, where AEM data are being studied to help inform the Chowilla SIS design and development and protect biodiversity.

Outcomes

An understanding of spatial patterns of floodplain salinity and the River will deliver improved biophysical constraint for various salinity management initiatives being developed in the Sunraysia region. We anticipate that project outputs will assist in the maintenance and development of enhanced environmental values for the floodplain and river through a mix of management strategies. For the MM SIS and Kings Billabong areas the AEM surveys will inform more detailed design of both surface water and groundwater management options including reducing the risk associated with the location of production wells for the proposed groundwater management scheme(s) and determining the potential salinity impacts of surface water management options. For the Kings Billabong area, the survey will assist in the design and subsequent implementation of an environmental watering regime to optimize billabong health.

In addition, project outcomes will directly support the further development of a region-wide numerical groundwater modelling package capable of meeting the MDBC requirements for Salinity Register (A) assessments, given the current suite of tools all suffer from a lack of detailed understanding of floodplain processes and in particular the attenuation and release mechanisms of salt stores on the flood plain and the spatial variability of these processes. Confidence in the modelling environment is considered critical in both the design of salt interception infrastructure and the assignment of credits and debits to the MDBC salinity registers.

Milestones

| 1. Service Agreement between CRCLEME and GMW |
| --- |
| Activity | Milestone |
| Service agreement signed by each party | 20th June 2006 |
| 2. AEM Survey contract agreed and survey planning initiated |
| Activity | Milestone |
| Contract with Fugro Airborne Surveys to acquire survey agreed and survey initiated | 30th June 2006 |
| 3. Stakeholder workshop & definition of biophysical data products from AEM data |
| Activity | Milestone |
| Workshop with Stakeholders convened by GMW. Definition of strategy for the constrained inversion of AEM data and agreement on biophysical outputs required from AEM interpretation | 30th July 2006 |
| 4 AEM data acquisition completed |
| Activity | Milestone |
| AEM Survey for Sunraysia area complete, Qa/Qc of preliminary survey data | 31st September 2006 |
| 5. Collation of information to constrain AEM inversion |
| Activity | Milestone |
| Collation of constraint information for use in reprocessing of AEM data including the acquisition of additional shallow borehole induction logs | 30th September 2006 |
| 6. Assessment of final AEM data from Contractor |
| Activity | Milestone |
| Analysis of interim data from contractor and assessment of quality. Compilation of report and generation of CDI products | 30th September 2006 |
| 7. Workshop and Stage 1 completion |
| Activity | Milestone |
| Conduct of interim workshop with DWLBC and decision on Stage 2 | 10th October 2006 |

Reporting

Progress reports are required on a monthly basis.

- Technical report on AEM survey outcomes and conductivity depth images (Nov 2006)

- Constrained inversion of EM data – Sunraysia (June 2007)

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO/Exec:		23.6.06

Date approved by Board:		29.6.06

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tim Munday | IK |  |  |  | 0.2 |  |  |  |  | 0.2 |
| Andrew Fitzpatrick | IK |  |  |  | 0.3 |  |  |  |  | 0.3 |
| Geophysicist | IK |  |  |  | 0.2 |  |  |  |  | 0.2 |
| KP Tan | Ind(CRC funded) |  |  |  |  |  | 0.1 |  |  | 0.1 |
| TOTAL |  |  |  |  |  |  |  |  |  | 0.8 |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $ | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 20,000 |  |
| Committed (definite) external funds | 403,768* | Golburn-Murray Water |
| Total Project Opex | 423,768 |  |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel/Accommodation |  |  |  | 15 |  | 4 |  |  | 19 |
| Misc/ Reporting |  |  |  | 2 |  |  |  |  | 2 |
| AEM data acquisition |  |  |  | 290 |  |  |  |  | 290 |
| Ground data acquisition /ground geophysics/lab analysis/equipment |  |  |  | 25 |  | 18 |  |  | 43 |
| Misc Operating |  |  |  | 69,768 |  |  |  |  | 69,768 |
| TOTAL |  |  |  | 403,768 |  | 20 |  |  | 423,768 |