Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		5.01				(Issued by LEME Head Office)

Submitted by:		Steve Hill

Date submitted: 	5 May 2006			VERSION 2 (5.5.06)

V3 Updated SG/JM 20.9.06

Project name:  	MTEC shortcourse programme

Abbreviated title: 	MTEC

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		5 E&T

Themes:  		Minerals Exploration Education & Training

Project Leader:  	Dr Ian Roach

Start date and duration:  1 July 2006, 1 year

Participants:	 	Dr Ian Roach (ANU)

Dr Steven Hill (UA)

Dr Mehrooz Aspandiar (CUT)

Dr Patrice de Caritat (GA)

Dr Dirk Kirste (ANU)

Dr Sue Welsh (ANU)

Dr Alan Mauger (PIRSA)

Dr Ravi Anand (CSIRO)

Dr Ken McQueen (ANU)

Dr Ian Robertson (CSIRO)

Dr D.C. McPhail (ANU)

Others as required

Brief project description:

These funds enable CRC LEME’s participation in MCA’s MTEC program. The MTEC program is designed to deliver better graduates to Australia's minerals industry, and CRC LEME is an important contributor, delivering 5 Honours-level courses and one postgraduate-level course each academic year. CRC LEME's latest research is taught to students and industry personnel in face-to-face field- or classroom-based courses.

Deliverables (outputs) and expected impacts of research (outcomes):

- Undergraduate (Honours) and postgraduate courses delivered on-site at core party universities, MTEC member universities and in-field;

- On-site E&T to minerals industry partners;

- Uses materials developed in Regolith TT project.

- Reports and articles as LEME Reports, Regolith Symposium papers, journal papers, press releases, radio interviews, etc.

Outcomes will be measured in terms of uptake of the Centre's research by industry professionals, and regolith-trained graduates entering the minerals and NRM industries.

Milestones: (dates of significant events marking scientific progress)

Milestones are as written in the table below, where existing courses are listed with approximate date of delivery:

| FY 2006-2007 |
| --- |
| Feb | Regolith Geology and Geochemistry (Melbourne) | Honours, 5 days | Aspandiar, Hill, Roach |
| Apr | Regolith Mapping and Field Techniques (Fowlers Gap) | Honours, 5 days | Hill, Roach |
| Apr | Introduction to Hydrogeochemistry (Melbourne) | Honours, 5 days | De Caritat, Kirste, Welsh |
| Jun | Advanced Remote Sensing (Adelaide) | Honours, 5 days | Mauger |
| Jun | Environmental Mineralogy (Canberra) | Honours, 5 days | Aspandiar |

| FY 2007-2008 |
| --- |
| Feb | Regolith Geology and Geochemistry (Melbourne) | Honours, 5 days | Aspandiar, Hill, Roach |
| Apr | Regolith Geology and Mineral Exploration (Fowlers Gap) | Masters, 11 days | Roach, Hill plus CRC LEME staff as required |
| Apr | Regolith Mapping and Field Techniques (Fowlers Gap) (concurrent with above) | Honours, 5 days | Hill, Roach |
| Apr | Introduction to Hydrogeochemistry (Melbourne) | Honours, 5 days | De Caritat, Kirste, Welsh |
| Jun | Advanced Remote Sensing (Adelaide) | Honours, 5 days | Mauger |
| Jun | Environmental Mineralogy (Canberra) | Honours, 5 days | Aspandiar |

Courses listed are those currently offered into the MCA shortcourse program. Courses or sub-sets may also be repeated each year targeted specifically to industry participants. Subsets of the Masters course will be offered for delivery as two-day modules in MCA's Pathways Program. Courses may be cancelled or rescheduled with appropriate notice if fee-paying or incentive-earning enrollments fall below a threshold, nominally 5 participants.

Confidentiality requirements:	None

Date submitted to Executive: 		5 May 2005

Date approved by CEO/Exec:		23.6.06

Date approved by Board:		29.6.06

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I Roach | CRC | 0.10 |  |  |  |  |  |  |  | 0.10 |
| S Hill | CRC |  | 0.10 |  |  |  |  |  |  | 0.10 |
| M Aspandiar | CRC |  |  | 0.10 |  |  |  |  |  | 0.10 |
| P de Caritat | IK |  |  |  |  |  | 0.10 |  |  | 0.10 |
| Kirste replacement | CRC | 0.10 |  |  |  |  |  |  |  | 0.10 |
| S Welsh | CRC | 0.10 |  |  |  |  |  |  |  | 0.10 |
| A Mauger | IK |  |  |  |  |  |  |  | 0.05 | 0.05 |
| TOTAL |  | 0.30 | 0.10 | 0.10 |  |  | 0.10 |  | 0.05 | 0.65 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| TBA (tutors as required) |  |  |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 30 |  |
| Committed (definite) external funds | 36,900 | MTEC |
| Total Project Opex | 66,900 |  |

| Possible additional external funds (for info) |  | MCA incentive payment |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Student/staff travel, course delivery | 10 | 10 | 10 |  |  |  |  |  | 30 |
|  | 36,900 |  |  |  |  |  |  |  |  |
| TOTAL | 46,900 | 10,000 | 10,000 |  |  |  |  |  | 66,900 |

Complete indicative resource tables for following year if appropriate

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Roach | CRC | 0.6 |  |  |  |  |  |  |  | 0.6 |
| Hill | CRC |  | 0.1 |  |  |  |  |  |  | 0.1 |
| Aspandiar | 0.5 CRC/0.5 IK |  |  | 0.1 |  |  |  |  |  | 0.1 |
| de Caritat | IK |  |  |  |  |  | 0.1 |  |  | 0.1 |
| Kirste | CRC | 0.1 |  |  |  |  |  |  |  | 0.1 |
| Welsh | CRC | 0.1 |  |  |  |  |  |  |  | 0.1 |
| Mauger | IK |  |  |  |  |  |  |  | 0.05 | 0.05 |
| Others as required | IK |  |  |  | 0.25 | 0.1 | 0.1 |  |  | 0.45 |
| TOTAL |  | 0.6 | 0.1 | 0.1 | 0.25 | 0.1 | 0.2 | 0 | 0.05 | 1.6 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| TBA (tutors as required) |  |  |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 30 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 30 |  |

| Possible additional external funds (for info) | ~30 | MCA incentive payment |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Student/staff travel, course delivery | 10 | 10 | 10 |  |  |  |  |  | 30 |
| TOTAL | 10 | 10 | 10 |  |  |  |  |  | 30 |