Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		5.03				(Issued by LEME Head Office)

Submitted by:	Steve Hill

Date submitted: April 2, 2006				V4 Updated SG/JM  20.9.06

Project name:  	Regolith Teaching and Training Materials

Abbreviated title: 	Regolith TTM

Type of project	Centre				(Centre or Industry/Commercial):

Program:  	5

Themes:  	Education & Training

Project Leader:  	Steve Hill

Start date and duration:  July 2006

Participants:

AU: Steve Hill, Graham Heinson, Karin Barovich, Andreas Schmidt-Mumm, John Joseph

ANU: Ian Roach, Bear McPhail, Dirk Kirste, Sue Welch, John Field

CUT: Mehrooz Aspandiar

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

This project includes outputs and outcomes that previously became the refocus of ‘Virtual Regolith Worlds’, but because of a change in outputs the project name has been changed.  The main emphasis on this project is for the provision of regolith teaching and training materials, used in the delivery of undergraduate, Honours and external client courses.  This includes the writing and presentation of lecture, practical and field-teaching materials; remote sensing and basemap imagery and presentation; and undergraduate student mapping and sampling programs.  The quality of these teaching materials ensures that CRC LEME science is an integral part of teaching courses, particularly within university undergraduate courses and the MTEC shortcourse program.  This project enables for the provision of high-quality teaching materials (ie. the content) for 2 of the 3 of the major objectives of CRC LEME’s E&T program:

- “Provide workshops, seminars and training courses on regolith geoscience and related disciplines, directed at students, industry, government and institutional professionals”; and,

- “Contribute regolith content to university” courses

Presently there is a major deficit in the provision of quality teaching materials for regolith geoscience.  This is necessary for the delivery of courses via the core party universities but also for providing materials for other teaching requirements in regolith geoscience.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs:

- Quality teaching content for the delivery of under-graduate courses in regolith geoscience;

- Quality teaching content for the delivery of MTEC shortcourses

- Regolith geoscience and remote sensing digital data package for Fowlers Gap Arid Zone Research Station (first edition).  This will include a compilation of remote sensing, maps and analytical results derived from previous CRC LEME courses at this much utilised regolith teaching site

- Production of teaching materials to contribute to regolith geoscience text-book

Publications:

- Roach, I.C. & Hill, S.M. Fowlers Gap Regolith Geoscience Research and Teaching Data Compilation.  Preliminary CD compilation, CRC LEME

- Hill, S.M. & Roach, I.C. Regolith geoscience research and teaching at Fowlers Gap, western NSW.  BHEI conference poster and abstract.

- Roach, I.C. & Hill, S.M. South Sandstone Paddock 1:25k regolith-landform map.  CRC LEME

- Hill, S.M. & Roach, I.C. Connors Paddock 1:25k regolith-landform map. CRC LEME

- Hill, S.M. & Roach, I.C. Regolith geoscience research and teaching at Fowlers Gap, western NSW.  2006 Regolith Symposium refereed abstract.

- Hill, S.M., Roach, I.C. Greenwood, D & Greenwood, D.  Long-term regolith and landscape evolution of the Sandy Creek catchment, WNSW. Geomorphology

Outcomes:

- The legacy of this work includes the increased skill and knowledge in regolith geoscience of graduates in Earth Sciences; continued recruitment of Honours and PhD students; and greater industry skill and knowledge.

- Impressive content for contributions of regolith geoscience to teaching and training courses

- Production of “industry-ready” graduates with regolith geoscience skills and knowledge

Milestones: (dates of significant events marking scientific progress)

- July 8-14, 2006: Joint AU/ANU undergraduate regolith geology fieldtrip to Fowlers Gap (SH, IR, GH, JF)

- July – November, 2006: Delivery of teaching materials in undergraduate courses at AU, ANU and CUT (All listed staff)

- September, 2006: Complete Sth Sandstone regolith-landform map (IR & SH)

- September, 2006: Complete Connors regolith-landform map (SH & IR)

- September 16-22, 2006: AU 3rd year regolith fieldtrip to Murray Basin (SH)

- November compilation of preliminary draft of Fowlers Gap Regolith Geoscience teaching materials CD (IR & SH)

- February 2007: Regolith Geology & Geochemistry Shortcourse, Wilsons Promontory (SH, IR, MA)

- April 2007: Regolith mapping & Field techniques shortcourse. Fowlers Gap (SH, IR)

Confidentiality requirements

None

Date submitted to Executive:

Date approved by CEO/Exec:		23.6.06

Date approved by Board:		29.6.06

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hill, Steve | CRC |  | 0.15 |  |  |  |  |  |  | 0.15 |
| Roach, Ian | CRC | 0.25 |  |  |  |  |  |  |  | 0.25 |
| Heinson, Graham |  |  | 0.25 |  |  |  |  |  |  | 0.25 |
| Barovich, Karin |  |  | 0.70 |  |  |  |  |  |  | 0.70 |
| Schmidt-Mumm, A |  |  | 0.45 |  |  |  |  |  |  | 0.45 |
| Field, John | IK | 0.50 |  |  |  |  |  |  |  | 0.50 |
| McPhail, Bear | IK | 0.10 |  |  |  |  |  |  |  | 0.10 |
| Kirste replacement | CRC | 0.10 |  |  |  |  |  |  |  | 0.10 |
| Welsh, Sue | CRC | 0.10 |  |  |  |  |  |  |  | 0.10 |
| Aspandiar. M |  |  |  | 0.25 |  |  |  |  |  | 0.25 |
| TOTAL |  | 1.05 | 1.55 | 0.25 |  |  |  |  |  | 2.85 |

All LEME STUDENTS contributing to Project 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| all | all | all |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 25 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 25 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Map production |  |  |  |  |  |  |  |  |  |
| Remote Sensing Data |  |  |  |  |  |  |  |  |  |
| Field courses (travel & accomm) |  |  |  |  |  |  |  |  |  |
| UG student chemical analyses |  |  |  |  |  |  |  |  |  |
| Course notes production |  |  |  |  |  |  |  |  |  |
| Total | 7,690 | 15,385 | 1,925 |  |  |  |  |  | 25,000 |