Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		1.23				(Issued by LEME Head Office)

Submitted by:		J Keeling

Date submitted: 	18 May 2005			V7 19 June 05

Changes by CEO

Project name:  	Central Gawler Gold Landscapes

Abbreviated title: 	Central Gawler

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		Program 1

Themes:  		Regional Exploration Studies

Project Leader:  	J Keeling

Start date and duration:  July 2003 – 4 years

Participants:	 	PIRSA (J Keeling, M Sheard, B Hou, W Zang, G Gouthas); CSIRO (E&M) (M Lintern, D Gray); AU (Steve Hill); GA (L Worrall)

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

An arcuate belt of Proterozoic rocks in the central Gawler Craton has been recognised as a new gold province of regional significance.  Deposits at Tarcoola, Boomerang, Glenloth and Earea Dam, together with new gold prospects at Tunkillia, Nuckulla Hill, Barns and Weednanna outline a >500 km long arcuate belt of similar mineralisation and alteration styles.  That such a regional gold system was historically unrecognised is due to the presence of extensive cover sediments, a gold-depleted regolith, and the lack of an effective exploratory tool until the widespread use of calcrete geochemistry in the mid-1990s.  Whilst some companies have experienced significant success with Au-in-calcrete sampling, others have been frustrated by the difficulty in discriminating between anomalies closely associated with bedrock mineralisation and spurious anomalies associated with significant thicknesses of transported regolith.  Companies have expressed the need for additional data on landscape history and the development of supplementary targeting techniques in order to plan effective drilling programs to test calcrete anomalies.

This project will focus on the regional regolith setting and the nature, distribution and thickness of the regolith cover.  Combining the results of regional compilations with detailed investigations at specific sites, the group will develop models of landscape evolution, physical and chemical dispersion processes and mineralogical changes of the bedrock and associated mineralising system through the weathered profile.  Of particular interest will be the impact of weathering on the hydrothermal alteration mineralogy in a variety of host rocks intruded by Hiltaba Suite granite.  Preliminary biogeochemical study focussed on the western Myall, common to the area, will also be included.

Compilation of regional scale maps of groundwater chemistry from existing data will be an output of this investigation.

This project will be done in conjunction with other CRC-LEME projects that either focus on regolith geochemistry and geophysics of the Central Gawler Gold mineralising systems, or incorporate data from this site in their research.  These include:

- Calcrete Gold (P2) (A Schmidt-Mumm, D McKirdy, J Brugger, D Chittleborough, R Dart)

- Predictive petrophysics of shear zone/ granite hosted Au in the Central Gawler Gold Province, South Australia (N Direen, J Joseph, Graham Heinson)

- Gold and Metal Mobility  (P2)  (B McPhail)

- Mineral Mapping (A Mauger and J Keeling,)

- Objective Logging (P1) (T Munday, D Gray, R Anand, J Keeling, A Mauger and others)

- Metal Transfer Mechanisms (P2) (R Hough, R Anand, A Cornelius, B McPhail, M Lintern and others).

Deliverables (outputs) and expected impacts of research (outcomes):

- Interim maps at 1:500,000 scale of

  - regolith thickness

  - regolith type

  - palaeo-drainage

  - geochemistry

  - groundwater chemistry

These maps will summarise data availability.

- Prospect scale preliminary models of

  - landscape evolution (includes: regolith stratigraphy dating transported cover and reference site description and maps)

  - weathering of the primary mineral system

  - physical dispersion processes

  - hydro-geochemical dispersion processes

  - role of western Myall in cycling of Au

Outcomes anticipated include uptake of regional data products and use of identified regolith vectors to mineralisation, leading to increased and more efficient mineral exploration in the area with improved exploration success.

Milestones: (dates of significant events marking scientific progress)

December 2003: Completion of all current work on the Harris Greenstone Belt on the northern margin of the Central Gawler Gold Province (work completed and final LEME report printed and distributed.  All work incorporated in the HGB GIS and data CD issued by PIRSA April 2005).

February 2004: complete construction of the Central Gawler Gold Province GIS, workshop the production of interim maps (Catalogue of available data compiled as a joint GA, PIRSA, CRCLEME report; initial GIS in completed; workshop of interim maps held 30 March –1 April).

June 2004: release GIS and interim maps, report on prospect-scale process studies, review and reassess project plan in conjunction with the PIRSA/GA group reviewing the nature and timing of the mineralising systems (commitment from GA and PIRSA to funding Central Gawler projects for a further 2 years, release of version 1 GIS and preliminary data issued at Gawler State of Play workshop, Adelaide 4-6 August, 2004).

October 2004:  Field workshop of LEME participants in Central Gawler Gold projects (combined field trip, PIRSA-AU-CSIRO, held June 04 during excavation of dune at Barns).

- Release Harris Greenstone GIS on DVD

- Report by Hou on Kingoonya Palaeochannel

June 2005:  Exploration Through Transported Cover Conference, Adelaide University, 24 June.

- Report on regolith studies of the Boomerang Au prospect (currently with VRU in Perth (May 05)

- Barns Au Prospect and western Myall biogeochemical studies.

December 2005:  Papers prepared on dating dune cover and significance to landscape evolution and geochemical dispersion.

June 2006: Reports issued on the results of vegetation sampling.  Completion report on regolith mapping and site studies in the Wudinna area.  Final copies of regional regolith and geochemical maps output on DVD in GIS.

June 2007:  Synthesis of landscape evolution, cover distribution and metal dispersion.

Confidentiality requirements

None (except where company data may have a short time restriction before release)

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| J Keeling | IK |  |  |  |  |  |  |  | 0.3 |  |
| B Hou | IK |  |  |  |  |  |  |  | 0.5 |  |
| M Sheard | IK |  |  |  |  |  |  |  | 1.0 |  |
| W Zang | IK |  |  |  |  |  |  |  | 0.5 |  |
| G Gouthas | IK |  |  |  |  |  |  |  | 0.25 |  |
| L. Stoian | IK |  |  |  |  |  |  |  | 0.1 |  |
| M Lintern/D Gray | IK |  |  |  | 0.1 |  |  |  |  |  |
| L Worrall | IK |  |  |  |  |  | 0.1 |  |  |  |
| S Hill | CRC |  | 0.1 |  |  |  |  |  |  |  |
| Total |  |  | 0.1 |  | 0.1 |  | 0.1 |  | 2.65 | 2.95 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS $K 2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 27 |  |
| Committed (definite) external funds |  |  |
| Committed (definite) in kind | 4* | PIRSA |
| Total Project Opex | 31 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

* Field expenses incl vehicles, fuel and accommodation which are being met by PIRSA

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field sampling |  |  |  |  |  |  |  | 4.5 | 4.5 |
| Travel |  |  |  |  |  |  |  | 4.5 | 4.5 |
| Analytical |  |  |  |  |  |  |  | 6.0 | 6.0 |
| Conferences, workshops |  | 0.5 |  |  |  |  |  | 3.5 | 4.0 |
| Biogeochemistry |  | 3.5 |  |  |  |  |  |  | 3.5 |
| Drafting/Reports/posters |  |  |  |  |  |  |  | 4.5 | 4.5 |
| Total |  | 4.0 |  |  |  |  |  | 23.0 | 27 |

Note: Operating funds for PIRSA staff in previous years largely contributed from PIRSA internal budget

Complete indicative resource table for following year if appropriate

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| J Keeling | IK |  |  |  |  |  |  |  | 0.3 |  |
| B Hou | IK |  |  |  |  |  |  |  | 0.5 |  |
| M Sheard | IK |  |  |  |  |  |  |  | 1.0 |  |
| W Zang | IK |  |  |  |  |  |  |  | 0.5 |  |
| G Gouthas | IK |  |  |  |  |  |  |  | 0.25 |  |
| L. Stoian | IK |  |  |  |  |  |  |  | 0.1 |  |
| M Lintern/D Gray | IK |  |  |  | 0.1 |  |  |  |  |  |
| L Worrall | IK |  |  |  |  |  | 0.1 |  |  |  |
| S Hill | CRC |  | 0.1 |  |  |  |  |  |  |  |
| Total |  |  | 0.1 |  | 0.1 |  | 0.1 |  | 2.65 | 2.95 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 12 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 12 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Analytical |  |  |  | 2 |  |  |  | 2 | 4 |
| Plan drafting and printing |  |  |  |  |  |  |  | 4 | 4 |
| Report printing/editing |  |  |  |  |  |  |  | 1.0 | 1.0 |
| Conference/Promotion |  |  |  | 1.5 |  |  |  | 1.5 | 3.0 |
| TOTAL |  |  |  | 2.5 |  |  |  | 9.5 | 12.0 |