Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY

Project No:  		1.24					(Issued by LEME Head Office)

Submitted by:		Dirk Kirste

Date submitted: 	20 May 2005			V7a (24 June 05

Changes by CEO-BM

Project name:  	Exploring through Cover in the Curnamona

Abbreviated title: 	CurnaMinEx

Type of project	Centre/Industry	(Centre or Industry/Commercial):

Program:  		P1: Regolith Geoscience

Themes:  		Theme 1. Understanding regolith processes

Theme 4. Regional mineral exploration studies

Theme 5. Making geochemistry more effective

Theme 6. Geophysical mapping and modelling

Project Leader:  	Dirk Kirste

Start date and duration:   1 July 2005 for 30 months

Participants:	Dirk Kirste (ANU), Sue Welch (ANU), John Keeling (PIRSA), Steve Hore (PIRSA), Mark McGeough (PIRSA), Barney Stevens (NSW DPI), Steve Hill (AU), Karen Hulme (AU),  John Joseph (AU), Nick Direen (AU), Adrian Fabris (PIRSA), Alistair Crooks (PIRSA), Aaron Brown (PIRSA), Liliana Stoian (PIRSA), George Gouthas (PIRSA), Luisa Ruperto (GA), TBA (NSW DPI), Joel Brugger (AU). Input from Roger Fidler, Malcolm Sheard.

Brief project description: (in no more than 400 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects, contribution to strategic intent.)

This project merges and expands upon Projects 1.24 Curnamona 3D and 1.25 Curnamona DTB, and integrates data acquired by the LEME I Basins Program, the LEME II Western NSW Regolith Project and various industry, government and research bodies.  We will develop comprehensive geochemical and geophysical exploration strategies to target specific mineral deposit types in areas of regolith cover, primarily Cu-Au, Pb-Zn, Au-U deposit types. The relation of these types of mineralisation to chemical and geophysical phenomena in the Curnamona is well documented. However, exploration methods are not clearly defined in areas of transported regolith. We will establish viable exploration strategies for these conditions by first developing our understanding of how the deposit types are expressed geochemically and geophysically within the regolith, and then by  establishing the processes of dispersion most likely to result in the physico-chemical expression of the mineralisation at the surface. This project will apply established and new (for the region) geochemical, biogeochemical and geophysical exploration techniques in areas of known mineralisation (Honeymoon/Kalkaroo, Portia, Hunter’s Dam, Polygonum, Brook’s Dam) to test the viability of the various methods. In order to establish a rigorous sampling program it is our intention to address three physico-chemical components of buried mineralisation:

- geophysical expression of mineralisation in primary/secondary form

- geochemical expression of mineralisation in primary/secondary form

- dispersion through cover from deposit to surface

The project consists of a series of sub-projects that address exploration methodologies at scales appropriate to district – prospect – target dimensions in terms of the geochemical mechanisms of formation and subsequent dispersion of mineralisation.

Sub-projects include:

- Targeted geochemistry and regolith studies CurnaMinEx A

- Geophysical Signatures at selected Mineral Prospects CurnaMinEx B

- Understanding Geochemical Signatures CurnaMinEx B

- 3D regolith mapping CurnaMinEx D

Deliverables (outputs) over total project time frame and expected impacts of research (outcomes):

Outputs

- Surface regolith maps*

- 3D models of Mesozoic to Tertiary cover from Basin to Prospect scales

- 3D models of regolith cover at regional scale (fully scalable)

- Baseline geochemical maps and databases

- Interpretive reports (geochemical and geophysical)*

- Analytical report for applied geochemical techniques

- Case studies for prospects

- 3D process (reactive transport) models

- Explorer’s guide

- Abstracts, publications, presentations

*interim and final reports

Outcomes

- More effective geochemical exploration through cover using process based understanding and combined geochemical and geophysical techniques

- Field testing of specific geochemical sample collection methods (CHIM, biota, partial/selective extraction, gas phase)

Milestones: (dates of significant events marking scientific progress)

1 July 2005		Project starts

4-6 July 2005		Organisational and strategy meeting Adelaide

July-October 2005	Acquisition and assessment of existing datasets

July-October 2005	Research and report on potential dispersion processes

26-28 Sept. 2005 	Meeting Adelaide to discuss geochemical methods

Oct-Nov 2005	Field to conduct CHIM and other geochemical methods and geophysical data acquisition

February 2006		Interim report on analytical results

March 2006 		Future direction strategy meeting

Feb 2006

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note:  Out of budget revisions or updates to the approved Project Summary are to be submitted by Program Leader to Susan Hame, HO Perth, for approval by CEO and advice to Business Manager.

RESOURCES

Staffing  FTEs   (eg 0.50)  for 2005-2006

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D Kirste | CRC | .35 |  |  |  |  |  |  | .35 |
| S Welch | CRC | .05 |  |  |  |  |  |  | .05 |
| L Ruperto | CRC |  |  |  |  | 1 |  |  | 1 |
| A Fabris | IK |  |  |  |  |  |  | 1 | 1 |
| J Joseph | CRC |  | .6 |  |  |  |  |  | .6 |
| B Stevens | IK |  |  |  |  |  | .1 |  | .1 |
| A Crooks | IK |  |  |  |  |  |  | .1 | .1 |
| A Brown | IK |  |  |  |  |  |  | .9 | .9 |
| L Stoian | IK |  |  |  |  |  |  | .1 | .1 |
| G Gouthas | IK |  |  |  |  |  |  | .3 | .3 |
| TBA | IK |  |  |  |  |  | .25 |  | .25 |
| J Keeling | IK |  |  |  |  |  |  | .1 | .1 |
| J Brugger | IK |  | .1 |  |  |  |  |  | .1 |
| S Hore | IK |  |  |  |  |  |  | .2 | .2 |
| M McGeough | IK |  |  |  |  |  |  | .1 | .1 |
| Contractor | Ind |  |  |  |  |  |  | 1 | 1 |
| S Hill | CRC |  | .1 |  |  |  |  |  | .1 |
| Total |  | 0.40 | 0.80 |  |  | 1 | .35 | 3.8 | 6.35 |

All LEME Students contributing to Project - 2005 - 2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Karen Hulme | AU | PhD |

#### PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 72.6 |  |
| Committed (definite) external funds |  |  |
| Committed (definite) In Kind | 185.1 | PIRSA, Industry* |
| Total Project Opex | 286.7 |  |

| Possible additional external funds (for info) | 25 | PACE |
| --- | --- | --- |

* Industry In Kind Support attached to the deployment of CHIM is approximately $43.5k. Additional Industry In Kind relating to the provision of accommodation totals approximately $6.7k. PIRSA is providing vehicles, fuel, field expenses and 1 FTE (contract position) as additional In Kind support to the project. The value of this support is in excess of $134.9k.

CRC Operating Expenses - $K - 2005-2006   (show allocation per core party)

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field | 2.6 | 4 |  |  |  |  |  | 6.6 |
| Analytical | 7 |  |  |  |  |  |  | 7 |
| Travel | 3 |  |  |  | 3 |  | 2 | 7 |
| Analyses (partial leaches) |  |  |  |  |  |  | 33 | 33 |
| Analyses (vegetation) |  | 8 |  |  |  |  |  | 8 |
| Trenching |  |  |  |  |  |  |  |  |
| Aircore drilling |  |  |  |  |  |  |  |  |
| Workshops |  |  |  |  |  |  |  |  |
| Reporting/Tech transfer |  | 1 |  |  |  | 1 | 1 | 3 |
| Equipment Rental |  | 4 |  |  |  |  |  | 4 |
| Purchase of Software |  | 2 |  |  |  |  |  | 2 |
| Administration Cost |  | 1 |  |  |  |  |  | 1 |
| Analyses (palynology) |  |  |  |  |  |  |  |  |
| Total | 12.6 | 20 |  |  | 3 | 1 | 36 | 72.6 |

Confidentiality requirements:  As per contracts with clients

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

Staffing  FTEs   (eg 0.50)  for 2006-2007

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D Kirste | CRC | .35 |  |  |  |  |  |  | .35 |
| S Welch | CRC | .05 |  |  |  |  |  |  | .05 |
| L Ruperto | IK |  |  |  |  | 1 |  |  | 1 |
| A Fabris | IK |  |  |  |  |  |  | 1 | 1 |
| J Josephs | CRC |  | .3 |  |  |  |  |  | .3 |
| B Stevens | IK |  |  |  |  |  | .1 |  | .1 |
| A Crooks | IK |  |  |  |  |  |  | .1 | .1 |
| A Brown | IK |  |  |  |  |  |  | .9 | .9 |
| L Stoian | IK |  |  |  |  |  |  | .1 | .1 |
| G Gouthas | IK |  |  |  |  |  |  | .3 | .3 |
| TBA | IK |  |  |  |  |  | .25 |  | .25 |
| J Keeling | IK |  |  |  |  |  |  | .1 | .1 |
| J Brugger | IK |  | .1 |  |  |  |  |  | .1 |
| S Hore | IK |  |  |  |  |  |  | .2 | .2 |
| M McGeough | IK |  |  |  |  |  |  | .1 | .1 |
| S Hill | CRC |  | .1 |  |  |  |  |  | .1 |
| Total |  | 0.40 | 0.50 |  |  | 1 | .35 | 2.8 | 5.05 |

All LEME Students contributing to Project - 2006 - 2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

#### PROJECT OPERATING COSTS $K 2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 77 |  |
| Committed (definite) external funds |  | PACE |
| Total Project Opex | 77 |  |
| Possible additional external funds (for info) |  | Industry Partners** |

**Funding from industry partners are not in cash, but in terms of as various infrastructural/field support

CRC Operating Expenses - $K - 2005-2006   (show allocation per core party)

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field | 4 | 3 |  |  |  |  |  | 7 |
| Analytical | 5 | 13 |  |  |  |  | 30 | 48 |
| Travel | 3 | 2 |  |  |  | 1 | 3 | 9 |
| Workshops | 1 | 2 |  |  |  | 1 | 5 | 9 |
| Reporting/Tech transfer | 1 | 1 |  |  |  |  | 2 | 4 |
| Total | 14 | 21 |  |  |  | 2 | 40 | 77 |

Confidentiality requirements:  As per contracts with clients

RESOURCES 2007-2008

STAFFING-FTEs

Staffing  FTEs   (eg 0.50)  for 2007-2008

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D Kirste | CRC | .35 |  |  |  |  |  |  | .35 |
| S Welch | CRC | .05 |  |  |  |  |  |  | .05 |
| L Ruperto | IK |  |  |  |  | 1 |  |  | 1 |
| A Fabris | IK |  |  |  |  |  |  | 1 | 1 |
| J Josephs | CRC |  | .3 |  |  |  |  |  | .3 |
| B Stevens | IK |  |  |  |  |  | .1 |  | .1 |
| A Crooks | IK |  |  |  |  |  |  | .1 | .1 |
| A Brown | IK |  |  |  |  |  |  | .9 | .9 |
| L Stoian | IK |  |  |  |  |  |  | .1 | .1 |
| G Gouthas | IK |  |  |  |  |  |  | .3 | .3 |
| TBA | IK |  |  |  |  |  | .25 |  | .25 |
| J Keeling | IK |  |  |  |  |  |  | .1 | .1 |
| J Brugger | IK |  | .1 |  |  |  |  |  | .1 |
| S Hore | IK |  |  |  |  |  |  | .2 | .2 |
| M McGeough | IK |  |  |  |  |  |  | .1 | .1 |
| S Hill | CRC |  | .1 |  |  |  |  |  | .1 |
| Total |  | 0.40 | 0.50 |  |  | 1 | .35 | 2.8 | 5.05 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS $K 2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 41 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 41 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

CRC Operating Expenses - $K - 2005-2006   (show allocation per core party)

| Expenditure Item | ANU | AU | CUT | CSIRO | GA | NSW DMR | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field | 4 | 3 |  |  |  |  |  | 7 |
| Analytical | 2 | 2 |  |  |  |  | 4 | 8 |
| Travel | 3 | 2 |  |  |  | 2 | 6 | 13 |
| Workshops | 1 | 2 |  |  |  | 1 | 5 | 9 |
| Reporting/Tech transfer | 1 | 1 |  |  |  |  | 2 | 4 |
| Total | 11 | 10 |  |  |  | 3 | 17 | 41 |

Confidentiality requirements:  As per contracts with clients

| PIRSA costs |  |  |
| --- | --- | --- |
| Vehicle x 1 (vehicle hire, fuel & lubricant, maintenance) | 14500 |  |
| Field costs (allowance 7 weeks for 2 geologist, 3 weeks for 2geologists) | 15400 |  |
| Opperating (office expenses) | 10000 |  |
| Palynology (~60) | 2400 |  |
| Total | 42300 |  |
| Wage of Aaron Brown at consultant rate + on costs | ~85000 |  |
| Industry costs |  |  |
| CHIM (travel, field, analysis, hire of equiptment, salaries, accommodation) | 43500 |  |
| Honeymoon accommodation | 6700 |  |
| Total | 50200 |  |
| Grand Total | 92500 |  |