Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		1.26				(Issued by LEME Head Office)

Submitted by:		Ken McQueen

Date submitted: 	12th May 2005			V6  13 June 2005

Project name:  	Lachlan Fold Belt Project

Abbreviated title: 	Lachlan Fold Belt

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		1

Themes:  Making geochemistry work through cover (5), Understanding regolith processes

Project Leader:  	Ken McQueen

Start date and duration:  July 2004, 2 years (till July 2006)

Participants:	 	ANU, GA

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The Lachlan Fold Belt project is an “umbrella” project set up in July 2004 to contain existing projects and develop LEME research in the geographical area of the Lachlan Fold Belt. There are currently two main components within the project:

- Synthesis products;

- Macquarie Arc under cover.

This proposal seeks funding to complete the work in these two components, in particular the Explorers Guide to western NSW, due for completion by January 2006 and the Tomingley area study in the Macquarie Arc. As part of the Synthesis products project it is planned to further develop the methodologies for producing derivative exploration “Go” maps with the aid of an Honours student in GIS starting February 2006.

Work in the Tomingley area will include testwork on the bio-detection of gold (see separate project proposal by Ian Roach), completion of geophysical characterisation of the transported regolith and investigation of groundwater geochemistry around the Tomingley area to ascertain the possibilities for hydrominex in the region. As part of the groundwater investigation it is also planned to complete a complementary groundwater geochemistry study in the Cobar Goldfield. The rationale for this is to provide information on present groundwater conditions and dispersion processes in an area where we already have a thorough knowledge of the regolith architecture, landscape evolution and geochemical dispersion processes. This study will also complement planned work in the project on “Mechanisms of metal transfer through transported overburden in 3/4D environments”.

Keith Scott will be engaged in an additional externally funded project with Triako Resources at Hera. Ken McQueen will be engaged in small externally funded applications project with Jervois Mining at Miandetta.

Deliverables (outputs):

- An “Explorers Guide” for exploration in the Central West region of NSW.

- Report on the findings of the integrated study of the Wyoming-Tomingley area and recommendations for further work.

- A groundwater model linking groundwater conditions with related regolith geochemistry for the Cobar goldfield.

- Technology transfer workshop to industry stakeholders.

Expected impacts of research (outcomes):

1. 	Knowledge of groundwater dispersion processes in the northern Lachlan Fold Belt under conditions similar to those prevailing at the present time.

2. 	Improved exploration procedures for regolith covered areas of Central West NSW, including for moderate to deep cover.

3. 	An increase in mineral exploration and an improved rate of resource discovery in the regolith covered areas of the Lachlan Fold Belt.

Milestones: (dates of significant events marking scientific progress)

September 2005 release of preliminary exploration models at IGES.

Early 2006 release of explorers guide.

June 2006 (possibly sooner) technology transfer workshops to industry.

Confidentiality requirements

TBA

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ken McQueen | CRC | .3 |  |  |  |  |  |  |  |  |
| Ian Roach | CRC | .1 |  |  |  |  |  |  |  |  |
| Keith Scott | In kind | .2 |  |  |  |  |  |  |  |  |
| Richard Greene | In kind | .10 |  |  |  |  |  |  |  |  |
| TOTAL |  | .70 |  |  |  |  |  |  |  | .70 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Michael Neimanis | ANU | Hons |
| Augustine Alorbi | ANU | Hons/Grad. Dip. |
| TBA | ANU | Hons |
| Kamal Khider | ANU | PhD |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 5.5 |  |
| Committed (definite) external funds | 20 | Triako tied to K. Scott |
| Committed (definite) In Kind | 15 | Industry |
| Total Project Opex | 40.5 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

* Industry In Kind from various companies includes field support and analytical costs

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Completion of Explorers Guide | 3 |  |  |  |  |  |  |  | 3 |
| Groundwater analyses |  |  |  |  |  |  |  |  |  |
| Travel | 1 |  |  |  |  |  |  |  | 1 |
| IGES Perth September | 1.5 |  |  |  |  |  |  |  | 1.5 |
| Total | 5.5 |  |  |  |  |  |  |  | 5.5 |

Complete indicative resource table for following year if appropriate

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ken McQueen | CRC | .25 |  |  |  |  |  |  |  |  |
| Richard Greene | In kind | .15 |  |  |  |  |  |  |  |  |
| Keith Scott | In kind | .2 |  |  |  |  |  |  |  |  |
| Ian Roach | CRC | .1 |  |  |  |  |  |  |  |  |
| TOTAL |  | .85 |  |  |  |  | .1 |  |  | .65 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 6 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 6 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Report preparation | 3 |  |  |  |  |  |  |  | 3 |
| Analyses | 3 |  |  |  |  |  |  |  | 3 |
| TOTAL | 6 |  |  |  |  |  |  |  | 6 |

Complete indicative resource tables for following year if appropriate

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ken McQueen | CRC | .25 |  |  |  |  |  |  |  |  |
| Bear McPhail | In kind | .1 |  |  |  |  |  |  |  |  |
| Ian Roach | CRC | .15 |  |  |  |  |  |  |  |  |
| Keith Scott | In kind | .2 |  |  |  |  |  |  |  |  |
| Richard Greene | In kind | .15 |  |  |  |  |  |  |  |  |
| Lisa Worrall | In kind |  |  |  |  |  | .1 |  |  |  |
| TOTAL |  | .85 |  |  |  |  |  |  |  | .95 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 8 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 8 |  |

| Possible additional external funds (for info) | 8 | Industry |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Workshop-conference | 8 |  |  |  |  |  |  |  | 8 |
| TOTAL | 8 |  |  |  |  |  |  |  | 8 |