Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		1.21

Submitted by:		Colin Pain

Date submitted: 	17 May 2005			V7   27.06.05

External funds altered to show

carry over

Project name:  	Physiographic regions of Australia

Abbreviated title: 	Physiographic regions

Type of project	Industry/Centre

Program:  		1

Themes:

Project Leader:  	Colin Pain

Start date and duration:  1 July 2005, 1 year duration

Participants:	 	Geoscience Australia

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The Australian Collaborative Land Evaluation Program (ACLEP) provided funding to LEME in late 2004-2005 to prepare a national map of physiographic regions. This project was initially proposed for 2004/2005. However, delays in getting the contract signed have meant that it will continue in 2005/2006. This has also led to a slight change in the objectives and outputs.

During 2004/2005 some progress was made, with line work being made available from Queensland and Victoria. There has also been some progress with NSW.

The work plan developed by the ASRIS project leader and the Subcontractor represented by Dr Colin Pain. Technical specifications for the spatial and profile data and interpretations are provided by McKenzie et al (2004). All activities are to be undertaken in collaboration with the relevant state or territory group contribution to ASRIS.

The map will form a basis for a new national regolith map of Australia, although that is not an objective of this project. This project will take mapping results from other LEME regional projects, especially in Northern Territory and South Australia, and incorporate them in the map of physiographic regions.

The project contributes to LEME’s strategic intent by providing a basis for the regional description and explanation of the Australian regolith. It also provides a firm basis on which to extrapolate results obtained from studies of detailed areas to surrounding areas at lower resolution. In particular the project will work with P4 projects in the Murray-Darling Basin.

Deliverables (outputs) and expected impacts of research (outcomes):

- Review the existing characterization of landform and regolith materials for Levels 1–3 in ASRIS and, if necessary, provide a revised scheme acceptable to the Working Group on Land Resource Assessment.

- Review and assess the adequacy of existing mapping at Levels 1–3. These are the agricultural lands of Western Australia and South Australia and the complete states of Victoria and Tasmania

- New line work for Levels 1–3 in ASRIS is being prepared for large areas. Review and modifications, where necessary, are required for rangelands of Western Australia, all of New South Wales; and all of Queensland. These coverages build on existing land-system or broader-level geomorphic stratifications for each region.

- Provide attribute descriptions (landform relief, modal slope and substrate materials) for land-unit tracts using the revised scheme arising from Activity 1.

Milestones: (dates of significant events marking scientific progress)

All deliverable have been promised by December 2005, contingent on the various states providing the line work as required.

Confidentiality requirements

None

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Colin Pain | In-kind |  |  |  |  |  | 0.20 |  |  | 0.20 |
| Contractor | Industry |  |  |  |  |  | 0.20 |  |  | 0.20 |
| TOTAL |  |  |  |  |  |  |  |  |  | 0.40 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested |  |  |
| Committed (definite) external funds | 10 | ACLEP |
| CARRY OVER FROM 04-05 | 10 |  |
| Total Project Opex | 20 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GIS/map preparation |  |  |  |  |  | 20 |  |  |  |
| Total |  |  |  |  |  | 20 |  |  | 20 |