Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		1.33				(Issued by LEME Head Office)

Submitted by:		Lisa Worrall

Date submitted: 	20/05/05			V7 19 June 2005

Changes by CEO

Project name:  	Exploration through Cover in the Tanami

Abbreviated title: 	Tanami

Type of project	Centre/Industry		(Centre or Industry/Commercial):

Program:  		One

Themes:  		1. Understanding of regolith processes

2. Models of regolith landscape evolution

4. Regional mineral exploration studies

5. Making geochemistry more effective

Project Leader:  	Lisa Worrall

Start date and duration:  01/07/05 3 years

Participants:	ANU, AU, CUT, GA, (NTGS, GSWA, Tanami Gold NL, Newmont Australia, Barrick Gold)

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

The Tanami Region is host to a number of significant gold deposits however, exploration of the region is hampered by the extensive development of regolith; comprised of both in situ and transported regolith materials.

Representatives of CRC LEME, GA, NTGS, GSWA and the three mining companies currently operating in the Tanami (Newmont, Tanami Gold and Barrick Gold) met in Perth in November 2004 and agreed to collaborate in order to maximize the impact of regolith research on the effectiveness of mineral exploration in the Tanami. It was also agreed that this collaboration would be facilitated by CRC LEME

The objective of the Tanami collaborative regolith research program is to develop an effective means of exploring through the cover. The achievement of this objective will be measured by an increase in successful exploration activity.

The strategy to achieve this objective will progress through three phases:

A	acquisition of data on the terrain which can be used to construct hypotheses about the processes dispersing elements and forming anomalies

B	construction of the explanatory hypotheses and

C	tests of the predictive capability of the explanatory hypotheses.

The work plan has seven elements:

1	mapping the character and disposition of regolith materials (including

groundwater) in 3D

2    	developing an understanding of the post-mineralisation geomorphic history of the Tanami Region

3	characterising contemporary dispersion processes (physical and chemical;

including hydro-geochemical, biogeochemical and electro-chemical processes)

4	identifying palaeo-dispersion processes

5	developing an exploration strategy

6	developing and implementing an effective transfer and training strategy

7	tracking results and revising the recommended exploration strategy based on   experience.

This project will have close interaction with the Generic Process projects in Programs One and Two; especially the Geochronology, Geophysical Signatures of Regolith, the HydroMinEx and Gold and Metal Mobility Projects.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

- Reports

- 4D model of regional regolith landscape evolution

- Recommendations about appropriate sampling media

- Recommendations about pre-competitive data acquisition

- Publications in national and international journals

- Presentations at national and international conferences

Outcomes

1) Improved effectiveness of exploration through cover in the Tanami

Milestones: (dates of significant events marking scientific progress)

March 2005 	Reconnaissance fieldwork at the Coyote Prospect

March 2005	Fieldwork Program Completion Report

Oct 2005 	Reports on the results of the Coyote Fieldwork Program and Review Meeting (Ivy Camp, Granites)

Oct 2005	Reconnaissance fieldwork at the Titania Prospect

Oct	 2005 		Fieldwork Program Completion Report

Nov 2005 	Reports on the results of both Fieldwork Programs and Review Meeting (AU, Adelaide)

Mar – May 2006	Additional fieldwork testing the predictive capability of hypotheses developed at the review meetings in Sept and Nov

June – Aug 2006   Completion Reports

Confidentiality requirements

All proposed publications and public presentations to be reviewed by the collaborating parties

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lisa Worrall | IK |  |  |  |  |  | 30 |  |  | 30 |
| Steve Hill | CRC |  | 30 |  |  |  |  |  |  | 30 |
| Nick Direen | IK |  | 30 |  |  |  |  |  |  | 30 |
| Brad Pillans | IK | 10 |  |  |  |  |  |  |  | 10 |
| Dirk Kirste/Bear McPhail | IK | 30 |  |  |  |  |  |  |  | 30 |
| Mehrooz Aspandiar | CRC |  |  | 40 |  |  |  |  |  | 40 |
| GIS support |  |  |  |  |  |  | 40 |  |  | 40 |
| TOTAL |  | 30 | 60 | 40 |  |  | 30 |  |  | 210 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Anna Petts | AU | PhD |
| Nathan Reid (Non LEME) | AU | PhD |
| New Student (Non LEME) | ANU | PhD |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 56.5 |  |
| Committed (definite) external funds |  |  |
| Committed In Kind | 80* | Industry |
| Total Project Opex | 56.5 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

* TGNL and Newmont Australia are providing in kind support; especially food accommodation, vehicles, fuel and field assistance. The total value of such support is in excess of $30k/a.  GA are also providing XRF, ICP-MS and XRD analyses as in kind support. The value of this support is in excess of $50k/a

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel | 4 | 4 | 3 |  |  | 3 |  |  | 14 |
| Vehicle hire and expenses | 1.5 | 1.5 | 1.5 |  |  | 3 |  |  | 7.5 |
| Incidentals |  |  |  |  |  |  |  |  |  |
| Geophysical equipment hire |  | 8 |  |  |  |  |  |  | 8 |
| Freight | 2 | 2 | 1 |  |  |  |  |  | 5 |
| Assays | 6 | 4 | 4 |  |  |  |  |  | 16 |
| Thin sections |  | 1 | 2 |  |  |  |  |  | 3 |
| Drafting and report production |  |  |  |  |  | 5 |  |  | 5 |
| Total | 13.5 | 20.5 | 11.5 |  |  | 11 |  |  | 56.5 |

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lisa Worrall | IK |  |  |  |  |  | 30 |  |  | 30 |
| Steve Hill | IK |  | 30 |  |  |  |  |  |  | 30 |
| Nick Direen | IK |  | 30 |  |  |  |  |  |  | 30 |
| Brad Pillans | IK | 10 |  |  |  |  |  |  |  | 10 |
| Dirk Kirste/Bear McPhail | IK | 30 |  |  |  |  |  |  |  | 30 |
| Mehrooz Aspandiar | CRC |  |  | 40 |  |  |  |  |  | 40 |
| GIS Support |  |  |  |  |  |  | 40 |  |  | 40 |
| TOTAL |  | 40 | 60 | 40 |  |  | 70 |  |  | 210 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Anna Petts | AU | PhD |
| Nathan Reid (Non LEME) | AU | PhD |
| New Student (Non LEME) | ANU | PhD |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 73.5 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 73.5 |  |

| Possible additional external funds (for info) | 80* |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel | 6 | 6 | 3 |  |  | 3 |  |  | 18 |
| Vehicle hire and expenses | 1.5 | 1.5 | 1.5 |  |  | 3 |  |  | 7.5 |
| Incidentals | 1 | 1 | 1 |  |  | 1 |  |  | 4 |
| Geophysical equipment hire |  | 11 |  |  |  |  |  |  | 11 |
| Freight | 2 | 2 | 1 |  |  |  |  |  | 5 |
| Assays | 8 | 6 | 6 |  |  |  |  |  | 20 |
| Thin sections |  | 1 | 2 |  |  |  |  |  | 3 |
| Drafting and report production |  |  |  |  |  | 5 |  |  | 5 |
| Total | 18.5 | 28.5 | 14.5 |  |  | 12 |  |  | 73.5 |

* TGNL and Newmont Australia are providing in kind support; especially food accommodation, vehicles, fuel and field assistance. The total value of such support is in excess of $30k/a.  GA are also providing XRF, ICP-MS and XRD analyses as in kind support. The value of this support is in excess of $50k/a

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lisa Worrall | IK |  |  |  |  |  | 30 |  |  | 30 |
| Steve Hill | IK |  | 30 |  |  |  |  |  |  | 30 |
| Nick Direen | IK |  | 30 |  |  |  |  |  |  | 30 |
| Brad Pillans | IK | 10 |  |  |  |  |  |  |  | 10 |
| Dirk Kirste/Bear McPhail | IK | 30 |  |  |  |  |  |  |  | 30 |
| Mehrooz Aspandiar | CRC |  |  | 40 |  |  |  |  |  | 40 |
| GIS Support |  |  |  |  |  |  | 40 |  |  | 40 |
| TOTAL |  | 30 | 60 | 40 |  |  | 70 |  |  | 210 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Nathan Reid (Non LEME) | AU | PhD |
| New Student (Non LEME) | ANU | PhD |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 59.5 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 59.5 |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel | 3 | 3 | 1.5 |  |  | 1.5 |  |  | 9 |
| Vehicle hire and expenses |  |  |  |  |  | 3 |  |  | 3 |
| Incidentals | 1 | 1 | 1 |  |  | 1 |  |  | 4 |
| Geophysical equipment hire |  | 5 |  |  |  |  |  |  | 5 |
| Freight | 1 | 1 | .5 |  |  |  |  |  | 2.5 |
| Assays | 4 | 3 | 3 |  |  |  |  |  | 10 |
| Thin sections |  | 1 | 2 |  |  |  |  |  | 3 |
| Drafting and report production | 1 | 1 | 1 |  |  | 5 |  |  | 8 |
| Conferences | 4 | 4 | 4 |  |  | 3 |  |  | 15 |
| Total | 14 | 19 | 13 |  |  | 13.5 |  |  | 59.5 |