# Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		2.44				(Issued by LEME Head Office)

Submitted by:		Tim Munday

Date submitted: 	17 May 2005			V4 19 June 2005

Changes by CEO

# Project name:  Objective Logging of Regolith Materials

# Abbreviated title: 	Objective Logging

Type of project	Centre			(Centre or Industry/Commercial):

# Program:  2

# Themes:

# Project Leader:  Tim Munday

# Start date and duration:  July 2005 – June 2008

# Participants:	 CSIRO EM, PIRSA, GA

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

# Background

The project aims to develop practical automatic interpretation tools for logging regolith materials returned as core, drill chips, or pulps. It also aims to better define the regolith mapping and predictive modelling capabilities of spectral data acquired from imaging spectrometers such as HyMap.  The intent is to provide the exploration geologist, mining engineer, geomorphologist or environmental scientist with meaningful, objective information of regolith materials to aid geological, geophysical, geotechnical and geochemical interpretation. A key part of the project is to develop automated procedures that permit rapid differentiation of regolith materials by exploiting contrasts in mineralogical, geochemical and petrophysical characteristics. Speed, repeatability and objectivity in interpretation are critical. The aim is to present the results in a form that can be used by non-specialists.

The goal is not to replace the experienced geological interpretation of materials in their spatial and temporal context, but to complement and refine this knowledge through the rapid analysis and presentation of mineralogical (spectral), geochemical (hand held XRF) and multi-parameter petrophysical (magnetic susceptibility, natural gamma, electrical) measurements of regolith samples. The project technology will aid the definition of 3D and 4D models of regolith and landscape with exploration and environmental applications. Project activities will develop and support interactions with other LEME studies in SA, WA, NT and NSW, as resources permit.

The project will place particular emphasis on the development of spectral logging procedures, using CRCLEME’s ASD and PIMA instruments, as these add significantly to our understanding of the nature and distribution of regolith materials in 3D. Spectro-mineralogical R&D will address issues arising from dealing with pulps (and chips) relative to spectral characteristics of equivalent whole rocks. We suspect some grain size, dilution or masking effects for certain types of pulps with certain minerals. We will develop new spectral library matching approaches specific to regolith materials based on a priori knowledge of proportions derived from XRD and XRF.

The potential for the commercialisation of algorithms and procedures will be investigated in conjunction with CSIRO EM Detection Technology Group who are planning commercialisation of Hylogging technologies.

We propose to develop and conduct a training workshop with AUSSpec for the  mining and exploration industry and their service providers, to promote understanding and awareness of the developed  technologies. We will explore opportunities for incorporation of objective logging technologies into the exploration workflow by developing one-to-one partnerships with exploration companies. This will assist in determining the nature and form of mineralogical and derived data that is of most value.

Specific Objectives for 2005-6 include:

- Report on two case studies detailing the application of spectral logging through the regolith.  This will include continued development of procedures to recognise and quantify various poorly ordered clay minerals and their mixtures. This will involve a number of site studies, the first being Moolart Well.

- Investigate quantifying quartz in regolith materials using the MID infra-red and partial least squares methods.

- Develop quantitative mineralogical criteria of the regolith that can be used to model spectral information from both remote (HyMap and ASTER) and field/mine (Chiplogger, HyLogger, PIMA and ASD) systems for more efficient mapping of the regolith.  This will be conducted in the Kalgoorlie area.

- Report on the automated interpretation of regolith minerals using spectral data

- Report on the value and relevance of spectral logging from a trial of automated logging procedures in the exploration workflow (Quasi-operational application of CRCLEME Logging table)

- Discussion document on commercialisation opportunities for objective logging technologies

- Conduct of workshop on Spectral indices for use in regolith settings.

- Refereed publication on regolith mapping/modelling using hyperspectral data linked to field investigations.

- Compilation of related papers for publication in a thematic journal (eg AJES) on the use of spectral technologies in mineral exploration through the regolith.

# Deliverables (outputs) and expected impacts of research (outcomes):

# Outputs (Over a 3 year timeframe)

- Continued development and documentation of spectral and portable XRF techniques applied to control data sets and case studies from a range of regolith settings across Australia.

- Continued development of procedures to recognise and quantify various poorly ordered clay minerals and their mixtures. This will be achieved by conducting a number of site studies including the Moolart Well area in the Yilgarn.

- Report on the value and relevance of spectral logging from a trial of automated logging procedures in the exploration workflow (Quasi-operational application of  CRCLEME Logging table)

- Supplementary technical report on the applicability of statistical procedures for the auto-interpretation of spectral, multi-parameter petrophysical, mineralogical and ancillary data of core and other samples for a case study over a mineralised system.

- Development and commercial implementation of algorithms for the rapid, objective interpretation of multi-parameter logs and presentation of interpreted results, including new spectral matching techniques specific to regolith materials. Specifically this will entail the further development and reporting on automated unmixing algorithms and will involve:

- Acquisition of additional regolith minerals of interest that are close to “pure”

- Development of “low frequency” spectral feature matching appropriate to unmixing algorithms

- Development of better compression techniques for processing and analysis

- Reducing the misrepresentation and poor estimation of  particular mineral species

These approaches will be implemented into TSG software as appropriate

- Definition of the hardware and simple software for mineralogical interpretation systems required by potential commercial suppliers (analytical labs) to be able to make these sorts of measurements routinely collaborative with CSIRO EM.

- Regolith models linked to hyperspectral image maps for the Kalgoorlie area

- Technology transfer workshops with industry (including analytical labs) – to raise awareness and broaden industry acceptance and adoption of techniques developed.

- Conduct of a workshop to define and document regolith “Spectral indices” which can be incorporated into commercial software (TSG).

- Refereed publication on regolith mapping/modelling using hyperspectral data linked to field investigations.

- Compilation of related papers for publication in a thematic journal on the use of spectral technologies in mineral exploration through the regolith

- White paper discussion document on commercialisation avenues and opportunities.

# Outcomes

- Routine acquisition of mineralogical (spectral) data with geochemical data in exploration through the regolith, resulting in more effective exploration, targeting and priority setting.

- Better value from drillhole data, through the provision of regolith material and mineralogical information.

- Take up of auto-interpretation procedures by the exploration sector (through analytical labs?) to aid geological and geochemical interpretation in regolith settings

- More efficient and effective exploration in areas of cover, through ready identification of significant regolith boundaries, and better discrimination of bedrock/alteration variations in the regolith.

# Milestones: (dates of significant events marking scientific progress) 2005-6

- November 2005: 	Workshop with CRC and interested scientists, industry partners, to define and document “regolith spectral indices” for incorporation into TSG software as templates. Presentation of Moolart Well study results in the workshop to industry partners and interested scientists.

- December 2005: Agreement by Journal for publication for thematic issue on spectral technologies applied to exploration through the regolith.

- March 2006:

  - Supplmentary report on trial of statistically-based procedures for the automatic logging of multi-parameter petrophysical logs of regolith core (materials) from different geological settings.

  - Report on development of spectral unmixing techniques.

- May 2006: 	White paper on commercialisation opportunities of CRCLEME objective logging technologies (Collaborative with CSIRO EM).

- May 2006: Submission of 2 papers for publication in refereed journal on spectral technologies for mapping and exploration through the regolith

- June 2006: Development and implementation of new algorithms (Regolith Templates) for the spectral interpretation and objective logging/analyses of regolith materials using TSG software.

- June 2006:	Moolart Well site study report.

- June 2006: 	Project progress report

Research progress will be formally reported through Quarterly reports and a final project report. Reports will be prepared in digital format for ready dissemination by electronic means.

# Confidentiality requirements:   None

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

# STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tim Munday | IK |  |  |  | 0.45 |  |  |  |  |  |
| C Phang | CRC |  |  |  | 0.4 |  |  |  |  |  |
| B. Singh | CRC |  |  |  | 0.6 |  |  |  |  |  |
| A. Hackett | IK |  |  |  | 0.15 |  |  |  |  |  |
| A. Cornelius | CRC |  |  |  | 0.1 |  |  |  |  |  |
| Tom Cudahy | IK |  |  |  | 0.25 |  |  |  |  |  |
| Alan Mageur | IK |  |  |  |  |  |  |  | 0.1 | 0.1 |
| TOTAL |  |  |  |  | 1.95 |  |  |  |  | 2.05 |

# All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |

# PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 48 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 48 |  |

| Possible additional external funds (for info) | 5-10K | Industry partners |
| --- | --- | --- |

# DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

# Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel and accommodation for field investigations |  |  |  | 8K |  |  |  | 2K | 10 |
| Sample preparation |  |  |  | 2.5K |  |  |  |  | 2.5 |
| Analysis – XRD and petrophysical |  |  |  | 11.5K |  |  |  |  | 11.5 |
| Contracting – unmixing algorithm development |  |  |  | 19.5K |  |  |  |  | 19.5 |
| Logger/ASD maintenance |  |  |  | 3K |  |  |  |  | 3 |
| Industry/ commercialisation Workshop materials etc |  |  |  | 2K |  |  |  |  | 2 |
| Contingencies, lab supplies |  |  |  | 0.5K |  |  |  |  | 0.5 |
| Reporting, VRU support |  |  |  | 2K |  |  |  |  | 2 |
| Conference and workshop – spectral technologies and application Publications costs and printing |  |  |  | 8 |  |  |  |  |  |
| Total |  |  |  | 46 |  |  |  | 2 | 48 |

# RESOURCES 2006-2007

# STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tim Munday | IK |  |  |  | 0.45 |  |  |  |  |  |
| C Phang | CRC |  |  |  | 0.4 |  |  |  |  |  |
| B. Singh | CRC |  |  |  | 0.6 |  |  |  |  |  |
| A. Hackett | IK |  |  |  | 0.15 |  |  |  |  |  |
| A. Cornelius | CRC |  |  |  | 0.1 |  |  |  |  |  |
| TOTAL |  |  |  |  | 1.7 |  |  |  |  | 1.7 |

# All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

# PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 40 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 40 |  |

| Possible additional external funds (for info) | 5-10 | Industry |
| --- | --- | --- |

# DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel and accommodation |  |  |  | 4K |  |  |  | 2K | 6 |
| Sample preparation |  |  |  | 2K |  |  |  |  | 2 |
| Analysis – XRD and petrophysical |  |  |  | 5K |  |  |  |  | 5 |
| Contracting – unmixing algorithm development |  |  |  | 20K |  |  |  |  | 20 |
| S/W maintenance |  |  |  | 3K |  |  |  |  | 3 |
| Industry/ commercialisation Workshop materials etc |  |  |  | 2.5K |  |  |  |  | 2.5 |
| Contingencies, lab supplies |  |  |  | 0.5K |  |  |  |  | 0.5 |
| Reporting, VRU support |  |  |  | 1K |  |  |  |  | 1 |
| Total |  |  |  | 38 |  |  |  | 2 | 40 |

# RESOURCES 2007-2008

# STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LWr | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tim Munday | IK |  |  |  | 0.45 |  |  |  |  |  |
| C Phang | CRC |  |  |  | 0.4 |  |  |  |  |  |
| B. Singh | CRC |  |  |  | 0.6 |  |  |  |  |  |
| A. Hackett | IK |  |  |  | 0.15 |  |  |  |  |  |
| A. Cornelius | CRC |  |  |  | 0.1 |  |  |  |  |  |
| TOTAL |  |  |  |  | 1.7 |  |  |  |  | 1.7 |

# All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |

# PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 27 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | 27 |  |

| Possible additional external funds (for info) | 25 | Industry |
| --- | --- | --- |

# DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

# Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Travel and accommodation |  |  |  | 2K |  |  |  | 0.5K | 2.5 |
| Analysis – XRD and petrophysical |  |  |  | 3K |  |  |  |  | 3 |
| Contracting – unmixing algorithm development |  |  |  | 15K |  |  |  |  | 15 |
| S/W maintenance |  |  |  | 3K |  |  |  |  | 3 |
| Industry/ commercialisation Workshop materials etc |  |  |  | 2K |  |  |  |  | 2 |
| Contingencies, lab supplies |  |  |  | 0.5K |  |  |  |  | 0.5 |
| Reporting, VRU support |  |  |  | 1K |  |  |  |  | 1 |
| Total |  |  |  | 26.5 |  |  |  | 0.5 | 27 |