Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		3.18				(Issued by LEME Head Office)

Submitted by:		S. Lamontagne

Date submitted: 	13 May 2005			V3 (2.6.05)

Project name:  	Impact of water level draw downs on the geochemistry of saline River Murray wetlands

Abbreviated title: 	Loveday Drawdown

(Part of Loveday Wetland Rehabilitation

with Loveday Geomicrobiology ASS 3.19)

Type of project	Centre				(Centre or Industry/Commercial):

Program:  		3. Environmental Applications of Regolith Geoscience

Themes:  		Acid sulfate soils

Project Leader:  	S Lamontagne

Start date and duration:  Start:  1 July 2004; Finish:  1 July 2007

Participants:	 	Lamontagne, Hicks

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

During the last century, many floodplain wetlands in the Murray Basin were converted into disposal basins to store excess irrigation water.  From an ephemeral freshwater environment, these wetlands became permanently flooded and saline.  These modifications to the hydrology of the wetlands had a profound impact on their biodiversity values, including the loss of riparian red gum and native fish species.

Loveday Wetland (Barmera, SA) was used extensively as a disposal basin from the 1970s to the early 2000s, during which time it became severely degraded.  The wetland has been recently selected as the case study for the rehabilitation of disposal basins in River Murray floodplains.  One of the challenges facing managers to rehabilitate disposal basins is how to deal with sulfidic materials present in the sediments.  Sulfidic materials were identified at Loveday Wetland during a previous CRC LEME study (Lamontagne et al 2004).  Sulfidic materials are known to have potential environmental risks when disturbed (that is, exposed to oxygen), including the generation of noxious smells and acidification.  Because rehabilitation of Loveday Wetland will involve changes water level, and possible exposure of sediments to the atmosphere, the risks associated with sulfidic materials are significant.

The aim of the Loveday Drawdown project is to develop knowledge and tools that will enable a safer management of the water level regime in Loveday Basin.  This will be done through:

- reconstruction of historical water, salt and sulfur balances for the wetland between 1970 and 2000 (when the wetland was used as a disposal basin);

- monitoring of surface water quality to follow impacts of water level variations over the next two years;

- literature review on mechanisms causing noxious smells in sulfide-rich wetlands;

- estimation of gaseous S losses from the wetland in partnership with the DWLBC Odour control program..

The current storage of S in the wetland and the assessment of biogeochemical processes in sediments during wetting-drying operations will be done through the CRC LEME Project 3.19 Loveday Drawdown.

Deliverables (outputs) and expected impacts of research (outcomes):

Outputs

1)  Report on historical water, salt and S budgets for the wetland;

2)  Report on water quality changes and sulfur mass-balance during wetting-drying operations between 2005 and 2007;

3)  Literature review on sulfur gas emissions from wetlands;

4)  Report on gaseous S losses from the wetland between 2005 and 20007;

5)  Produce a simple hydrological-biogeochemical model to predict how changes in wetland water regime result in gain or loss of sulfidic materials over time.

6)  Present national and international scientific conferences; write several scientific journal papers.

Outcomes

1)  Participation to the design of the rehabilitation program for Loveday Wetland with SA DWLBC;

2)  Knowledge to help manager assess and mitigate the risks associated with sulfidic materials during wetland rehabilitation efforts across the Murray-Darling Basin;

Milestones: (dates of significant events marking scientific progress)

| Milestone date | Description | Status at May 2005 |
| --- | --- | --- |
| 1. Dec 2004 | Selection of field site | Completed |
| 2. Apr 2005 | Preliminary compilation of historical water, salt and sulfur budgets for Loveday | Completed |
| 3. May 2005 | Contract with DWLBC for 2005/06 monitoring program | On track |
| 4. May 2005 | Start of water quality monitoring program | On track |
| 5. Dec 2005 | Literature review on the significance of S gas emissions from wetlands | On track |
| 6. May 2006 | Contract with DWLBC for 2006/07 monitoring program | Incomplete |
| 7. Jun 2006 | Report on first year of monitoring program | Incomplete |
| 8. Jun 2006 | Final Report on historical water, salt and sulfur budgets for the wetland | Incomplete |
| 9. Mar 2007 | End of monitoring program | Incomplete |
| 10. Jun 2007 | Final report | Incomplete |

Confidentiality requirements

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lamontagne | CRC |  |  |  |  | 0.05 |  |  |  |  |
| Lamontagne | in kind |  |  |  |  | 0.20 |  |  |  |  |
| Hicks | CRC |  |  |  |  | 0.10 |  |  |  |  |
| Hicks | in kind |  |  |  |  | 0.10 |  |  |  |  |
| TOTAL |  |  |  |  |  | 0.45 |  |  |  |  |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | $35K |  |
| Committed (definite) external funds | $10K | DWLBC* |
| Total Project Opex | $45K |  |

*contract drafted

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Monitoring station |  |  |  |  | $8K |  |  |  |  |
| Water quality analyses |  |  |  |  | $15K |  |  |  |  |
| Isotopic analyses |  |  |  |  | $6K |  |  |  |  |
| Benthic primary production |  |  |  |  | $6K |  |  |  |  |
| Travel and accommodations |  |  |  |  | $10K |  |  |  |  |
| Total |  |  |  |  | $45K |  |  |  |  |

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lamontagne | CRC |  |  |  |  | 0.05 |  |  |  |  |
| Lamontagne | in kind |  |  |  |  | 0.20 |  |  |  |  |
| Hicks | CRC |  |  |  |  | 0.10 |  |  |  |  |
| Hicks | in kind |  |  |  |  | 0.10 |  |  |  |  |
| TOTAL |  |  |  |  |  | 0.45 |  |  |  |  |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | $40K |  |
| Committed (definite) external funds |  |  |
| Total Project Opex | $40K |  |

| Possible additional external funds (for info) | $10K | DWLBC |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Monitoring station |  |  |  |  | $8K |  |  |  |  |
| Water quality analyses |  |  |  |  | $14K |  |  |  |  |
| Isotopic analyses |  |  |  |  | $8K |  |  |  |  |
| Travel and accommodations |  |  |  |  | $10K |  |  |  |  |
| Total |  |  |  |  | $40K |  |  |  |  |