Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		3.23				(Issued by LEME Head Office)

Submitted by:		Steve Rogers

Date submitted: 	13.05.05			V3  (2.6.05)

Project name:  	Engineering Evaluation Initiative Phase II-Wheat belt Geochemistry Risk Assessment

Abbreviated title: 	EEI-Geochem Phase II

Type of project	Centre-Industry (WA EEI, CALM, Avon Catchment Council) co-investment				(Centre or Industry/Commercial):

Program:  		3

Themes:  		Acid Sulfate Soils

Project Leader:  	Steve Rogers (part-time)

Start date and duration:  01.-7.05-30.06.08

Participants:	 CRC LEME, CSIRO L&W, Agriculture WA, DoE WA, CALM, WA EEI, Avon CC, Yarra Yarra CC, WA  Channel Management Group

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

This project will be a new initiative based on the current CRC LEME Project 3.15.  Drainage geochemical risk assessments will be expanded beyond their current focus in the Avon Catchment. The Engineering Evaluation Initiative is a program founded, supported and largely funded by WA government agencies (principally WA Ag Dep,  CALM) and relevant Catchment Authorities) to evaluate engineering options for environmental rehabilitations in agricultural areas subject to salinity risk.

Original proposal to EEI attached to this Project Summary

New initiatives for drainage geochemistry risk assessment will comprise four main foci (assuming duration of three years FY 2005-2008):

- Pilot geochemical evaluation of specific engineering projects

- Assessment of potential trace-element risk risks

- Geochemical risks to receiving environments

- Active management of acid-trace element rich drainage waters

- Project coordination

Details of focus and outputs

- Pilot Geochemical Evaluation

Pilot drainage studies will focus on selected sites of the Engineering Evaluation Initiative Stage 2 (EEI-2):

  - Yenyenning

  - Yarra Yarra (specific site to be determined)

  - Two others - to be determined

Outputs

- Database of analyses of surface waters, drain waters and groundwaters

- Prediction of drainage water characteristics (geochemistry, pH) prior to drain installation based on groundwater hydrogeochemistry, soil pit geochemistry, regolith and basement geology, and geochemistry of proposed receiving environments.

- Prediction of geochemical risk to receiving environments and recommend management options based on ii above.

- Observation of pilot drain geochemistry if drain installed (validation of predictions)

- Regional Geochemical Risk Assessment

Regional geochemical surveys at a scale commensurate to that undertaken in Phase 1, Avon River Geochemical Risk Assessment (2005).  New catchments to include:

  - Yarra Yarra

  - Moore River (to be defined by consultation)

  - Upper Blackwood (to be defined by consultation)

  - South Coast (to be defined by consultation)

Outputs

- Review of existing data on acid groundwater trace element geochemistry, soil types, regolith architecture, trace element analysis, flow regimes and, remote sensing data.

- Geochemical reconnaissance (similar to current Avon study) of existing drains, ground and surface waters

- Modelling in support of regional water balance assessments (part of EEI 2) using methods established for the CSIRO-EEI Avon Drainage Modelling project.

- Identification of knowledge gaps and additional data requirements needed to complete regional-scale geochemical risk assessment.

# Additional data collection: data required to fill knowledge gaps identified in Output iv, sampling and detailed geochemical analysis of ground waters and drainage waters, and mineralogical analysis of drainage material (especially Fe precipitates).

- Identification of potential geochemical hazards and risks.

- Geochemical risks of receiving environments

This project will complement assessments in receiving environments being undertaken in the Avon Drainage, as part of Stage two of the current Avon EEI/CRC LEME project. The aspect will focus on:

  - playas and other natural wetlands,

  - surface waters (rivers, creeks)

  - engineered wetlands and disposal basins (Morowa, Bodallin)

Our project will provide assistance with site selection, and forge research partnerships with CALM and other partners, focussing on key receiving environments.  Priory will be given to existing or proposed community drainage projects.

Outputs

- Determination of trace-element and heavy-metal loadings to receiving environments from drains

- Prediction of trace-element and heavy-metal behaviour in receiving environments (proportion of material that remains in solution, as distinct from precipitation and incorporation into sediments).

- Geochemical speciation of trace-element and heavy-metals in receiving environment sediments.

- Determination of scenarios where sediment-bound trace elements and heavy metals may be re-solubilised and re-enter the aqueous phase

- Determination of long-term acid buffering capacity of alkaline receiving environments, and estimation of  useful life for acid drainage disposal

- Management options for minimising risks of trace elements in receiving environments

- Active management

This project will be developed after year two of the current EEI project and is planned for year 2 of the EEI-2 Project.  Effective management can only be developed after the water geochemistry and risks have been assessed.

Outputs

Demonstration of active and passive management options for acid drainage with partners

- Project coordination

A project of this magnitude requires a WA-based project manager, to coordinate day-to-day activities of scientific and community partners, including fieldwork, sampling, community liaison, data management. Detailed management requirements will be determined once the project scope and budget has been agreed.

Outputs

EEI-2 Reporting

Research Management

Project Communication

Deliverables (outputs) and expected impacts of research (outcomes):

See outputs above

Outcomes

- Evaluation of drainage through careful assessment of risk, opportunities and the determination of effective management systems.

- Enable NRM regions and stakeholder groups to develop a consistent approach to catchment and regional drainage, with minimal off site environmental impact.

Milestones: (dates of significant events marking scientific progress)

To be developed in consultation with proponents

Confidentiality requirements

Permission to be sought from WA DoE EEI (John Ruprecht) prior to media contact

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. Rogers | IK |  |  |  |  | 0.2 |  |  |  |  |
| R. Fitzpatrick | IK |  |  |  |  | 0.10 |  |  |  |  |
| D.Gray | IK |  |  |  | 0.10 |  |  |  |  |  |
| D.Gray | Industry |  |  |  | 0.15 |  |  |  |  |  |
| TOTAL |  |  |  |  | 0.25 | 0.30 |  |  |  | 0.55 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 50 |  |
| Committed (definite) external funds |  |  |
| Total Project Opex |  |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |
|  | 100 | WA EEI Phase II |
|  | 50 | CALM |
|  | 100 | Avon CC |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Non-CRC* | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project co-ordination (30% salary) |  |  |  |  |  |  |  |  | 30 | 30 |
| Geochemical Modelling (salary) |  |  |  | 15 | 20 |  |  |  |  | 35 |
| Analytical Technical Assistant (ICP-MS)-Fee for service |  |  |  |  | 35 |  |  |  |  | 35 |
| Analysis (Anions, mineralogy)- -Fee for service |  |  |  |  | 20 |  |  |  |  | 20 |
| Field Sampling consumables |  |  |  | 4 | 4 |  |  |  |  | 8 |
| Field work (vehicles, accommodation, airfares |  |  |  | 7 | 8 |  |  |  |  | 15 |
| Review meetings x 2 |  |  |  | 3 | 3 |  |  |  |  | 6 |
| CALM Wetlands Assessment 50K |  |  |  |  |  |  |  |  |  |  |
| Avon Catchment Assessment 100K |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  | 29 | 90 |  |  |  | 30 | 149 |

* Plan to sub-contract ADWA employee to coordinate project activities in WA