Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		4.22

Submitted by:		Paul Wilkes

Date submitted: 	12 May 2005			V3	Recd 10.6.05

Project name:  	WA Rural Towns

Abbreviated title: 	Rural Towns

Type of project	Commercial + Centre

Program:  		4

Themes:  		Salinity systems in regolith and groundwater

Project Leader:  	Paul Wilkes

Start date and duration:  April 2004 to June 2007

Participants:	 	CUT plus external agencies

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

This is a continuing project which began in 2004.

Urban salinity has a significant impact on 38 rural towns in WA. The Rural Towns – Liquid Assets project is a major multi-party initiative convened by WA Dept of Ag. This major initiative contributes to effective salinity control and shows how locally sourced saline groundwater may be treated and turned into a resource. This three-year project is working on 16 of the most salt affected towns.

CRC LEME is a partner in the overall project with CUT, CSIRO including Water for a Healthy Country, Department of Agriculture WA,

WA Chemistry Centre and UWA, Water Corporation and the 16 Shires

LEME contributes basic regolith information to better understand the geology and hydrogeology of the towns and related catchments. Geophysical surveys and existing datasets are being used to provide regolith information including regolith thickness and geological structures which affect the regolith and salt distribution within the regolith. New challenges include working effectively in urban built environments with powerlines, people, vehicles etc.

Some surveys are sub-contracted to commercial groups with LEME providing specification and management of these surveys. Data processing and interpretation are done by LEME staff and students.

All operating costs for this project are externally funded. LEME provides in-kind support through making available 20 % of each of Paul Wilkes and Anton Kepic.

Opportunities will be created for student involvement. The project will include technology transfer and communication both to other project scientists and to the local communities in the towns where we are operating.

Deliverables (outputs) and expected impacts of research (outcomes):

Provide cost effective regolith geoscience information to meet the overall objectives of Rural Towns – Liquid Assets project. This includes research results and case histories on how to apply geophysical methods in urban environments and how this contributes to a multi-disciplinary, multi-facetted project.

Maps, reports, datasets and interpretations are delivered as project outputs.

Paul Wilkes also provides technical leadership to the multi-disciplinary team and is a member of the overall Steering Committee.

Milestones: (dates of significant events marking scientific progress)

As shown in the accompanying payment schedule which is reproduced from the draft project agreement.

.

| Quarter commencing | Expected payment | Milestone achieved or output delivered |
| --- | --- | --- |
| 1 April 2004 | $60,000 | On signature of the Agreement by both parties |
| 1 July 2004 | $30,000 | On completion of the first Pilot study. Data sets and report delivered. |
| 2 Sept 2004 | $26,973 | On completion of Katanning Project |
| 1 October 2004 | $30,000 | On completion of the second and third Pilot town studies. Data sets and reports delivered. |
| 1 January 2005 | $30,000 | On completion of the fourth Pilot town study. Methodology finalised and ready to apply to Priority towns. Data sets and reports delivered. |
| 1 April 2005 | $30,000 | On completion of four of 12 Priority town studies. Data sets and reports delivered. |
| 1 July 2005 | $30,000 | On completion of eight of 12 Priority town studies. Data sets and reports delivered. |
| 1 October 2005 | $30,000 | On completion of 12 of 12 Priority town studies. Data sets and reports delivered. |
| 1 January 2006 | $60,000 | On production of a final report and financial statement. |
| TOTAL | $326,973 |  |

$ 176,973 plus GST was received in 2004-2005. The balance ( $ 150 K will be received in 2005 - 2006

Confidentiality requirements

The following is an extract from the Project Agreement between CRC LEME and WA Department of Agriculture ( managers of Rural Towns – Liquid Assets project )

The CRC LEME shall treat as confidential all information disclosed to the CRC LEME, made known to the CRC LEME or developed by the CRC LEME during the course of or for the purposes of the Services ("the confidential information").

Without limiting the generality of the preceding sub-clause, the confidential information includes computer programs, client lists, the Department of Agriculture's methods of operation and details of clientele and potential clientele of the Department of Agriculture.

Immediately upon the completion of the Services and the termination of the General Agreement, the CRC shall deliver to the Department of Agriculture all documents, electronic datasets, files and materials relating in anyway to the confidential information which are then in the CRC LEME's possession.

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wilkes | CRC |  |  | 0.2 |  |  |  |  |  | 0.2 |
| Kepic | In-kind |  |  | 0.2 |  |  |  |  |  | 0.2 |
| Harris | Ind |  |  | 0.5 |  |  |  |  |  | 0.5 |
| TOTAL |  |  |  | 0.9 |  |  |  |  |  | 0.9 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Cameron Jones | CUT | Hons |
| Jacob Paggi | CUT | Hons |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | Nil |  |
| Committed (definite) external funds | 150 K | DAWA |
| Total Project Opex | 150 K |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 150 K |  |  |  |  |  | 150 K |
| Total |  |  | 150 K |  |  |  |  |  | 150 K |

Complete indicative resource table for following year if appropriate

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wilkes | CRC |  |  | 0.1 |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested |  |  |
| Committed (definite) external funds |  |  |
| Total Project Opex |  |  |

| Possible additional external funds (for info) |  |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL |  |  |  |  |  |  |  |  |  |