Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  						(Issued by LEME Head Office)

Submitted by:	Richard Cresswell, Dirk Kirste, KP Tan, Jim Cox

Date submitted: 	24.5.05		V5 30.06.05 Text updated DG

Project name: The dynamics of salinity in Australia: Origins, mobilisation and transport of salt in the Australian regolith and response times relating to salinity.

Abbreviated title: 	Salinity Dynamics

Type of project	Centre				(Centre or Industry/Commercial):

## Program:  		4. Salinity mapping and hazard assessment

## Themes:  		1. Understanding regolith processes

3. Acid and alkaline soils

4. Regional mineral exploration studies

5. Making geochemistry more effective

7. Salinity systems in regolith and groundwater

9. Environmental geochemistry and the regolith

Project Leader:  	Richard Cresswell

## Start date and duration:  1 July 2005 for 3 years

Participants:	 	CSIRO Land & Water, Geoscience Australia, ANU

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

Understanding system response time is a vital component in identifying appropriate land management practices for problems of salinity. In particular, the rates of salt mobilisation play a critical role in determining the timeframes of salinity manifestation and amelioration.  This project investigates the physical, chemical and environmental factors influencing salt mobilisation, and integrates this understanding in a broad landscape and climatic context.

This project aims to determine quantitative parameters that address system response times in salinity-prone environments. The following specific questions will be addressed by the project:

- What is the origin of the salt?

This question will be addressed on 3 fronts: isotopic studies (Lenahan, Cresswell); rainfall chemistry studies (Cresswell, Dighton) and through chemical modelling in the unsaturated zone (Rassam, Kirste, Cresswell).

- How does saline water and salt interact with regolith materials?

This will be addressed through geochemical modelling (Kirste, Rassam); column experiments (Kirste) and chemical equilibrium, determined through CEC and XRD analysis (Kirste, Tan, Rassam)

- How and how fast is it mobilized?

Basic hydraulic properties of regolith materials will be determined through field pump tests and laboratory analysis (porosimetry, x-ray tomography, permeability test, etc) on samples collected from drill cores (Tan, Turner, Cresswell, Gilfedder, Dighton). Isotopic studies will help elucidate timeframes for mobilisation and components of the mass balance equations (Cresswell, Lenahan, Kirste). Diffusion and solute flow experiments and modelling will enhance laboratory quantification to compare with field results (Rassam, Cresswell, Kirste).

- Where and at what rate is it transported?

Landscape analysis, hydrology and hydrogeology models will be used to characterise different terrains and model the 3D spatial variability in salinity mobilisation using the parameters determined in 3)(Cox, Davies, Gilfedder, Stenson, Cresswell, Gibson, Tan). Climate as a driver will be examined in well-characterised catchments and the effects of land-use change evaluated (Cresswell, Davies, Stenson).

Components of this project will thus address hydrogeological, hydrochemical, hydrophysical and climatic drivers and indicators through field studies, laboratory investigations and computer modelling. Different components will be conducted at different sites but will be integrated into a coherent synthesis of salt mobility and salt-regolith interaction. A common theme will be quantification of reactions and process rates with a goal of providing confidence levels for salinity risk maps being developed by State agencies and catchment resource managers.

Thus, isotopic and chemical studies will be carried out through CSIRO and ANU and these groups will also incorporate modelling of the results in stochastic and deterministic models of solute flow in up to 4 dimensions.

Physical parameters for regolith materials will mainly be determined through GA.

Fundamental to this project is the choice and detailed investigation of materials that can best define the broadest range of regolith materials. Hence customised drilling for cores will be undertaken to collect material for detailed laboratory analysis. It is proposed that only 2 additional catchments are chosen in the first year so we may focus resources effectively. From previous work on this project, we have significant and detailed information from sites in depositional environments (Bland Creek, Lower Balonne, Murray Floodplains, Goondoola Basin, Corangamite) across static (Bland, L. Balonne) to dynamic (Murray, Goondoola, Corangamite) groundwater regimes. These areas will continue to be investigated, with a focus on on-going laboratory and modelling frameworks.

For the next phase of this project, we wish to focus our field investigations on upland, erosional environments: the feeder catchments for the salt of the Murray-Darling Basin. Current proposals are for a catchment from the Queensland Dividing Range (Hodgson Creek) and one from the southwest slopes of NSW (Boorowa or Spicers Creek).

The project will build on the previous studies carried out under project 4.9 (Salt mobilisation and water quality), and will also incorporate part of 4.25 (Salinity Hazard Mapping) integrating climatic drivers of salinity.

To date, salinity parameters have been largely semi-quantitative. Working constructs, such as groundwater flow systems provide a targeting approach for more detailed studies, but generally involve poor integration of sub-surface regolith constraints. The continuing MDBC-funded project is attempting to redress this issue, but requires quantification of parameters such as hydraulic conductivity, transmissivity, permeability, specific yield and porosity that are specific to regolith materials, particularly where these materials act as groundwater hosts. This information is required at micro- macro- and regional scales.

Water transport properties for the regolith are vital components of transport models, and require detailed quantification. The interaction and ionic exchange of salts, particularly at high salinities, is also critical when deducing potential end-of-valley salt loads and correlating standard electrical conductivity measurements to actual salt impact. Hydrochemical studies aimed at elucidating the transport of salts within, and through, the regolith, are also fundamental to this project. This also links to projects under Programs 2 and 3.

A number of studies show the importance of climatic drivers on salinity. It will not be the intent of this project to develop climatic models, but climate forces will be considered in the context of currently developed hydrogeological models (e.g. BC2C, 2c). Climate trend analysis will be integral to the development of salinity risk maps and will, therefore, come under the scope of this project. This will link to P1.17 History of Aridity.

Deliverables (outputs) and expected impacts of research (outcomes):

Deliverables (Outputs):

- Journal papers, Technical Reports and Open File Reports

- Papers presented at National and International Conferences

- Groundwater models developed in key NRM regions

- Geochemical/solute transport models developed in key NRM regions

- Rainfall chemistry database established

- Rainfall/hydrograph analysis tools

- Look-up tables developed and populated for physical (porosity and permeability), chemical (salinity, sodicity, acidity), physico-chemical (CEC, Adsorption co-efficients, dissolution/precipitation) and hydrogeological (hydraulic conductivity, transmissivity, specific yield) parameters of the regolith for use in hydrogeological and hydrogeochemical models

- 3D hydrogeological and hydrogeochemical frameworks for modelling of key NRM areas

- Communication of results through conferences, workshops and literature

Expected impacts (Outcomes):

- Better assessment of salinity risk

- Better understanding of salinity processes

- Adoption of outputs from airborne geophysics and regolith characterisation projects into salinity management procedures and modelling exercises

- Integration of chemical processes into salinity delivery mechanisms (e.g. salt mobilisation into streams)

- Consolidation of research on the age, origins and distribution of salts in the Australian regolith

- Establishment of hydrogeological dynamics (response times of a system) to changes in land-use and/or climate change

- Demonstration of the relevance of regolith and geophysical information to decision support systems for land management of salinity

Milestones: (dates of significant events marking scientific progress)

Quarterly reports from each Principal Investigators to Project Leader

Quarterly reports from Project Leader to Program 4 Leader and Board

Annual Report of Activities

See attached sheet for milestone details, principal investigator responsibilities and timeline. Major milestones are:

Groundwater models for Corangamite, Bland, Hodgson - June 2006

Geochemical solute models for Bland, Hodgson Goondoola - Jan 2006

Rainfall:hydrograph analysis tools developed – Jun 2007

Integrated look-up tables for salinity modelling - Jun 2008

Confidentiality requirements

Some proprietary requirements for CMAs and State Agencies. Short term Commercial-in-Confidence issues with CMAs and INRM groups.

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Richard Cresswell | CRC |  |  |  |  | X |  |  |  | 0.75 |
| Jim Cox | CRC/IK |  |  |  |  | X |  |  |  | 0.75 |
| KP Tan | CRC |  |  |  |  |  | X |  |  | 0.30 |
| David Rassam | CRC/IK |  |  |  |  | X |  |  |  | 0.40 |
| Phil Davies | CRC/IK |  |  |  |  | X |  |  |  | 0.30 |
| Dirk Kirste | CRC | X |  |  |  |  |  |  |  | 0.25 |
| Heike Apps |  |  |  |  |  |  | X |  |  | 0.20 |
| Mat Gilfedder | CRC/IK |  |  |  |  | X |  |  |  | 0.20 |
| Larysa Halas | CRC |  |  |  |  |  | X |  |  | 0.20 |
| John Dighton | IK |  |  |  |  | X |  |  |  | 0.15 |
| Andrew Fitzpatrick | CRC |  |  |  |  |  | X |  |  | 0.05 |
| Dave Gibson |  |  |  |  |  |  | X |  |  | 0.20 |
| Richard Greene |  | X |  |  |  |  |  |  |  | 0.10 |
| Tony Jakeman | CRC | X |  |  |  |  |  |  |  | 0.05 |
| Matt Stenson | IK |  |  |  |  | X |  |  |  | 0.10 |
| Ken Lawrie | IK |  |  |  |  |  | X |  |  | 0.10 |
| Patrice de Caritat | Ind |  |  |  |  |  | X |  |  | 0.05 |
| Keith Fifield | in-kind | X |  |  |  |  |  |  |  | 0.10 |
| TOTAL |  |  |  |  |  |  |  |  |  | 4.25 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Matt Lenahan | ANU | PhD |
| Michael Turner | ANU | PhD |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 132 |  |
| Committed (definite) external funds | 200 | Corangamite CMA |
| Total Project Opex | 332 |  |

| Possible additional external funds (for info) | 125 | Qld Projects* |
| --- | --- | --- |

* Committed through share of projects with QDNRM: Fitzroy Basin ($20k), Burdekin ($30).

Expected share in QDRNRM projects in: Burnett ($25k), Moonie ($25k), Warrego/Paroo ($25k).

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Drilling (coring) program |  |  |  |  | 15 | 30 |  |  | 45 |
| Physical properties analysis | 2 |  |  |  | 5 | 4 |  |  | 11 |
| Chemical properties analysis | 20 |  |  |  | 10 | 3 |  |  | 33 |
| Consumables | 2 |  |  |  | 3 | 3 |  |  | 8 |
| Travel | 5 |  |  |  | 10 | 5 |  |  | 20 |
| Anal. services (SEM, etc.) | 4 |  |  |  | 0 | 5 |  |  | 9 |
| Publications | 2 |  |  |  | 2 | 2 |  |  | 6 |
| Total | 35 | 0 | 0 | 0 | 45 | 52 |  |  | 132 |

Complete indicative resource table for following year if appropriate

RESOURCES 2006-2007

STAFFING-FTEs

(eg 0.50) for 2006-2007 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Richard Cresswell | CRC |  |  |  |  | X |  |  |  | 0.80 |
| Jim Cox | CRC/IK |  |  |  |  | X |  |  |  | 0.75 |
| KP Tan | CRC |  |  |  |  |  | X |  |  | 0.70 |
| David Rassam | CRC/IK |  |  |  |  | X |  |  |  | 0.40 |
| Phil Davies | CRC/IK |  |  |  |  | X |  |  |  | 0.30 |
| Dirk Kirste | CRC | X |  |  |  |  |  |  |  | 0.25 |
| Heike Apps | CRC |  |  |  |  |  | X |  |  | 0.20 |
| Mat Gilfedder | CRC/IK |  |  |  |  | X |  |  |  | 0.20 |
| John Dighton | IK |  |  |  |  | X |  |  |  | 0.15 |
| Andrew Fitzpatrick | CRC |  |  |  |  |  | X |  |  | 0.10 |
| Matt Stenson | IK |  |  |  |  | X |  |  |  | 0.10 |
| Dave Gibson |  |  |  |  |  |  | X |  |  | 0.20 |
| Richard Greene |  | X |  |  |  |  |  |  |  | 0.10 |
| Tony Jakeman | CRC | X |  |  |  |  |  |  |  | 0.05 |
| Hydro-modeller | CRC |  |  |  |  |  | X |  |  | 0.30 |
| Ken Lawrie | IK |  |  |  |  |  | X |  |  | 0.05 |
| TOTAL |  |  |  |  |  |  |  |  |  | 4.65 |

All LEME STUDENTS contributing to Projects 2006-2007

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Matt Lenahan | ANU | PhD |
| Michael Turner | ANU | PhD |

PROJECT OPERATING COSTS  $K  2006-2007

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 130 |  |
| Committed (definite) external funds | 150 | CCMA |
| Total Project Opex | 280 |  |

| Possible additional external funds (for info) | 145 | Qld projects* |
| --- | --- | --- |

* Expected share in QDRNRM projects in: Western catchments ($40k), Border Rivers ($25k), L Balonne/Maranoa ($40k); Condamine ($40k).

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2006-2007

Show major expenditure items and allocation to core parties. This table is to revised if ‘possible additional external’ funds become definite.

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field program | 5 |  |  |  | 5 | 5 |  |  |  |
| Physical properties analysis | 0 |  |  |  | 5 | 20 |  |  |  |
| Chemical properties analysis | 20 |  |  |  | 20 | 5 |  |  |  |
| Consumables | 4 |  |  |  | 4 | 5 |  |  |  |
| Travel | 4 |  |  |  | 8 | 4 |  |  |  |
| Analytical services | 6 |  |  |  | 0 | 4 |  |  |  |
| Publications | 2 |  |  |  | 2 | 2 |  |  |  |
| Total | 41 | 0 | 0 | 0 | 44 | 45 |  |  | 130 |

Complete indicative resource tables for following year if appropriate

RESOURCES 2007-2008

STAFFING-FTEs

(eg 0.50) for 2007-2008 (minimal fractional contribution should be 0.05)

| Staff Name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Richard Cresswell | CRC |  |  |  |  | X |  |  |  | 0.80 |
| Jim Cox | CRC/IK |  |  |  |  | X |  |  |  | 0.75 |
| KP Tan | CRC |  |  |  |  |  | X |  |  | 0.70 |
| David Rassam | CRC/IK |  |  |  |  | X |  |  |  | 0.40 |
| Phil Davies | CRC/IK |  |  |  |  | X |  |  |  | 0.30 |
| Dirk Kirste | CRC | X |  |  |  |  |  |  |  | 0.25 |
| Heike Apps | CRC |  |  |  |  |  | X |  |  | 0.20 |
| Mat Gilfedder | CRC/IK |  |  |  |  | X |  |  |  | 0.20 |
| John Dighton | IK |  |  |  |  | X |  |  |  | 0.15 |
| Andrew Fitzpatrick | CRC |  |  |  |  |  | X |  |  | 0.10 |
| Matt Stenson | IK |  |  |  |  | X |  |  |  | 0.10 |
| Dave Gibson |  |  |  |  |  |  | X |  |  | 0.20 |
| Richard Greene |  | X |  |  |  |  |  |  |  | 0.10 |
| Tony Jakeman | CRC | X |  |  |  |  |  |  |  | 0.05 |
| Hydro-modeller | CRC |  |  |  |  |  | X |  |  | 0.50 |
| Ken Lawrie | IK |  |  |  |  |  | X |  |  | 0.05 |
| TOTAL |  |  |  |  |  |  |  |  |  | 4.85 |

All LEME STUDENTS contributing to Project 2007-2008

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Michael Turner | ANU | PhD |
| Matt Lenahan | ANU | PhD |

PROJECT OPERATING COSTS  $K  2007-2008

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | 93 | 150 |
| Committed (definite) external funds | ?? | Negotiating1 |
| Total Project Opex | >93 |  |

| Possible additional external funds (for info) | 200 |  |
| --- | --- | --- |

1 Extension of CCMA: VVP project ($100k)

* Expected share in QDRNRM projects in: Western Catchments ($40k), Belyando/Suttor ($25k), Condamine ($40k).

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2007-2008

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field program | 5 |  |  |  | 5 | 5 |  |  | 15 |
| Physical properties analysis | 0 |  |  |  | 2 | 5 |  |  | 7 |
| Chemical properties analysis | 10 |  |  |  | 10 | 5 |  |  | 25 |
| Consumables | 4 |  |  |  | 4 | 4 |  |  | 12 |
| Travel | 5 |  |  |  | 8 | 5 |  |  | 18 |
| Analytical services | 5 |  |  |  | 0 | 5 |  |  | 10 |
| Publications | 2 |  |  |  | 2 | 2 |  |  | 6 |
| Total | 31 | 0 | 0 | 0 | 31 | 31 |  |  | 93 |

Milestone details

| Deliverable | details | milestone date | PI | comments |
| --- | --- | --- | --- | --- |
| Journal papers, Technical Reports and Open File Reports | NAP projects | Jun-06 | RC | Special issues, multiple authors |
|  | Project results | on-going | ALL |  |
| Papers presented at conferences | IAH 2005 | Nov-05 | RC |  |
|  | AIG-6 | Sep-05 | RC | Additional funds from CLW |
|  | ASEG | Jul-06 | RC, KT | Special session on Salinity Mapping, etc |
|  | others as required | on-going | ALL |  |
| Groundwater models developed in key NRM regions | Corangamite, VIC | Jun-06 | JC |  |
|  | Bland Basin, NSW | Jun-06 | DK | input from RC, DR |
|  | Hodgson Creek, QLD | Jun-06 | MS | input from MG, DR, QDNRM; MDBC case-study site |
|  | NSW SW slopes site | Jun-06 | DR | input from MG, MS, QDNRM; MDBC case-study site |
|  | others as required | on-going | ALL | linked to QDNRM and MDBC case-studies |
| Geochemical/solute models developed | effect of salinity on solute models | Jun-06 | DR | input from RC, DK |
|  | Bland Basin, NSW | Jun-06 | DK | input from RC, DR |
|  | Hodgson Creek, QLD | Jun-06 | DR | input from MG, MS, RC, QDNRM; MDBC case study site |
|  | Goondoola Basin, Moonie, QLD | Jun-06 | DR | input from MG, MS, RC, QDNRM; linked to L. Balonne work |
|  | others as required | on-going |  | linked to MDBC case-studies |
| Rainwater chemistry database | National collector network | on-going | RC | $5k/a support from MDBC |
| Rainfall:hydrograph analysis tools developed | in house models | Jun-07 | RC | comparison to HARTT |
| Look-up tables developed for physical parameters | gap analysis | Jul-05 | KT | continuation from 4.9 |
|  | colluvial & alluvial deposits | Jun-06 | KT | sand/silt dominated |
|  | "granite" saprolite | Jun-07 | KT | kaolinite dominant |
|  | "basalt" saprolite | Jun-07 | KT | mont. Dom. |
|  | "shale" saprolite | Jun-08 | KT | illite/smectite dom. |
| Look-up tables developed for chemical parameters | gap analysis | Dec-05 | DK | with RC & DR |
|  | column experiments | on-going | DK | as required from modelling requests |
|  | compilation of SAR | Jun-06 | DK | with RC & DR |
|  | compilation of CEC | Jun-06 | DK | with RC & DR |
|  | mineralogy effects | Jun-07 | DK | with RC & DR |
|  | salinity effects | Jun-08 | DK | with RC & DR |
| Look-up tables developed for hydrogeological parameters | gap analysis | Dec-05 | RC | input from all |
|  | existing data compilation | Jun-06 | RC | input from all |
|  | additional data accumulated | Jun-07 | RC | linked to drilling program |
| Look-up tables for physico-chemical parameters | effect of salinity on EC | Jun-06 | RC | input from all |
|  | effect of mineralogy on EC | Jun-07 | RC | input from all |
|  | effect of water on EC | Jun-07 | RC | input from all |
| 3D hydrogeological frameworks | Corangamite, VIC | Jun-07 | JC | external funding |
|  | Hodgson Creek, QLD | Jun-06 | MG | linked to QDNRM; MDBC case-study site |
|  | others as required | on-going | ALL | linked to QDNRM and MDBC case-studies |
| Integrated look-up tables for salinity modelling | synthesis of previous work | Jun-08 | ALL |  |

Timelines for activities

| 2005-06 | Jul-05 | Aug-05 | Sep-05 | Oct-05 | Nov-05 | Dec-05 | Jan-06 | Feb-06 | Mar-06 | Apr-06 | May-06 | Jun-06 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Journal papers, Technical Reports and Open File Reports | NAP projects |  | On-going |  |  |  |
| Papers presented at conferences |  |  | AIG-6 |  | IAH-NZ |  |  |  |  |  |  |  |
| Drilling of focus catchments | Hodgson Creek | SW slopes |
| Groundwater models developed in key NRM regions | Corangamite, Bland, Hodgson Creek, Warrego/Paroo, Border Rivers, Fitzroy Basin |
| Geochemical/solute models developed | Effects of salinity, Bland, Hodgson Creek, Goondoola Basin |
| Rainwater chemistry database | Monthly collection and analysis of rainfall from 20 sites across Australia |  |  |  |
| Rainfall:hydrograph analysis tools developed | Development of "in house" models and comparison to existing methods (e.g. HARTT) |
| Look-up tables developed for physical parameters | Gap | Colluvial and alluvial deposits |
| Look-up tables developed for chemical parameters | Gap analysis | SAR, CEC constraints |
| Look-up tables developed for hydrogeological parameters | Gap analysis | Existing data compilation |
| Look-up tables for physico-chemical parameters | effect of salinity & water on EC |
| 3D hydrogeological frameworks | Hodgson Creek | Corangamite |
| Integrated look-up tables for salinity modelling |  |  |  |  |  |  |  |  |  |  |  |  |
| 2006-07 | Jul-06 | Aug-06 | Sep-06 | Oct-06 | Nov-06 | Dec-06 | Jan-07 | Feb-07 | Mar-07 | Apr-07 | May-07 | Jun-07 |
| Journal papers, Technical Reports and Open File Reports |  |  |  | On-going |  |  |  |  |  |  |  |  |
| Papers presented at conferences | GSA/ASEG |  |  |  |  |  |  |  |  |  |  |  |
| Drilling of focus catchments | To be chosen |  |
| Groundwater models developed in key NRM regions | Fitzroy Basin, SEQ Western Catchments, L. Balonne/Maranoa |
| Geochemical/solute models developed | linked to QDNRM priorities |
| Rainwater chemistry database | Monthly collection and analysis of rainfall from 20 sites across Australia |  |  |  |
| Rainfall:hydrograph analysis tools developed | Development of "in house" models and comparison to existing methods (e.g. HARTT) |
| Look-up tables developed for physical parameters | Granite and basalt saprolite |
| Look-up tables developed for chemical parameters | mineralogical constraints |
| Look-up tables developed for hydrogeological parameters | data accumulation, drilling program complete |
| Look-up tables for physico-chemical parameters | effect of mineralogy on EC |
| 3D hydrogeological frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrated look-up tables for salinity modelling |  |  |  |  |  |  |  |  |  |  |  |  |
| 2007-08 | Jul-07 | Aug-07 | Sep-07 | Oct-07 | Nov-07 | Dec-07 | Jan-08 | Feb-08 | Mar-08 | Apr-08 | May-08 | Jun-08 |
| Journal papers, Technical Reports and Open File Reports |  |  |  | On-going |  |  |  |  |  |  |  |  |
| Papers presented at conferences |  |  |  |  |  |  |  |  |  |  |  |  |
| Groundwater models developed in key NRM regions | Condamine, Belyando/Suttor |
| Geochemical/solute models developed |  |  |  |  |  |  |  |  |  |  |  |  |
| Rainwater chemistry database | Monthly collection and analysis of rainfall from 20 sites across Australia |  |  |  |
| Rainfall:hydrograph analysis tools developed | Development of "in house" models and comparison to existing methods (e.g. HARTT) |
| Look-up tables developed for physical parameters | "shale" saprolite |  |
| Look-up tables developed for chemical parameters | salinity effects |  |
| Look-up tables developed for hydrogeological parameters | data validation (on-going) |  |
| Look-up tables for physico-chemical parameters |  |  |
| 3D hydrogeological frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrated look-up tables for salinity modelling | synthesis of previous work |