Cooperative Research Centre for Landscape Environments and Mineral Exploration

PROJECT SUMMARY				HO-170105

Project No:  		4.27

Submitted by:		Paul Wilkes

Date submitted: 	12 May 2005			V3   Recd 10.6.05

Project name:  	Yarra Yarra

Abbreviated title: 	Yarra Yarra

Type of project	Commercial + Centre

Program:  		4

Themes:  		Salinity systems in regolith and groundwater

Project Leader:  	Paul Wilkes

Start date and duration:  May 2004 to June 2006

Participants:	 CUT in collaboration with WA Agriculture and the Yarra Yarra Catchment Management Group.

Brief project description: (in no more than 500 words address objectives, scope of work, knowledge to date, what is new, interactions with other projects)

This is a continuation of a project which began in 2004 – 2005.

This LEME project is a component within the larger NAP/ NHT funded WA Govt program entitled: Feasibility study into establishing Yarra Yarra as a pilot demonstration project to demonstrate Catchment Governance and planning concepts. This WA Govt initiative will identify best-practice management and design criteria for a sustainable regional drainage system. It will provide seed funding to establish a working model of the combined initiatives to enable effective evaluation by the community. A second parallel WA Govt project has also been funded - A coordinated approach to dissemination and collection of NRM data in the Yarra Yarra sub-region.

The LEME Yarra Yarra Project P4.27 will produce soil maps from airborne geophysical datasets and digital elevation data drawn from the WA Land Monitor program and also from low level geophysical surveys. GA released a composite airborne geophysical dataset for the Burakin area in late February 2004. This combines newly acquired data flown for GA in 2003 with some existing company datasets. The study area – the Yarra Yarra catchment and surrounds - is located within the Ninghan, Bencubbin, Kellerberrin, Moora and Perth 1:250 000 map sheets.

The project builds on experience gained at Elashgin (in Kellerberrin map sheet) in 2001. This area of detailed airborne geophysics (20m flying height and 25m line spacing) has become a test area for soil mapping using a variety of techniques which include airborne and ground geophysics, conventional soil mapping, and very recently Hymap.

In Yarra Yarra catchment we are establishing a robust method for soil mapping from airborne geophysics and digital elevation data with associated field checking and analysis. The work is done in conjunction with WA Agriculture and engages with the Yarra Yarra Catchment Management Group. The group has produced some of their own soil maps by conventional methods which will be compared with the new maps.

An extension to the initial LEME project is to do work on up to six transects across the catchment to study linkage between surface drainage and underlying aquifers. Fieldwork for this extension to the project will be done in 2005–2006.

Deliverables (outputs) and expected impacts of research (outcomes):

- Establish methodology for efficiently producing soil maps from airborne geophysical datasets and digital elevation data.

- Soil maps for and with the Yarra Yarra Catchment Management Group.

- Report of drainage aspects of up to 6 transects across the catchment

Project outcomes will impact on decisions regarding a regional drainage system. Findings will feed into the second externally funded project on best use of NRM data for catchment management.

Milestones: (dates of significant events marking scientific progress)

- Preliminary radiometric, magnetic and DEM images produced in June 2004

- Soil sites sampled by DAWA in late 2004

- Soil maps to be produced by end June 2005.

- Fieldwork on up to ?six drainage transects done in mid 2005

Confidentiality requirements

No special requirements.

Date Endorsed by Executive and Approved by CEO;	22 June 2005

Date Endorsed by the Board:					8 July 2005

Note: Out-of-Budget revisions/updates to the approved Project Summary are to be submitted by Program Leader to Susan Game HO Perth for approval by CEO and advice to Business Manager.

RESOURCES 2005-2006

STAFFING-FTEs

(eg 0.50) for 2005-2006 (minimal fractional contribution should be 0.05)

| Staff name | In-kind, CRC or Industry | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wilkes | CRC |  |  | 0.2 |  |  |  |  |  | 0.2 |
| Harris | Ind |  |  | 0.1 |  |  |  |  |  | 0.1 |
| TOTAL |  |  |  | 0.3 |  |  |  |  |  | 0.3 |

All LEME STUDENTS contributing to Project 2005-2006

| Students Name | University | PhD or Honours |
| --- | --- | --- |
| Simon Abbott | CUT | PhD |

PROJECT OPERATING COSTS  $K  2005-2006

|  | $K | Source external funds |
| --- | --- | --- |
| CRC Opex funds requested | Nil |  |
| Committed (definite) external funds | 20 K | YYCMG |
| Total Project Opex |  |  |

| Possible additional external funds (for info) | 20 K |  |
| --- | --- | --- |

DISTRIBUTION OF TOTAL PROJECT OPERATING COSTS 2005-2006

Show major expenditure items and allocation to core parties

| Expenditure Item | ANU | AU | CUT | CSIRO EM | CSIRO LW | GA | NSW DPI | PIRSA | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 20 k |  |  |  |  |  | 20 k |
| Total |  |  | 20 k |  |  |  |  |  | 20 k |