QUARTERLY REPORTS – JANUARY TO MARCH 2004 – PROGRAM 2 (Ravi Anand)

AMIRA P618 – ISOTOPIC DISCRIMINATION OF PARTIAL LEACH GEOCHEMICAL ANOMALIES IN COVERED TERRAINS

# Project Leader:  G. Carr

During the period October 2003 to March 2004 the AMIRA P618 project has been focussed on the following endeavours.

Detailed sampling programs were undertaken over two case history sites.  At Kutarta, at MVT prospect on the Lennard Shelf, 184 samples were collected along three traverses over the surface projection of the blind mineralisation and in a “background” situation.  At the Wheatley Archaean VMS prospect 140 samples were taken over blind mineralisation and along background traverses.  All analytical work for the Kutarta project was completed and about 50% of the work for Wheatley.

- We have continued to develop the single pass ion exchange column technique using acetate solutions for Pb isotopic analysis.

- We have been working on a method of sequential stripping of Pb from soil samples to get signatures of the labile as well as the “background” components in each sample.

- We have finally solved problems in technique development for continuos flow mass spectrometry for S isotope analysis and have commenced analysis of several hundred samples.

Two case history reports have been written and are being circulated internally for review.

DEVELOPMENT OF GEOCHEMICAL MODELLING

Project Leader:  D.C. McPhail

This project is a strategic one because it is a direct link with pmd*CRC.  Progress in last quarter consists of compiling references related to the thermodynamic properties of gold and iron minerals and aqueous species, and the continued development of the web-based database of thermodynamic properties and ancillary software to provide database files useable in current state-of-the-art geochemical software packages (e.g., Geochemist’s Workbench and HCh).

Laura Richardson (undergraduate; ANU) was hired to assist with the compilation of gold and iron references.

Ge/Si and Ga/Al INDICATORS

Project Leader:  S. Welch

The purpose of this project was to investigate mobility of trace elements with respect to major elements during weathering, specifically focusing on Ge/Si and Ga/Al ratios.  It is suggested that the element mobility could be significantly different under predominately inorganic versus biotic-organic dominated weathering reactions.  The scope of the project has broadened to focus on the effects of biotic verses abiotic processes on mineral weathering in the regolith.

I have made considerable progress for this project in the last few months primarily due to the fact that (i) we now have a small but functioning lab for use by several LEME researchers in the Department of Earth and Marine Sciences and (ii) that the ICP-MS in our department is currently working for solution analysis.

In the last few months, I have started several sets of mineral dissolution experiments with mineral separates in solution of organic and inorganic acids over a range of pH to determine a baseline behaviour.  Results show that major ion release to solution is ~ 2 to 10 fold greater in organic solutions compared to inorganic controls depending on experimental conditions. Major ions such as Al and Fe are preferentially released to solution compared to inorganic controls, presumably due to the formation of metal-organic complexes.  Analysis of trace elements such as Ga, Ti, V, Li, REE, show they are preferentially mobilised by organic acids as well.

Based on results of the initial analysis, additional samples of the Bemboka granodiorite have been prepared for laser ablation analysis.  Many of the samples have been characterized by electron microscopy to target areas for analysis by laser ablation ICP-MS, though samples have not yet been analysed.

In April 2004 I collected additional samples from Bemboka for organic extraction and mineral leaching experiments.  Samples have been crushed and sieved and are being prepared for bulk rock geochemistry and clay analysis.

GOLD, LEAD AND ARSENIC MOBILITY

Project Leaders:  D.C. McPhail and D.J. Gray

The main aims of this project are to understand better the geochemistry and mobility of gold, and the properties and solubilities of lead- and arsenic-bearing apatite-group minerals.

This is an integrated project that consists of multiple experimental, numerical modelling and field studies.  The individual components include: the geochemistry of gold in hypersaline brines; the relationship between biota and gold mobility; the reactive transport of gold; sorption of gold on mineral surfaces; the synthesis, solid solution properties and solubility of lead- and arsenic-bearing apatite-group minerals.

- Experiments have started on the geochemistry of gold in hypersaline brines (Ph.D. student Alistair Usher).

  - UV-Vis spectra have been measured for Au(III, I) in chloride, iodide and thiosulphate solutions.  Preliminary results show promise in identifying Au(I) thiosulphate complexes and possibly Au(I) iodide complexes; however, Au(I) chloride complexes are probably invisible in the observable range of UV-Vis wavelengths.

  - A preliminary experiment to measure the solubility of native gold under halite-saturated conditions has commenced.  We need to establish our methodology of measuring very low (e.g., ppt) concentrations of dissolved gold in concentrated salt solutions.  We are also exploring the possibility of using Au(I) solids in order to avoid the need for precise control of redox in these experiments.

  - There is a link with LEME project 2.20 Development of Geochemical Modelling. The initial stage of that project is to develop a database of reliable thermodynamic properties for gold minerals and aqueous species, over wide ranges in temperature, pressure and solution composition.  This will provide a basis with which we can predict gold geochemistry and mobility in regolith and other environments.

- Ongoing progress in the studies of microbiology and gold (Ph.D. student Frank Reith).  The most important aspects in this quarter have been:

  - Continued experimental studies of microbiological growth and the mobilisation of gold in regolith samples (>70 day experiments to determine correlations between changes in bacterial population and concentrations of gold and other elements) – results are pending chemical analysis of sampled solutions.

  - DAPI staining (for DNA and RNA associated with gold grains from regolith samples) and confocal microscopy.  Biofilms have been identified on gold grains from the Palmer River region of Queensland.  This may be the first evidence in the world of biofilms on gold grains that have a morphology attributed to bacterial activity.

  - Preparation of first manuscript from Frank Reith’s research.  Present title is “Bacillus cereus, gold and associated elements in soil and regolith samples from Tomakin park gold mine in south-eastern New South Wales”, the manuscript draft is complete and is in final revisions here and will be submitted to Journal of Geochemical Exploration (plan is during October 2003).

- Reactive transport experiments and gold mobility

  - Dirk Kirste, Sue Welch and Frank Reith will begin to set up column experiments, building on the experience of David Gray’s work a few years ago in Perth.

- Sorption experiments

  - We are unlikely to study sorption in the short term; however, we have made contact with David Cohen of UNSW, who did an experimental study on Au(III) on goethite, kaolinite and smectite as part of his Ph.D. several years ago.  David Cohen has recently submitted a manuscript on that work to GEEA, and is now revising it after receiving reviewers’ comments.  There is a good possibility of collaboration with his group.

- Lead- and arsenic-bearing apatite-group minerals

  - Natural apatite-group minerals have been obtained (from Sweden) and their chemical compositions measured.  The results clearly show a solvus gap in the solution between hedyphane (Pb-Ca-Cl arsenate) and johnbaumite-turnearite (richer in Pb and poorer in Ca than hedyphane).  Materials are being obtained to start synthesising end-members of the apatite group, in preparation for studying solvus gaps in the solid solutions and solubilities of the minerals in aqueous solutions.

GEOCHEMICAL DISPERSION MECHANISMS THROUGH TRANSPORTED COVER

Project Leader:  Mehrooz Aspandiar

There are two aims of the project.  The first is to conduct a literature search on the potential geochemical dispersion mechanisms operating through transported regolith cover, and this phase has been initiated and is in progress.  The type, nature and extent of the different mechanisms is being researched, documented and placed in a framework for the nature of the Australian transported regolith.  The second aim is to find field sites having characteristics where the effectiveness of the potential mechanisms will be tested, and planning is in progress to visit some of the prospective sites.  The sites will be tested with surface sampling and geochemical analysis to validate whether anomalies can be seen through cover and subsequently test the mechanisms.

MINERAL HOSTS

#### Project Leader:  R. Hough

To better understand the formation of geochemical anomalies in the regolith.  The project involves constraining mineralogical associations with significant trace elements, especially Au in regolith from different deposits.  It provides an insight into the dispersion processes for trace elements into mineral hosts, also their environmental implications.  Ultimately we aim to determine how geochemical anomalies form that in turn will assist in the understanding of when, how and where particular regolith material is applicable for the exploration industry.

- New electron microprobe data has been acquired for Mount Gibson Enterprise pit samples including work on the hardpan, ferricete and saprolite.  Appreciable anomalism was detected and these results further confirm, and add to the previous Laser Ablation ICPMS results.

- Lancefield South:  Samples from various sedimentary units ranging from Quaternary to Permian sediments and in situ regolith were collected from pit walls to investigate whether there is any dispersion in secondary minerals developed in the overlying sediments from the underlying mineralisation.  A variety of techniques including petrography, SEM, electron microprobe, Laser Ablation ICPMS and XRD are being used to characterise the regolith materials.  Results from geochemical analyses of different constituents of regolith materials have been received for a suite of 25 samples.  Initial electron microprobe data show there is dispersion of As and Cu in goethite in Permian sediments, and only Cu in goethite of Tertiary sediments, and possibly goethite and smectite in red-brown hardpan.  Laser Ablation ICPMS analysis is underway.

- Results from Mount Gibson and Lancefield South indicate we are able to detect late stage Au and pathfinder element dispersion within weathering products in transported overburden.

- We have collected samples from the Whirling Dervish gold prospect in cooperation with the Northern Yilgarn team.  Bulk geochemical analyses have been performed, and we have prepared polished thin sections that are now ready for detailed petrography, SEM and Probe analyses.

- We have made extensive headway in analysis of the internal crystallography of gold nuggets and are in the process of acquiring some further samples.  Our current results show how silver depletion lies along crystal boundaries within the gold and that the depleted areas are in the same crystallographic orientation as their host grains.

- Ray Smith (CSIRO EM), on retiring in February after 31 years’ employment with CSIRO, has been appointed a CSIRO Emeritus Research Fellow.  In this role, he continues his research into geochemical dispersion from concealed mineral deposits.  His investigation of the basal lateritic conglomerate, which forms the cover about the Golden Grove Gossan Hill Cu-Zn-Au VHMS deposit, has established criteria for identification, in the cover, of detritus derived from the ore deposit or its immediate proximity.  The study sites are located within the kilometre-wide multi-element geochemical dispersion anomaly described by Ray Smith and John Perdrix in 1983.  Such broad and strongly-zoned anomalies are important in mineral exploration for concealed ore deposits.  The current study focuses on: (a) improved methods for ranking of geochemical anomalies; and (b) translating findings for a proposed model for exploration involving drilling through thick cover applicable elsewhere.  A poster paper on this research has been accepted for presentation at the international SEG 2004 Conference “Predictive Mineral Discovery Under Cover” in Perth in September.

#### Ryan Noble (PhD study)

The research project on arsenic and antimony distribution in regolith continues to develop.  Over the past months the following work has been conducted towards establishing and completing this project:

- I have sieved recently collected soil samples to various size fractions for future analysis.  The samples were from the past sampling trip in November covering the Stawell region and Wildwood prospect.

- I have conducted some cluster and principle component statistical analysis on the Wartook soils, confirming that the various techniques give different results and are significantly different, however like initially thought the Bacterial Leach is similar to the hydroxylamine hydrochloride technique and the water and weak hydrogen peroxide technique are also very similar to each other, but very different from the previously mentioned techniques.  Total dissolution technique was in between these two groups.  Similarities between element responses for all techniques are not clearly explainable yet.  Some groupings of Ni with Zn were expected, but further investigation and understanding of the results is required.

- I have written a report on the Wartook soils to be included in the SGM Wartook annual report appendices.

- Although, not directly related to the project, I have submitted a paper to be published in the American Society of Mine Reclamation (ASMR) Proceedings in April based on the Stawell Gold Mine Mt. Micke geochemical characterisation.

- The Wildwood samples have been analysed using the Bacterial Leach and ICPMS, however I have not received the results back.

- I have done some analysis of the calcrete data and also contacted Stan Harrison, who has provided some helpful information.  The calcrete data was examined spatial variation of elements.  The sampled area is approximately 600 km2 and encompasses the Kewell and Wallup prospects.  Initial findings indicate there is minor variation in element concentrations and the carbonate materials are fairly uniform.  Initially, the results indicate calcrete sampling is not beneficial in sampling for signatures of underlying mineralisation in the Murray Basin alluvial sediments.  The regional calcrete is subject to too high rainfall and too deep transported cover to be an effective sampling medium.  I do plan to follow this up with a comparison of chemistry and underlying geology types, as well as trying to incorporate drilling data.

- I have investigated the use of sequential leaches and have Wildwood samples ready to be analysed.  .

- Mineralogical analysis is being planned using the PIMA/ASD instrument at CSIRO.  The analysis should provide information on some clay types, iron oxides and carbonates present in the soils.  The information will be beneficial in determining if mineralogy is influential in anomaly expression.

- Several presentations made to the LEME review panel including members of the Minerals Advisory Council.

BIOLOGICAL AND NON-BIOLOGICAL FACTORS INVOLVED IN THE FORMATION OF GOLD IN CALCRETE ANOMALIES

Student:  M.J. Lintern (Curtin University)

Studies of calcrete and their associated materials in the soil profile continued on two fronts this quarter.  Zonation of gold in calcrete was studied using laser ablation which re-commenced after a number of setbacks last year.  The first results are being processed and the rate of sample submission will gather pace in the coming weeks if confidence in the instrumentation, the technique and the data increases.  The geobiological factors involved in gold in calcrete formation has commenced.  Bacillus cereus and other spore-forming soil bacteria have been isolated from gold prospects in South Australia and Western Australia.

MINERAL MAPPING SOUTH AUSTRALIA

##### Project Leader:  Alan Mauger

HyLogger:

- Completed scanning 35,000 metres of drill core by 20 January 2004.

- Ongoing processing of data into TSG (The Spectral Geologist program) format through to mid-March.

- Visit to CSIRO North Ryde - TSG training and discussions on Web Delivery of HyLogger data.

Central Gawler Gold:

- Made presentation on HyLogger project.

- Established some priorities for processing HyLogger data.

- Consulted on ASTER data processing for project.

John Keeling:

- Examining HyLogger data for Tunkillia, Barns and Pine Creek.

- Barns results indicate correlation between mineralogy and gold mineralisation.

- Barns study allows comparison of chips vs core and HyLogger vs PIMA.

Ian Lau (PhD student):

- Processed White Dam HyMap data - using SWIR spectral indices has produced FeOx/Veg maps. Next phase is to produce SWIR mineral maps and compare to other processing techniques.

- Regolith Mapping: using HyMap, Radiometrics, Landsat, & DEM  produced 1:30,000 map covering same area as HyMap.Completed line tracing and sent to GA for scanning.

- 3 day field trip to White Dam for sampling.

OBJECTIVE REGOLITH LOGGING

Project Leaders:  R. Anand / T. Munday

To develop a practical automatic interpretation tool/s and procedures for logging regolith materials returned as core, drill chips, or pulps.

- Defined strategy to test mixed (compositionally) samples as part of a spectral library in TSG/TSA software.

- Case Study:

Moolart Well:

- Cross-section generation of drill logs and recorrecting major anomalies in regolith logging (based on log codes).

- MVS file preparation (create geology file based on Newmont logging; create assay files for Ag, As, Au, Cr, Cu, Fe, Mn, Mo, Ni, Pb, Sb, Zn, HmGt, FeOx, Kindex, Brightness, Colour Index, HK, MgChlorite, Montmorillonite, Opal).

- Gridding of above files and investigation of appropriate limits/settings for each.

- Image generation – slices and 3d fence diagrams of above.

- Despatch of 190 samples from a transect across different lithologies at Moolart Well for geochemical and XRD analyses.

Gidgee:

- Investigate the mineralogical composition of three drill intersections at Gidgee transect using X-ray diffractograms, supplemented by geochemical data as a control for interpretation of VNIR spectral indices-still ongoing.

- Evaluation of portable XRFs:

- The Niton Xli700 Environmental Analyser (uses radioactive isotope 55Fe and 109Cd as source) vs Innov-X XT-440 Soil Analyzer (uses miniature X-ray tube).

- A sample set of about 65-70 powdered regolith samples of different regolith types from felsic and mafic lithologies including known standards were tested for both instruments.  Niton instrument was tested by CRCLEME personnel while Innov-X did the testing in USA.  Elements of interest include Fe, Mn, Ca, Ti, Cr, Zr, K, Rb, Ni, Co, Cu, V, Pb, Ba, Zn.  Data acquired from the instruments were compared with our known XRF data.

- The highlight of the results indicates in general that Niton Portable XRF is promising, with a lower detection limits than Innov-X Portable XRF in a range of elements, the latter detecting only elements Cr,Fe,Sr,Ti and Zr.  Both instruments show consistent performance over a wide concentration range for Sr, Zr, and Fe, the latter element showing a non-linear response.  In addition, Niton also gives a better linear response for Ti and Rb over a wide concentration range.  Both instruments however give very poor Co results, due to interference by Fe.  Although both instruments report fairly poor accuracy in Cr especially below 1500-2000 ppm, Niton still gives a better result.  In terms of precision, Fe gives the best precision for both Niton (5.3% on 12 replicate analyses at 22% Fe, exposure time of 30s) and Innov-X (2.5% on 10 replicate analyses at 32% Fe, exposure time of 40-45s) instruments.

- Presentation of project results and progress at internal CRCLEME project review in March 2004.

- Need to develop strategy for investigating the broader commercialisation options for the Objective logging project.  This should be integrated with broader CSIRO EM commercialisation strategy for spectral logging systems.

REGOLITH EXPRESSION OF AUSTRALIAN ORE SYSTEMS

#### Project Leader:  C.R.M. Butt

To assemble and publish a monograph summarizing the characteristic expression of bedrock ore systems in the Australian regolith, as a series of conceptual dispersion, process and exploration models, illustrated by relevant case histories.

About 15 case histories were added to the LEME web page during the quarter, making a total of 50.  A further  50 are under review.  Six supporting articles have also been drafted and are under review.

We anticipate there will be a final total of 100 case histories.  Good progress was made in the this quarter, but will slow in the next quarter with the demands of field work in other projects.  The departure of Keith Scott in July will be a considerable loss.

Project staff and ‘outside authors’ will continue to revise case histories and edit the contributions, and completed case histories will continue to be released on the web when completed.  Further introductory articles will be written/reviewed.

## WESTERN NSW REGOLITH

Project Leader:  P. de Caritat

- Appointment of Luisa Ruperto (from 18 February, 2004) as GIS specialist for the WNSWR project.

- Development of a basement depth and regolith thickness model for Teilta 1:100,000 map-sheet based on drill-hole data and outcrop observation.

- Database population for geochemical GIS of the Broken Hill region, and initial concept development for geochemical GIS of all the project-generated geochemical data in the area (since 1998).

- 2D reactive-transport modelling of the formation and dispersion of hydrogeochemical anomalies around sulfide mineralisation.

- Karen Hulme carried out field work sampling River red gum material and performing analyses.

- Other students started (details: cfr Steve Hill).

- Shortcourse on “Geochemical Modelling” at ANU (27-30 Jan 2004).

- Presentation at the Australian Geological Convention (Hobart, 8-13 Feb 2004).

- LEME-MTEC Shortcourse on “Regolith Geology & Geochemistry”, Wilsons Promontory, Victoria (23-27 Feb 2004).

- LEME-MTEC Shortcourse on “Regolith Mapping & Field Techniques”, Fowlers Gap via Broken Hill, NSW (15-19 March).

- LEME-MTEC Shortcourse on “Introduction to Hydrogeochemistry”, Melbourne, Victoria (29 Mar-2 Apr 2004).

YILGARN LATERITE ATLAS

#### Project Leader:  M. Cornelius

In early March, we completed a reconnaissance field trip to the southern wheat belt and introduced two sampling teams to laterite sampling protocols and landform appraisal in order to identify suitable sample sites.  One sampling team led by Don Hunter remained in the field and took 163 samples on the Dumbleyung and Newdegate 1:250 000 geological sheets.  Approval was given by CALM to enter all nature reserves and national parks for sampling.

All samples are stored with the Geological Survey at their Carlisle facility.  Sampling will continue in April and May.

YILGARN REGOLITH PROJECT (CONFIDENTIAL)

NORTHERN YILGARN

#### Project Leader:  M. Cornelius

Due to OHS concerns, work planned at the Karari pit, Carosue Dam, had to be cancelled.  Instead, work commenced at the Whirling Dervish prospect, 1.5 km north of Karari pit, in a geological setting very similar to that at Karari.

Thirteen aircore holes (719 m) were drilled to obtain samples of various regolith materials for mineralogical and geochemical studies.  Au analyses show that weak enrichment is widespread in the top 3-5 m, dominantly a carbonate-cemented gravely colluvium.

Diamond drill core from the Whirling Dervish pit was logged (regolith only) and photographed.  In addition, approximately 200 specimens were taken for geochemical and/or mineralogical investigations.

Results of geochemical analyses (53 elements) have been received for a suite of 55 regolith and seven fresh rock samples from diamond drill cores.  The results will be statistically evaluated together with the results of Sons of Gwalia fresh rock analyses from the Karari pit.  A preliminary evaluation shows that significant pathfinder elements are Au and Bi.

Thin sections of 11 samples from diamond core are being prepared and will be examined to determine critical fabrics which may aid core and drill spoil logging.

Spectroscopic analysis of the chip tray materials was completed for all 719 aircore samples using an ASD instrument.  The dominant minerals in the regolith are kaolinite/halloysite and montmorillonite.  In the saprock, muscovite, phengite, ankerite and Mg-chlorite are present.

The colour and crystallinity index of sediments in the south western part of Whirling Dervish are very different from those of in situ material.  A distinct change in kaolinite crystallinity and colour index indicate a thickness of the transported cover of approximately 15 m.

In the north eastern part of the area, the depth of the unconformity appears to be about 24 m (Figure 4).  The spectral difference between sediments and saprolite is less obvious and it appears the sediments below about 15 m depth are bleached and kaolinite crystallinity has increased during this process. The material with a crystallinity index <1, a generally accepted range for transported kaolinite, is tentatively classified as sediment.

Work in the northern Leonora area has been delayed and will commence in April.   The work will be in conjunction with studies at the Jaguar base metal deposit south of Teutonic Bore.

#### SOUTHERN YILGARN – ST IVES

#### Project Leaders:  B. Singh and D.J. Gray

Final project outcomes were presented to Gold Fields at their St Ives site in December 2003.  In this quarter posters describing the results have been prepared.  A preliminary proposal to extend the project at St Ives was also developed in collaboration with Jon Huntington.